## Slide 1
Business Process Automation
Kenitra Invoice-Matching Automation
A narrow, well-scoped RPA project with no judgment calls — journi's deliberate low-resistance, fast-moving contrast case.
7
PHASES
19
WEEKS
6
EXCEPTIONS
3
TRAINING TIERS
Manufacturing Sector · Bouregreg Group Scenario Library · Confidential

## Slide 2
PART 0 — PURPOSE
What This Guide Is, and How to Use It
WHAT THIS GUIDE IS
This deck follows the Kenitra Invoice-Matching Automation program — journi's Business Process Automation archetype case — from tenant setup through CoE handover, the shortest and cleanest program in the entire scenario library.
HOW TO USE IT
This program runs inside the same Bouregreg Group tenant as every other archetype in this series. A reader with the tenant already set up skips straight to CM Project creation.
journi — Business Process Automation (Kenitra Invoice-Matching Automation)
01

## Slide 3
PART 0 — A NOTE ON FIDELITY
Verified Against journi's Real Source
This is journi's own stated case with no alerts in its real record. This deck states that plainly, the same way it documents every real exception in the series' other guides — a clean record reported as a clean record, not dramatized, with six realistic contingency patterns shown as hypothetical precisely because none of them actually occurred.
RACSI CODES USED THROUGHOUT
ES = Executive Sponsor · CM = Change Manager · PM = Program/Project Manager · FPO = Functional Process Owner · ITL = IT/Technical Lead · SUP = Supervisor · EU = End User
journi — Business Process Automation (Kenitra Invoice-Matching Automation)
02

## Slide 4
PART 1 — EXECUTIVE SUMMARY
Why This Case Matters
Every other guide in this series shows a program working through a real risk. This one proves the opposite point just as concretely: not every Change Management Project needs a recovery playbook, when the scope is narrow, the team is already bought in, and the Sponsor is visibly active from day one.
journi — Business Process Automation (Kenitra Invoice-Matching Automation)
03

## Slide 5
PART 1 — EXECUTIVE SUMMARY
The Case, in Brief
18 staff, Kenitra accounts payable
19 weeks (guide numbering)
A robotic process automation project matches supplier invoices against purchase orders at the Kenitra plant — a repetitive task with no judgment calls, automated in 19 weeks against an already-bought-in 18-person team.
journi — Business Process Automation (Kenitra Invoice-Matching Automation)
04

## Slide 6
PART 1 — EXECUTIVE SUMMARY
What This Guide Proves, Concretely
A closed program with zero of journi's 9 live alerts fired, a real two-week shadow-mode validation before go-live, and six honestly-labeled hypothetical contingencies showing exactly how this program could have gone differently, had the conditions been less favorable.
journi — Business Process Automation (Kenitra Invoice-Matching Automation)
05

## Slide 7
PART 2 — THE FOUR FRAMEWORKS
Weighting for This Archetype
All four frameworks read favorably from the start, by design. This is journi's deliberate contrast case: a narrow scope, an already-bought-in team, and a visibly active Sponsor mean no framework carries unusual risk — the point being that not every program needs a recovery playbook.
journi — Business Process Automation (Kenitra Invoice-Matching Automation)
06

## Slide 8
PART 2 — THE FOUR FRAMEWORKS
The Composite Readiness Index, Read for This Case
The Composite Readiness Index reads high and rising from Week 1 with no dip worth naming — Benchmarking reads "Ahead" for most of the program's life, and this guide's own honesty standard applies here just as strictly as anywhere else: a clean trend is reported as a clean trend.
journi — Business Process Automation (Kenitra Invoice-Matching Automation)
07

## Slide 9
PART 3 — TENANT AND ADMIN SETUP
The Existing Tenant, and Reading Paths by Role
THE EXISTING TENANT
This program runs inside the same tenant journi's Master User Guide builds, under the existing Bouregreg Manufacturing Maroc Organization — no new Organization needed.
READING PATHS, BY ROLE
› A Change Manager running this program day to day: Part 2 once, then Part 4 in full.
› A Program/Project Manager: Part 4's PM Track column and the Master WBS & Gantt.
› An Executive Sponsor: Part 1, then Part 4's phase-opening narratives.
› A Super Admin or Org Admin: Part 3.
journi — Business Process Automation (Kenitra Invoice-Matching Automation)
08

## Slide 10
PART 3 — TENANT AND ADMIN SETUP
The RACSI Team for This Program
Name | RACSI Code | Role
Hakim Berrada | ES | Sponsor
Salma Ouazzani | CM | Change Manager
Amine Sqalli | PM | Program Manager
Yassine Kabbaj | ITL | IT/Technical Lead
Nawal Fassi | FPO, SUP | Functional Process Owner and Supervisor, combined
journi — Business Process Automation (Kenitra Invoice-Matching Automation)
09

## Slide 11
PART 3 — TENANT AND ADMIN SETUP
Creating the CM Project
1
On Module 1 — Hierarchy, create the Kenitra Invoice-Matching Automation CM Project under the existing Bouregreg Manufacturing Maroc Organization.
2
Set Change type: Business Process Automation. Target population: "Kenitra accounts payable, 18 staff." Business driver: "A repetitive task with no judgment calls — a strong automation candidate."
3
Save. Lewin opens at Unfreeze — the team already bought in, unlike every resistance-driven case elsewhere in this series.
4
On Module 17 — WBS & Gantt, load the TPL-BPA-7 phase template: Automation-Opportunity Assessment, Architecture Design, Build, UAT & Shadow-Mode, Production Go-Live, Exception Tuning, CoE Handover.
journi — Business Process Automation (Kenitra Invoice-Matching Automation)
10

## Slide 12
PART 3 — TENANT AND ADMIN SETUP
Charters for This Program
Charter | Accountable | Review Cadence
CHTR-01 Sponsorship / Leadership Charter | Hakim Berrada (ES) | Per Phase Gate
CHTR-08 Pulse / Interview Charter | Salma Ouazzani (CM) | Per phase gate + ad hoc
journi — Business Process Automation (Kenitra Invoice-Matching Automation)
11

## Slide 13
PART 3 — TENANT AND ADMIN SETUP
Setup Checklist
Base tenant confirmed (Bouregreg Group, existing Organization)
Automation program team accounts created
CM Project created, Lewin opened at Unfreeze
TPL-BPA-7 phase template loaded on M17
Applicable Charters reviewed and accountable owners confirmed
journi — Business Process Automation (Kenitra Invoice-Matching Automation)
12

## Slide 14
PART 4 — WEEK-BY-WEEK TIMELINE
7 Phases, In Order
1. Automation-Opportunity Assessment
2. Architecture Design
3. Build
4. UAT & Shadow-Mode
5. Production Go-Live
6. Exception Tuning
7. CoE Handover
Total program length: 19 weeks (guide numbering). Every phase below is walked in detail across the next slides — normal flow first, then six exceptions in full operational detail.
journi — Business Process Automation (Kenitra Invoice-Matching Automation)
13

## Slide 15
PHASE 1 OF 7
Automation-Opportunity Assessment
Weeks 1–4
NARRATIVE
Confirms the invoice-matching task is genuinely low-exception and judgment-free — the specific test every automation candidate has to pass before Architecture Design begins.
journi — Business Process Automation (Kenitra Invoice-Matching Automation)
14

## Slide 16
PHASE 1 · AUTOMATION-OPPORTUNITY ASSESSMENT
Key Moments in This Phase
Week | What Happens
Week 1 | Kickoff; Lewin opens at Unfreeze.
Week 3 | Historical invoice data sampled to confirm low exception rate.
Week 4 | Opportunity assessment gate closes.
journi — Business Process Automation (Kenitra Invoice-Matching Automation)
15

## Slide 17
PHASE 1 · AUTOMATION-OPPORTUNITY ASSESSMENT
Framework Snapshot
LEWIN
Unfreeze
ADKAR
Awareness
BRIDGES
Exploration
KÜBLER-ROSS
Commitment
KEY TECHNIQUE THIS PHASE
Exception-rate sampling: Confirm the task is genuinely low-judgment before committing design effort.
journi — Business Process Automation (Kenitra Invoice-Matching Automation)
16

## Slide 18
PHASE 2 OF 7
Architecture Design
Weeks 4–9
NARRATIVE
Designs the bot's architecture against the confirmed opportunity — where a licensing or platform constraint (Exception C5) could realistically surface.
journi — Business Process Automation (Kenitra Invoice-Matching Automation)
17

## Slide 19
PHASE 2 · ARCHITECTURE DESIGN
Key Moments in This Phase
Week | What Happens
Week 5 | Bot architecture drafted against the purchase-order matching logic.
Week 9 | Architecture design signed off.
journi — Business Process Automation (Kenitra Invoice-Matching Automation)
18

## Slide 20
PHASE 2 · ARCHITECTURE DESIGN
Framework Snapshot
LEWIN
Unfreeze
ADKAR
Knowledge
BRIDGES
Exploration
KÜBLER-ROSS
Commitment
KEY TECHNIQUE THIS PHASE
Bot architecture design against real system constraints: Design against actual platform/licensing limits, not assumed ones.
journi — Business Process Automation (Kenitra Invoice-Matching Automation)
19

## Slide 21
PHASE 3 OF 7
Build
Weeks 9–12
NARRATIVE
Builds the bot against the signed-off architecture — the phase this guide's contingency patterns C1, C4, and C5 all map to.
journi — Business Process Automation (Kenitra Invoice-Matching Automation)
20

## Slide 22
PHASE 3 · BUILD
Key Moments in This Phase
Week | What Happens
Week 10 | Development against the purchase-order matching logic.
Week 12 | Build gate closes; internal testing confirms exception-handling rules.
journi — Business Process Automation (Kenitra Invoice-Matching Automation)
21

## Slide 23
PHASE 3 · BUILD
Framework Snapshot
LEWIN
Change
ADKAR
Knowledge
BRIDGES
Exploration
KÜBLER-ROSS
Commitment
KEY TECHNIQUE THIS PHASE
Iterative build against the matching logic: Build the bot's core matching logic and exception-handling rules together.
journi — Business Process Automation (Kenitra Invoice-Matching Automation)
22

## Slide 24
PHASE 4 OF 7
UAT & Shadow-Mode
Weeks 12–14
NARRATIVE
Runs the bot alongside the manual process for two weeks — a real, not simulated, validation before any production dependency.
journi — Business Process Automation (Kenitra Invoice-Matching Automation)
23

## Slide 25
PHASE 4 · UAT & SHADOW-MODE
Key Moments in This Phase
Week | What Happens
Week 12 | Shadow-mode begins; bot runs in parallel with the manual process.
Week 14 | Shadow-mode closes clean; UAT gate passes.
journi — Business Process Automation (Kenitra Invoice-Matching Automation)
24

## Slide 26
PHASE 4 · UAT & SHADOW-MODE
Framework Snapshot
LEWIN
Change
ADKAR
Knowledge → Ability
BRIDGES
Exploration
KÜBLER-ROSS
Commitment
KEY TECHNIQUE THIS PHASE
Two-week parallel shadow-mode run: Validate the bot against real production data with a real fallback still active.
journi — Business Process Automation (Kenitra Invoice-Matching Automation)
25

## Slide 27
PHASE 5 OF 7
Production Go-Live
Weeks 14–16
NARRATIVE
Cuts the manual process over to the bot in production — the shortest go-live window in the scenario library.
journi — Business Process Automation (Kenitra Invoice-Matching Automation)
26

## Slide 28
PHASE 5 · PRODUCTION GO-LIVE
Key Moments in This Phase
Week | What Happens
Week 14 | Production go-live.
Week 16 | Go-live gate closes; stability confirmed.
journi — Business Process Automation (Kenitra Invoice-Matching Automation)
27

## Slide 29
PHASE 5 · PRODUCTION GO-LIVE
Framework Snapshot
LEWIN
Change
ADKAR
Ability
BRIDGES
New Beginning
KÜBLER-ROSS
Commitment
KEY TECHNIQUE THIS PHASE
Direct production cutover: Cut over once shadow-mode has already proven the bot clean.
journi — Business Process Automation (Kenitra Invoice-Matching Automation)
28

## Slide 30
PHASE 6 OF 7
Exception Tuning
Weeks 16–18
NARRATIVE
Tunes the bot's exception-handling rules against real production volume, not just the test sample.
journi — Business Process Automation (Kenitra Invoice-Matching Automation)
29

## Slide 31
PHASE 6 · EXCEPTION TUNING
Key Moments in This Phase
Week | What Happens
Week 16 | Real-volume exception patterns reviewed.
Week 18 | Exception-handling rules finalized and stable.
journi — Business Process Automation (Kenitra Invoice-Matching Automation)
30

## Slide 32
PHASE 6 · EXCEPTION TUNING
Framework Snapshot
LEWIN
Change → Refreeze
ADKAR
Ability → Reinforcement
BRIDGES
New Beginning
KÜBLER-ROSS
Commitment
KEY TECHNIQUE THIS PHASE
Real-volume exception review: Tune rules against real production volume, which always differs from the test sample.
journi — Business Process Automation (Kenitra Invoice-Matching Automation)
31

## Slide 33
PHASE 7 OF 7
CoE Handover
Weeks 18–19
NARRATIVE
Hands the bot's ongoing monitoring to the Center of Excellence — the handover Exception C6 warns can happen on paper without genuinely transferring.
journi — Business Process Automation (Kenitra Invoice-Matching Automation)
32

## Slide 34
PHASE 7 · COE HANDOVER
Key Moments in This Phase
Week | What Happens
Week 18 | CoE handover package delivered.
Week 19 | Program closes with zero alerts fired.
journi — Business Process Automation (Kenitra Invoice-Matching Automation)
33

## Slide 35
PHASE 7 · COE HANDOVER
Framework Snapshot
LEWIN
Refreeze
ADKAR
Reinforcement
BRIDGES
New Beginning
KÜBLER-ROSS
Commitment
KEY TECHNIQUE THIS PHASE
Genuine capacity-backed handover: Ensure ongoing monitoring ownership actually transfers, not just the paperwork.
journi — Business Process Automation (Kenitra Invoice-Matching Automation)
34

## Slide 36
PART 4 — MASTER WBS & GANTT
Every Phase, Across the Four Frameworks
Phase | Week(s) | Lewin | ADKAR | Bridges | Kübler-Ross
Automation-Opportunity Assessment | Weeks 1–4 | Unfreeze | Awareness | Exploration | Commitment
Architecture Design | Weeks 4–9 | Unfreeze | Knowledge | Exploration | Commitment
Build | Weeks 9–12 | Change | Knowledge | Exploration | Commitment
UAT & Shadow-Mode | Weeks 12–14 | Change | Knowledge → Ability | Exploration | Commitment
Production Go-Live | Weeks 14–16 | Change | Ability | New Beginning | Commitment
Exception Tuning | Weeks 16–18 | Change → Refreeze | Ability → Reinforcement | New Beginning | Commitment
CoE Handover | Weeks 18–19 | Refreeze | Reinforcement | New Beginning | Commitment
journi — Business Process Automation (Kenitra Invoice-Matching Automation)
35

## Slide 37
PART 4 — MASTER WBS & GANTT
Every Phase, Techniques and Tools
Phase | Week(s) | Technique | Goal | Tool
Automation-Opportunity Assessment | Weeks 1–4 | Exception-rate sampling | Confirm the task is genuinely low-judgment before committing design effort. | M21 (Field Notes)
Architecture Design | Weeks 4–9 | Bot architecture design against real system constraints | Design against actual platform/licensing limits, not assumed ones. | M17 (WBS & Gantt)
Build | Weeks 9–12 | Iterative build against the matching logic | Build the bot's core matching logic and exception-handling rules together. | M21 (Field Notes)
UAT & Shadow-Mode | Weeks 12–14 | Two-week parallel shadow-mode run | Validate the bot against real production data with a real fallback still active. | M9 (Training)
Production Go-Live | Weeks 14–16 | Direct production cutover | Cut over once shadow-mode has already proven the bot clean. | M3 (Initiative Registry)
Exception Tuning | Weeks 16–18 | Real-volume exception review | Tune rules against real production volume, which always differs from the test sample. | M14 (Analytics)
CoE Handover | Weeks 18–19 | Genuine capacity-backed handover | Ensure ongoing monitoring ownership actually transfers, not just the paperwork. | M12 (Sustainment)
journi — Business Process Automation (Kenitra Invoice-Matching Automation)
36

## Slide 38
PART 4 — SIX EXCEPTIONS, IN DETAIL
Six Realistic Contingencies — None of Which Actually Occurred
journi — Business Process Automation (Kenitra Invoice-Matching Automation)
37

## Slide 39
C1 · BUILD, WEEKS 9–12
Hidden Exception Volume Underestimated
DESCRIPTION
The Phase 1 suitability assessment concludes the task is low-exception; internal testing then reveals a meaningfully higher real exception rate, because the historical sample under-represented a seasonal invoice pattern.
TRIGGER
Internal test exception rate exceeds the threshold set during architecture design.
TIMELINE IMPACT
Would delay the Build gate by one to two weeks, and push shadow-mode from two weeks to three.
RECOVERY TASKS
Redesign exception-handling rules for the newly discovered seasonal pattern before declaring Build complete.
OUTPUTS: An expanded exception-handling rule set; a validated seasonal-pattern test case. RACSI: R = PM, ITL · A = CM · C = FPO · S = ES · I = SUP, EU
journi — Business Process Automation (Kenitra Invoice-Matching Automation)
38

## Slide 40
C2 · UAT & SHADOW-MODE, WEEKS 12–14
Shadow-Mode Discrepancy Traced to a Data Quality Issue, Not the Bot
DESCRIPTION
A shadow-mode discrepancy initially looks like a bot logic error; investigation instead finds the discrepancy traces to inconsistent supplier-name formatting in the source system — a data-quality issue the bot correctly flagged.
TRIGGER
A shadow-mode discrepancy rate above the expected noise floor.
TIMELINE IMPACT
No phase-gate delay if resolved within shadow-mode's existing window.
RECOVERY TASKS
Investigate the discrepancy's true source before assuming bot error; correct the upstream data-quality issue.
OUTPUTS: A confirmed root cause; an unmodified, already-correct bot. RACSI: R = ITL · A = CM · C = FPO · S = PM · I = ES, SUP
journi — Business Process Automation (Kenitra Invoice-Matching Automation)
39

## Slide 41
C3 · ARCHITECTURE DESIGN–UAT, WEEKS 4–14
A Single Vocal Staff Member Resists Despite Overall Buy-In
DESCRIPTION
One of the 18 AP staff — often the person who has done the manual match longest — resists individually, even though the rest of the team and the Sponsor are genuinely supportive.
TRIGGER
A single resistance entry from one staff member, with no similar entries from the rest of the cohort.
TIMELINE IMPACT
None to the program timeline if handled directly and early.
RECOVERY TASKS
Address the individual concern directly and early, before it becomes a Phase 5 go-live morale issue.
OUTPUTS: A resolved individual concern; no broader team impact. RACSI: R = CM, FPO · A = CM · C = ES · S = SUP · I = PM, EU
journi — Business Process Automation (Kenitra Invoice-Matching Automation)
40

## Slide 42
C4 · BUILD, WEEKS 9–12
IT Change-Freeze Delays Integration
DESCRIPTION
Bouregreg Group's IT function declares a change freeze — commonly tied to a fiscal period close — that blocks the bot's integration work during Build.
TRIGGER
An IT-declared change freeze overlapping Build's planned integration window.
TIMELINE IMPACT
A direct delay equal to the freeze's duration, typically one to three weeks, pushed straight through to UAT and go-live.
RECOVERY TASKS
Plan integration work around known freeze windows where possible; escalate for an exception where the freeze cannot be avoided.
OUTPUTS: A revised integration schedule; a documented freeze-driven delay. RACSI: R = PM, ITL · A = PM · C = CM · S = ES · I = FPO, SUP, EU
journi — Business Process Automation (Kenitra Invoice-Matching Automation)
41

## Slide 43
C5 · BUILD, WEEKS 9–12
Platform Licensing or Technical Limitation Discovered Mid-Build
DESCRIPTION
The RPA platform's licensing terms or a technical limitation (a rate limit on the legacy system's API) is discovered mid-Build to constrain the bot's design in a way Architecture Design didn't anticipate.
TRIGGER
A platform constraint discovered during active development that the signed-off architecture didn't account for.
TIMELINE IMPACT
Reopens part of the Architecture Design gate, typically adding one to two weeks.
RECOVERY TASKS
Adjust the design within the newly discovered constraint rather than treat it as a blocking failure.
OUTPUTS: A revised architecture; a documented platform constraint for future automation projects. RACSI: R = ITL · A = PM · C = CM · S = FPO · I = ES, SUP, EU
journi — Business Process Automation (Kenitra Invoice-Matching Automation)
42

## Slide 44
C6 · COE HANDOVER, WEEKS 18–19
Post-Go-Live Complacency: CoE Ownership Never Really Transfers
DESCRIPTION
The Center of Excellence handover happens on paper — the package delivered, sign-off toggled — but day-to-day monitoring quietly stays with Yassine Kabbaj rather than genuinely transferring, because the CoE was never given real capacity for it.
TRIGGER
A sustainment checkpoint (M12) shows the named CoE owner has logged no monitoring activity since handover.
TIMELINE IMPACT
No impact to this program's own 19-week timeline, since it manifests after formal close.
RECOVERY TASKS
A post-handover checkpoint specifically verifying logged monitoring activity, not just a signed handover document.
OUTPUTS: A verified, capacity-backed CoE handover; an early catch of any silent non-transfer. RACSI: R = FPO · A = ES · C = PM, ITL · S = CM · I = SUP, EU
journi — Business Process Automation (Kenitra Invoice-Matching Automation)
43

## Slide 45
PART 5 — TRAINING PROGRAM
What This Training Covers
Per the E2E-BPA chain, MP-05 is present but light-touch — this archetype's training focuses on operating alongside the bot and handling its flagged exceptions, not persuasion for an already-bought-in team.
journi — Business Process Automation (Kenitra Invoice-Matching Automation)
44

## Slide 46
PART 5 · TIER 1 OF 3
Strategic Management
Cohort: Hakim Berrada (Sponsor) · Weeks 1–3
Curriculum Entry | Content Focus
Sponsoring a Low-Risk Automation Project | Why visible sponsorship still matters even when the team is already bought in.
Reading a Clean Program's Own Data | How to confirm a clean record honestly, without assuming it will simply continue.
journi — Business Process Automation (Kenitra Invoice-Matching Automation)
45

## Slide 47
PART 5 · TIER 2 OF 3
Operational Management
Cohort: Nawal Fassi (FPO/SUP), Amine Sqalli (PM) · Weeks 3–6
Curriculum Entry | Content Focus
Operating the Bot's Exception Queue | Handling the specific invoice-matching exceptions the bot flags rather than auto-resolves.
Shadow-Mode Validation Procedure | How to compare bot output against the manual process during the two-week parallel run.
journi — Business Process Automation (Kenitra Invoice-Matching Automation)
46

## Slide 48
PART 5 · TIER 3 OF 3
Operations (Frontline)
Cohort: All 18 Kenitra AP staff · Weeks 5–13
Curriculum Entry | Content Focus
Working Alongside the Automated Match | What changes and what stays the same in daily AP work once the bot is live.
Escalating a Flagged Exception | The specific steps for routing a bot-flagged invoice back to a human reviewer.
journi — Business Process Automation (Kenitra Invoice-Matching Automation)
47

## Slide 49
PART 5 — TRAINING PROGRAM
Why This Curriculum Is Shaped This Way
This program's training curriculum is deliberately the lightest in the series — proof that not every automation needs an elaborate change program when the scope is narrow and the team is already on board.
journi — Business Process Automation (Kenitra Invoice-Matching Automation)
48

## Slide 50
CROSS-REFERENCE
Which journi Modules Dominate This Archetype
M17 (WBS & Gantt)
The shortest phase template in the library — closed in as few as 18–19 weeks.
M5 (ADKAR Engine)
A light-touch score, since the team starts already bought in.
M7 (Sponsor & Coalition)
A visibly active Sponsor from day one — the opposite pattern of the Cultural case.
M21 (Field Notes)
Routine logging — this archetype's data is notable for how little it needs to escalate.
M14 (Analytics)
Confirms a rising, unremarkable CRI trend rather than tracking a recovery.
M12 (Sustainment)
The CoE handover checkpoint — the one place this clean program still needs real verification.
journi — Business Process Automation (Kenitra Invoice-Matching Automation)
49

## Slide 51
ALERTS & PROOF
What This Case Proves By Not Firing
NO LIVE ALERT FIRES IN THIS PROGRAM'S REAL RECORD
Stated plainly, not manufactured — a clean record reported as a clean record.
WHY
None. Closed by design without any of journi's 9 live alerts firing — the clean-close contrast case that proves not every program needs a recovery playbook.
journi — Business Process Automation (Kenitra Invoice-Matching Automation)
50

## Slide 52
KEY TAKEAWAYS
What to Remember About This Archetype
› A closed program with zero of journi's 9 live alerts fired, a real two-week shadow-mode validation before go-live, and six honestly-labeled hypothetical contingencies showing exactly how this program could have gone differently, had the conditions been less favorable.
› All four frameworks read favorably from the start, by design. This is journi's deliberate contrast case: a narrow scope, an already-bought-in team, and a visibly active Sponsor mean no framework carries unusual risk — the point being that not every program needs a recovery playbook.
› None. Closed by design without any of journi's 9 live alerts firing — the clean-close contrast case that proves not every program needs a recovery playbook.
journi — Business Process Automation (Kenitra Invoice-Matching Automation)
51

## Slide 53
Business Process Automation
Kenitra Invoice-Matching Automation
Manufacturing Sector · Bouregreg Group Scenario Library · Confidential