## Slide 1
Integrated Management System
ISO 9001/14001 Integrated Management System
Pursuing ISO 9001/14001 certification on one management system rather than two — sponsored alone, without a guiding coalition.
7
PHASES
60
WEEKS
6
EXCEPTIONS
3
TRAINING TIERS
Manufacturing Sector · Bouregreg Group Scenario Library · Confidential

## Slide 2
PART 0 — PURPOSE
What This Guide Is, and How to Use It
WHAT THIS GUIDE IS
This deck follows the ISO 9001/14001 Integrated Management System program — journi's QMS archetype case — from tenant setup through ongoing surveillance, the guide in this series with the longest single-phase tail, since certification surveillance never formally closes.
HOW TO USE IT
This program runs inside the same Bouregreg Group tenant as every other archetype in this series. A reader with the tenant already set up skips straight to CM Project creation.
journi — Integrated Management System (ISO 9001/14001 Integrated Management System)
01

## Slide 3
PART 0 — A NOTE ON FIDELITY
Verified Against journi's Real Source
Every journi module, field, and role named here is verified against journi's real source. This is journi's own stated case for ALT-010 (Guiding Coalition Gap) — this deck shows exactly how a single-Sponsor structural gap fires the alert and is resolved through genuine coalition-building, not a wider distribution list.
RACSI CODES USED THROUGHOUT
ES = Executive Sponsor · CM = Change Manager · PM = Program/Project Manager · FPO = Functional Process Owner · ITL = IT/Technical Lead · SUP = Supervisor · EU = End User
journi — Integrated Management System (ISO 9001/14001 Integrated Management System)
02

## Slide 4
PART 1 — EXECUTIVE SUMMARY
Why This Case Matters
A Quality Manager sponsoring a certification program alone, without a broader guiding coalition, is a realistic single-sponsor failure mode journi is specifically built to catch — the Sponsor & Coalition record, not any single ADKAR score, is this archetype's central risk signal.
journi — Integrated Management System (ISO 9001/14001 Integrated Management System)
03

## Slide 5
PART 1 — EXECUTIVE SUMMARY
The Case, in Brief
410 staff, Settat plant operations + quality
60 weeks (guide numbering)
Settat plant pursues integrated ISO 9001 (quality) and ISO 14001 (environmental) certification on one management system rather than two, driven by a customer contract now requiring certified quality management, across 410 staff over 60 weeks.
journi — Integrated Management System (ISO 9001/14001 Integrated Management System)
04

## Slide 6
PART 1 — EXECUTIVE SUMMARY
What This Guide Proves, Concretely
A real ALT-010 firing at Week 26–31, resolved by recruiting a genuine Procurement Director and HR Business Partner as coalition members — plus five further exceptions showing exactly how a certification program can drift even after the headline coalition gap is closed.
journi — Integrated Management System (ISO 9001/14001 Integrated Management System)
05

## Slide 7
PART 2 — THE FOUR FRAMEWORKS
Weighting for This Archetype
Lewin never fully closes. Ongoing Surveillance is the longest single-phase tail in the library by design — certification surveillance never formally ends, so Refreeze is the one Lewin stage this archetype treats as a standing state, not a destination, unlike every other case in this series.
journi — Integrated Management System (ISO 9001/14001 Integrated Management System)
06

## Slide 8
PART 2 — THE FOUR FRAMEWORKS
The Composite Readiness Index, Read for This Case
The Composite Readiness Index climbs steadily through Design and Implementation, dips briefly around the coalition-gap discovery, then recovers once the coalition is genuinely rebuilt — Benchmarking reads "Behind" only in that narrow window, "In Line" everywhere else.
journi — Integrated Management System (ISO 9001/14001 Integrated Management System)
07

## Slide 9
PART 3 — TENANT AND ADMIN SETUP
The Existing Tenant, and Reading Paths by Role
THE EXISTING TENANT
This program runs inside the same tenant journi's Master User Guide builds, under the existing Bouregreg Manufacturing Maroc Organization — no new Organization needed.
READING PATHS, BY ROLE
› A Change Manager running this program day to day: Part 2 once, then Part 4 in full.
› A Program/Project Manager: Part 4's PM Track column and the Master WBS & Gantt.
› An Executive Sponsor: Part 1, then Part 4's phase-opening narratives.
› A Super Admin or Org Admin: Part 3.
journi — Integrated Management System (ISO 9001/14001 Integrated Management System)
08

## Slide 10
PART 3 — TENANT AND ADMIN SETUP
The RACSI Team for This Program
Name | RACSI Code | Role
Nadia Fassi | ES | Sponsor — Quality Manager
Rania Bensouda | CM | Change Manager
Samir Chraibi | PM | Program Manager
Mehdi Ouahbi | FPO | Functional Process Owner
Yasmine Kadiri | ITL | IT/Technical Lead
Aziz Berrada | SUP | Supervisor
journi — Integrated Management System (ISO 9001/14001 Integrated Management System)
09

## Slide 11
PART 3 — TENANT AND ADMIN SETUP
Creating the CM Project
1
On Module 1 — Hierarchy, create the ISO 9001/14001 Integrated Management System CM Project under the existing Bouregreg Manufacturing Maroc Organization.
2
Set Change type: Integrated Management System. Target population: "Settat plant operations and quality, 410 staff." Business driver: "A customer contract now requires certified quality management; a parallel environmental certification is bundled in for efficiency."
3
Save. Lewin opens at Unfreeze, started alongside the ERP program's own kickoff.
4
On Module 17 — WBS & Gantt, load the TPL-IMS-7 phase template: Intake & Diagnosis, Design, Implementation, Mock-up Audit, Certifying Audit, Surveillance Prep, Ongoing Surveillance.
journi — Integrated Management System (ISO 9001/14001 Integrated Management System)
10

## Slide 12
PART 3 — TENANT AND ADMIN SETUP
Charters for This Program
Charter | Accountable | Review Cadence
CHTR-01 Sponsorship / Leadership Charter | Nadia Fassi (ES) | Per Phase Gate
CHTR-04 Organizational Impact Charter | Rania Bensouda (CM) | On scope change
CHTR-08 Pulse / Interview Charter | Rania Bensouda (CM) | Per phase gate + ad hoc
journi — Integrated Management System (ISO 9001/14001 Integrated Management System)
11

## Slide 13
PART 3 — TENANT AND ADMIN SETUP
Setup Checklist
Base tenant confirmed (Bouregreg Group, existing Organization)
QMS program team accounts created
CM Project created, Lewin opened at Unfreeze
TPL-IMS-7 phase template loaded on M17
Applicable Charters reviewed and accountable owners confirmed
journi — Integrated Management System (ISO 9001/14001 Integrated Management System)
12

## Slide 14
PART 4 — WEEK-BY-WEEK TIMELINE
7 Phases, In Order
1. Intake & Diagnosis
2. Design
3. Implementation
4. Mock-up Audit
5. Certifying Audit
6. Surveillance Prep
7. Ongoing Surveillance
Total program length: 60 weeks (guide numbering). Every phase below is walked in detail across the next slides — normal flow first, then six exceptions in full operational detail.
journi — Integrated Management System (ISO 9001/14001 Integrated Management System)
13

## Slide 15
PHASE 1 OF 7
Intake & Diagnosis
Weeks 1–12
NARRATIVE
Establishes the gap between current practice and both ISO 9001 and ISO 14001 requirements, started alongside the ERP program's own kickoff.
journi — Integrated Management System (ISO 9001/14001 Integrated Management System)
14

## Slide 16
PHASE 1 · INTAKE & DIAGNOSIS
Key Moments in This Phase
Week | What Happens
Week 1 | Kickoff; Lewin opens at Unfreeze.
Week 8 | Gap analysis against both standards, run as one integrated exercise.
Week 12 | Diagnosis gate closes.
journi — Integrated Management System (ISO 9001/14001 Integrated Management System)
15

## Slide 17
PHASE 1 · INTAKE & DIAGNOSIS
Framework Snapshot
LEWIN
Unfreeze
ADKAR
Awareness
BRIDGES
Ending
KÜBLER-ROSS
Denial
KEY TECHNIQUE THIS PHASE
Dual-standard integrated gap analysis: Assess ISO 9001 and ISO 14001 as one exercise, not two parallel ones.
journi — Integrated Management System (ISO 9001/14001 Integrated Management System)
16

## Slide 18
PHASE 2 OF 7
Design
Weeks 10–26
NARRATIVE
Designs the integrated procedure set covering both quality and environmental requirements — where Exception E5's standards conflict surfaces.
journi — Integrated Management System (ISO 9001/14001 Integrated Management System)
17

## Slide 19
PHASE 2 · DESIGN
Key Moments in This Phase
Week | What Happens
Week 18 | An ISO 14001 waste-handling requirement conflicts with existing operations practice — Exception E5 opens.
Week 26 | Design gate closes; five weeks into Implementation the coalition gap is discovered.
journi — Integrated Management System (ISO 9001/14001 Integrated Management System)
18

## Slide 20
PHASE 2 · DESIGN
Framework Snapshot
LEWIN
Unfreeze
ADKAR
Awareness → Knowledge
BRIDGES
Ending → Neutral Zone
KÜBLER-ROSS
Denial → Resistance/Anger
KEY TECHNIQUE THIS PHASE
Integrated procedure-set design: Design one procedure set covering both quality and environmental requirements.
journi — Integrated Management System (ISO 9001/14001 Integrated Management System)
19

## Slide 21
PHASE 3 OF 7
Implementation
Weeks 24–38
NARRATIVE
Implements the designed procedures plant-wide — the phase where Nadia Fassi's solo sponsorship becomes visible as a structural gap.
journi — Integrated Management System (ISO 9001/14001 Integrated Management System)
20

## Slide 22
PHASE 3 · IMPLEMENTATION
Key Moments in This Phase
Week | What Happens
Week 26 | Sponsor & Coalition record still shows zero named members — Exception E1 opens, firing ALT-010.
Week 31 | A Procurement Director and HR Business Partner recruited as genuine coalition members.
Week 38 | Implementation gate closes.
journi — Integrated Management System (ISO 9001/14001 Integrated Management System)
21

## Slide 23
PHASE 3 · IMPLEMENTATION
Framework Snapshot
LEWIN
Change
ADKAR
Knowledge → Ability
BRIDGES
Neutral Zone
KÜBLER-ROSS
Resistance/Anger
KEY TECHNIQUE THIS PHASE
Genuine coalition recruitment: Move beyond solo sponsorship to a real guiding coalition with named, active members.
journi — Integrated Management System (ISO 9001/14001 Integrated Management System)
22

## Slide 24
PHASE 4 OF 7
Mock-up Audit
Weeks 36–46
NARRATIVE
Runs an internal mock-up audit before the real certifying body ever sees the system — where a systemic documentation gap can still be caught.
journi — Integrated Management System (ISO 9001/14001 Integrated Management System)
23

## Slide 25
PHASE 4 · MOCK-UP AUDIT
Key Moments in This Phase
Week | What Happens
Week 40 | Mock-up audit finds a systemic documentation gap in ISO 14001's waste-handling clause — Exception E2 opens.
Week 43 | Documentation gap closed across the environmental half of the system.
Week 46 | Mock-up audit gate closes clean.
journi — Integrated Management System (ISO 9001/14001 Integrated Management System)
24

## Slide 26
PHASE 4 · MOCK-UP AUDIT
Framework Snapshot
LEWIN
Change
ADKAR
Ability
BRIDGES
Neutral Zone
KÜBLER-ROSS
Exploration
KEY TECHNIQUE THIS PHASE
Internal mock-up audit: Catch systemic documentation gaps before the real certifying body does.
journi — Integrated Management System (ISO 9001/14001 Integrated Management System)
25

## Slide 27
PHASE 5 OF 7
Certifying Audit
Weeks 44–50
NARRATIVE
The real, external certifying audit — the moment this program's preparation is actually tested.
journi — Integrated Management System (ISO 9001/14001 Integrated Management System)
26

## Slide 28
PHASE 5 · CERTIFYING AUDIT
Key Moments in This Phase
Week | What Happens
Week 47 | The certifying body's auditor flags a minor nonconformity — Exception E3 opens.
Week 49 | Nonconformity corrected and closed with the auditor.
Week 50 | Certification passes clean.
journi — Integrated Management System (ISO 9001/14001 Integrated Management System)
27

## Slide 29
PHASE 5 · CERTIFYING AUDIT
Framework Snapshot
LEWIN
Change
ADKAR
Ability
BRIDGES
Neutral Zone
KÜBLER-ROSS
Exploration
KEY TECHNIQUE THIS PHASE
External certifying audit: Confirm certification against the certifying body's own independent standard.
journi — Integrated Management System (ISO 9001/14001 Integrated Management System)
28

## Slide 30
PHASE 6 OF 7
Surveillance Prep
Weeks 48–52
NARRATIVE
Prepares the standing surveillance rhythm that will run indefinitely past this program's own formal close.
journi — Integrated Management System (ISO 9001/14001 Integrated Management System)
29

## Slide 31
PHASE 6 · SURVEILLANCE PREP
Key Moments in This Phase
Week | What Happens
Week 50 | Surveillance schedule and spot-check cadence confirmed.
Week 52 | Surveillance prep gate closes.
journi — Integrated Management System (ISO 9001/14001 Integrated Management System)
30

## Slide 32
PHASE 6 · SURVEILLANCE PREP
Framework Snapshot
LEWIN
Change → Refreeze
ADKAR
Ability → Reinforcement
BRIDGES
New Beginning
KÜBLER-ROSS
Commitment
KEY TECHNIQUE THIS PHASE
Standing surveillance-rhythm design: Design a spot-check cadence that will run indefinitely without a dedicated program team.
journi — Integrated Management System (ISO 9001/14001 Integrated Management System)
31

## Slide 33
PHASE 7 OF 7
Ongoing Surveillance
Weeks 52 onward, open-ended
NARRATIVE
The longest single-phase tail in the library — certification surveillance never formally closes, by design.
journi — Integrated Management System (ISO 9001/14001 Integrated Management System)
32

## Slide 34
PHASE 7 · ONGOING SURVEILLANCE
Key Moments in This Phase
Week | What Happens
Week 56 | A function quietly reverts to a pre-certification shortcut once audit pressure passes — Exception E4 opens.
Week 58+ | The recruited HR Business Partner departs, risking a quiet reversion to the original coalition gap — Exception E6 opens.
journi — Integrated Management System (ISO 9001/14001 Integrated Management System)
33

## Slide 35
PHASE 7 · ONGOING SURVEILLANCE
Framework Snapshot
LEWIN
Refreeze (standing)
ADKAR
Reinforcement
BRIDGES
New Beginning
KÜBLER-ROSS
Commitment
KEY TECHNIQUE THIS PHASE
Surveillance spot-checks: Catch "audit theater" reversion before it becomes the new normal.
journi — Integrated Management System (ISO 9001/14001 Integrated Management System)
34

## Slide 36
PART 4 — MASTER WBS & GANTT
Every Phase, Across the Four Frameworks
Phase | Week(s) | Lewin | ADKAR | Bridges | Kübler-Ross
Intake & Diagnosis | Weeks 1–12 | Unfreeze | Awareness | Ending | Denial
Design | Weeks 10–26 | Unfreeze | Awareness → Knowledge | Ending → Neutral Zone | Denial → Resistance/Anger
Implementation | Weeks 24–38 | Change | Knowledge → Ability | Neutral Zone | Resistance/Anger
Mock-up Audit | Weeks 36–46 | Change | Ability | Neutral Zone | Exploration
Certifying Audit | Weeks 44–50 | Change | Ability | Neutral Zone | Exploration
Surveillance Prep | Weeks 48–52 | Change → Refreeze | Ability → Reinforcement | New Beginning | Commitment
Ongoing Surveillance | Weeks 52+ | Refreeze (standing) | Reinforcement | New Beginning | Commitment
journi — Integrated Management System (ISO 9001/14001 Integrated Management System)
35

## Slide 37
PART 4 — MASTER WBS & GANTT
Every Phase, Techniques and Tools
Phase | Week(s) | Technique | Goal | Tool
Intake & Diagnosis | Weeks 1–12 | Dual-standard integrated gap analysis | Assess ISO 9001 and ISO 14001 as one exercise, not two parallel ones. | M4 (Stakeholder Mapping)
Design | Weeks 10–26 | Integrated procedure-set design | Design one procedure set covering both quality and environmental requirements. | M17 (WBS & Gantt)
Implementation | Weeks 24–38 | Genuine coalition recruitment | Move beyond solo sponsorship to a real guiding coalition with named, active members. | M7 (Sponsor & Coalition)
Mock-up Audit | Weeks 36–46 | Internal mock-up audit | Catch systemic documentation gaps before the real certifying body does. | M21 (Field Notes)
Certifying Audit | Weeks 44–50 | External certifying audit | Confirm certification against the certifying body's own independent standard. | M17 (WBS & Gantt)
Surveillance Prep | Weeks 48–52 | Standing surveillance-rhythm design | Design a spot-check cadence that will run indefinitely without a dedicated program team. | M12 (Sustainment)
Ongoing Surveillance | Weeks 52+ | Surveillance spot-checks | Catch "audit theater" reversion before it becomes the new normal. | M12 (Sustainment)
journi — Integrated Management System (ISO 9001/14001 Integrated Management System)
36

## Slide 38
PART 4 — SIX EXCEPTIONS, IN DETAIL
Six Realistic Ways This Program Could Have Gone Differently
journi — Integrated Management System (ISO 9001/14001 Integrated Management System)
37

## Slide 39
E1 · IMPLEMENTATION, WEEKS 28–31
Guiding Coalition Gap
DESCRIPTION
Five weeks into Implementation, Nadia Fassi's Sponsor & Coalition record still showed zero named coalition members, and procurement/HR rollout had stalled outside her direct authority — ALT-010's exact condition.
TRIGGER
The Sponsor & Coalition record on M7 names fewer than 2 coalition members.
TIMELINE IMPACT
No formal gate delay, but procurement/HR rollout stalls until the coalition is rebuilt.
RECOVERY TASKS
Recruit a genuine Procurement Director and HR Business Partner as coalition members, not just a wider distribution list.
OUTPUTS: A rebuilt Sponsor & Coalition record with two genuine, active members. RACSI: R = CM, ES · A = ES · C = PM · S = FPO · I = SUP, EU
journi — Integrated Management System (ISO 9001/14001 Integrated Management System)
38

## Slide 40
E2 · MOCK-UP AUDIT, WEEKS 40–43
Mock-up Audit Finds a Systemic Documentation Gap
DESCRIPTION
The mock-up audit finds that Design's procedure set never fully addressed ISO 14001's waste-handling documentation clause — a systemic gap across the whole environmental half of the integrated system.
TRIGGER
An internal mock-up audit finding spanning multiple procedures, not a single missed document.
TIMELINE IMPACT
Extends Mock-up Audit by two to three weeks while the environmental documentation set is rebuilt.
RECOVERY TASKS
Rebuild the waste-handling documentation set specifically, cross-checked against ISO 14001's actual clause text.
OUTPUTS: A corrected, complete environmental documentation set. RACSI: R = FPO, ITL · A = CM · C = PM · S = SUP · I = ES, EU
journi — Integrated Management System (ISO 9001/14001 Integrated Management System)
39

## Slide 41
E3 · CERTIFYING AUDIT, WEEK 47
External Auditor Flags a Nonconformity During Certification
DESCRIPTION
The certifying body's own auditor, independent of the mock-up audit, flags a minor nonconformity during the real certifying audit — a procedure followed correctly on paper but not consistently in observed plant-floor practice.
TRIGGER
An independent certifying-body finding during the real audit.
TIMELINE IMPACT
A short correction window before the audit's own close-out, typically days not weeks.
RECOVERY TASKS
Correct the specific practice gap and demonstrate the correction to the auditor before close-out.
OUTPUTS: A closed nonconformity; certification passes clean. RACSI: R = FPO, SUP · A = CM · C = ES · S = PM · I = ITL, EU
journi — Integrated Management System (ISO 9001/14001 Integrated Management System)
40

## Slide 42
E4 · ONGOING SURVEILLANCE, WEEKS 54–58
A Function Reverts to Old Practice Once the Auditor Leaves
DESCRIPTION
A surveillance spot-check finds that one function has quietly reverted to a pre-certification shortcut once audit pressure passed — the classic "audit theater" risk every certification program has to guard against.
TRIGGER
A surveillance spot-check finding a reverted practice.
TIMELINE IMPACT
No formal gate — this phase runs open-ended — but requires an immediate corrective conversation.
RECOVERY TASKS
Address the reversion directly with the function; reinforce why the practice matters beyond audit optics.
OUTPUTS: A corrected practice; a reinforced surveillance spot-check cadence. RACSI: R = FPO, SUP · A = CM · C = ES · S = PM · I = ITL, EU
journi — Integrated Management System (ISO 9001/14001 Integrated Management System)
41

## Slide 43
E5 · DESIGN–IMPLEMENTATION, WEEKS 18–26
Environmental Requirements Conflict With an Existing Operations Practice
DESCRIPTION
A specific ISO 14001 waste-handling requirement conflicts directly with an existing, longstanding operations practice that was never a problem for ISO 9001 alone — the specific complication a genuinely integrated certification introduces.
TRIGGER
A direct conflict identified during Design between the two standards' requirements.
TIMELINE IMPACT
Adds one to two weeks to Design while the conflict is resolved before Implementation begins.
RECOVERY TASKS
Resolve the conflict explicitly, documenting why the resolution satisfies both standards rather than favoring one.
OUTPUTS: A documented, dual-compliant resolution. RACSI: R = FPO, SUP · A = CM · C = ITL · S = PM · I = ES, EU
journi — Integrated Management System (ISO 9001/14001 Integrated Management System)
42

## Slide 44
E6 · ONGOING SURVEILLANCE, WEEKS 56+
A Coalition Member Departs During Surveillance
DESCRIPTION
The HR Business Partner recruited as a coalition member during Exception E1's recovery leaves the organization during Ongoing Surveillance, risking a quiet reversion to the exact structural gap the program worked to close.
TRIGGER
A confirmed departure of a named coalition member during Ongoing Surveillance.
TIMELINE IMPACT
No formal delay, but requires prompt coalition-seat succession.
RECOVERY TASKS
Identify and onboard a successor coalition member promptly, rather than let the coalition quietly shrink back toward solo sponsorship.
OUTPUTS: A maintained, genuine coalition membership. RACSI: R = CM, ES · A = ES · C = FPO · S = PM · I = SUP, ITL, EU
journi — Integrated Management System (ISO 9001/14001 Integrated Management System)
43

## Slide 45
PART 5 — TRAINING PROGRAM
What This Training Covers
Per the E2E-IMS chain, MP-05 is present — training here covers both ISO 9001 and ISO 14001 procedures as one integrated curriculum, not two separate tracks.
journi — Integrated Management System (ISO 9001/14001 Integrated Management System)
44

## Slide 46
PART 5 · TIER 1 OF 3
Strategic Management
Cohort: Nadia Fassi (Sponsor), plant leadership · Weeks 1–10
Curriculum Entry | Content Focus
Sponsoring a Certification Program | Why solo sponsorship is a structural risk journi is specifically built to catch.
Reading a Guiding Coalition Gap | How to read fewer than 2 coalition members as a real, actionable signal.
journi — Integrated Management System (ISO 9001/14001 Integrated Management System)
45

## Slide 47
PART 5 · TIER 2 OF 3
Operational Management
Cohort: Mehdi Ouahbi (FPO), Aziz Berrada (SUP) · Weeks 10–36
Curriculum Entry | Content Focus
Operating the Integrated Procedure Set | Quality and environmental procedures as one system, not two.
Preparing for a Mock-up and Certifying Audit | What auditors actually check, and how to have evidence ready.
journi — Integrated Management System (ISO 9001/14001 Integrated Management System)
46

## Slide 48
PART 5 · TIER 3 OF 3
Operations (Frontline)
Cohort: All 410 Settat plant operations and quality staff · Weeks 20–46
Curriculum Entry | Content Focus
Following the New Integrated Procedures | Day-to-day quality and environmental practice under the new certified system.
Sustaining Practice Beyond the Audit Window | Specifically addressing the "audit theater" risk Exception E4 shows happening.
journi — Integrated Management System (ISO 9001/14001 Integrated Management System)
47

## Slide 49
PART 5 — TRAINING PROGRAM
Why This Curriculum Is Shaped This Way
Training completion here is necessary but not the finish line — Ongoing Surveillance's indefinite spot-check cadence is what actually verifies the certified practice holds, long after the certifying audit itself passes.
journi — Integrated Management System (ISO 9001/14001 Integrated Management System)
48

## Slide 50
CROSS-REFERENCE
Which journi Modules Dominate This Archetype
M7 (Sponsor & Coalition)
The archetype's central risk — fewer than 2 coalition members fires ALT-010.
M17 (WBS & Gantt)
The TPL-IMS-7 template — Mock-up and Certifying Audit are external-facing gates.
M12 (Sustainment)
Ongoing Surveillance checkpoints, run indefinitely past program close.
M19 (Charter Registry)
Formal charters carry unusual weight given the external audit stakes.
M21 (Field Notes)
Documentation-gap and nonconformity findings, logged with their corrections.
M4 (Stakeholder Mapping)
Both quality and environmental impact dimensions tracked in one integrated map.
journi — Integrated Management System (ISO 9001/14001 Integrated Management System)
49

## Slide 51
ALERTS & PROOF
What This Case Fires
ALERTS THIS CASE EXERCISES
ALT-010 (Guiding Coalition Gap)
WHY
Built specifically because a Quality Manager sponsoring alone, without a broader coalition, is a realistic single-sponsor failure mode.
journi — Integrated Management System (ISO 9001/14001 Integrated Management System)
50

## Slide 52
KEY TAKEAWAYS
What to Remember About This Archetype
› A real ALT-010 firing at Week 26–31, resolved by recruiting a genuine Procurement Director and HR Business Partner as coalition members — plus five further exceptions showing exactly how a certification program can drift even after the headline coalition gap is closed.
› Lewin never fully closes. Ongoing Surveillance is the longest single-phase tail in the library by design — certification surveillance never formally ends, so Refreeze is the one Lewin stage this archetype treats as a standing state, not a destination, unlike every other case in this series.
› Built specifically because a Quality Manager sponsoring alone, without a broader coalition, is a realistic single-sponsor failure mode.
journi — Integrated Management System (ISO 9001/14001 Integrated Management System)
51

## Slide 53
Integrated Management System
ISO 9001/14001 Integrated Management System
Manufacturing Sector · Bouregreg Group Scenario Library · Confidential