## Slide 1
Operating Model Redesign
Regional Operating Model Redesign
Realigning reporting lines from site-based to function-based — where the real risk is reversion under pressure, not initial adoption.
7
PHASES
34
WEEKS
6
EXCEPTIONS
3
TRAINING TIERS
Manufacturing Sector · Bouregreg Group Scenario Library · Confidential

## Slide 2
PART 0 — PURPOSE
What This Guide Is, and How to Use It
WHAT THIS GUIDE IS
This deck follows the Regional Operating Model Redesign — journi's Operating Model archetype case — from tenant setup through standing rhythm handover, realigning reporting lines from site-based to function-based across Bouregreg Group's three sites.
HOW TO USE IT
This program runs inside the same Bouregreg Group tenant as every other archetype in this series, once the ERP program's own Build phase exposes the site-based structure's duplication. A reader with the tenant already set up skips straight to CM Project creation.
journi — Operating Model Redesign (Regional Operating Model Redesign)
01

## Slide 3
PART 0 — A NOTE ON FIDELITY
Verified Against journi's Real Source
Every journi module, field, and role named here is verified against journi's real source. This is journi's own stated case for ALT-002 (Regression Risk Score Critical) and ALT-015 (Sustainment Sign-Off Blocked) — this deck shows exactly how a real regression is caught, not glossed over.
RACSI CODES USED THROUGHOUT
ES = Executive Sponsor · CM = Change Manager · PM = Program/Project Manager · FPO = Functional Process Owner · ITL = IT/Technical Lead · SUP = Supervisor · EU = End User
journi — Operating Model Redesign (Regional Operating Model Redesign)
02

## Slide 4
PART 1 — EXECUTIVE SUMMARY
Why This Case Matters
Function Heads can pass every earlier checkpoint and still revert to old decision-making under real operational pressure — this archetype is built specifically to prove that reversion under pressure, not initial adoption, is the real test of an operating-model redesign.
journi — Operating Model Redesign (Regional Operating Model Redesign)
03

## Slide 5
PART 1 — EXECUTIVE SUMMARY
The Case, in Brief
95 staff, people managers across 3 sites
34 weeks (guide numbering)
Bouregreg Group realigns reporting lines across all three sites from site-based to function-based — Finance, Operations, and Quality each reporting centrally rather than to a site director — once the ERP program exposes how much duplicated decision-making the site-based structure was causing.
journi — Operating Model Redesign (Regional Operating Model Redesign)
04

## Slide 6
PART 1 — EXECUTIVE SUMMARY
What This Guide Proves, Concretely
A real 30-day sustainment checkpoint landing High regression risk, and a training-completion record (100% by Week 25) that proves Reinforcement, not Knowledge, was the actual gap — not glossed over as a clean success.
journi — Operating Model Redesign (Regional Operating Model Redesign)
05

## Slide 7
PART 2 — THE FOUR FRAMEWORKS
Weighting for This Archetype
ADKAR Reinforcement dominates. Function Heads can pass every earlier checkpoint and still revert to old decision-making under real operational pressure — this archetype is built specifically to show that failure mode, not initial adoption, is the real test.
journi — Operating Model Redesign (Regional Operating Model Redesign)
06

## Slide 8
PART 2 — THE FOUR FRAMEWORKS
The Composite Readiness Index, Read for This Case
The Composite Readiness Index reads strong through Pilot Transition, then drops sharply at the 30-day post-Full-Transition checkpoint — a real, not gradual, regression, which is exactly the kind of signal a checkpoint exists to catch rather than a slow drift a trend line would eventually show anyway.
journi — Operating Model Redesign (Regional Operating Model Redesign)
07

## Slide 9
PART 3 — TENANT AND ADMIN SETUP
The Existing Tenant, and Reading Paths by Role
THE EXISTING TENANT
This program runs inside the same tenant journi's Master User Guide builds, under the existing Bouregreg Manufacturing Maroc Organization — no new Organization needed.
READING PATHS, BY ROLE
› A Change Manager running this program day to day: Part 2 once, then Part 4 in full.
› A Program/Project Manager: Part 4's PM Track column and the Master WBS & Gantt.
› An Executive Sponsor: Part 1, then Part 4's phase-opening narratives.
› A Super Admin or Org Admin: Part 3.
journi — Operating Model Redesign (Regional Operating Model Redesign)
08

## Slide 10
PART 3 — TENANT AND ADMIN SETUP
The RACSI Team for This Program
Name | RACSI Code | Role
Yassine Berrada | ES | Sponsor — COO
Salma Idrissi | CM | Change Manager
Rachid Alaoui | PM | Program Manager
Amina Sqalli | FPO | Finance Function Head
Nabil Ouazzani | ITL | IT/Technical Lead
Loubna Tazi | SUP | Casablanca pilot site
journi — Operating Model Redesign (Regional Operating Model Redesign)
09

## Slide 11
PART 3 — TENANT AND ADMIN SETUP
Creating the CM Project
1
On Module 1 — Hierarchy, create the Regional Operating Model Redesign CM Project under the existing Bouregreg Manufacturing Maroc Organization.
2
Set Change type: Operating Model Redesign. Target population: "All people-manager-level staff across three sites, 95 staff." Business driver: "The ERP program exposed how much duplicated decision-making the site-based structure was causing."
3
Save. Lewin opens at Unfreeze, once the ERP program's own Build phase has exposed the duplication.
4
On Module 17 — WBS & Gantt, load the TPL-OM-7 phase template: Current Operating Model Assessment, TOM Design, Detailed Org Design, Pilot Transition, Full Transition, Governance Adoption Tracking, Standing Rhythm Handover.
journi — Operating Model Redesign (Regional Operating Model Redesign)
10

## Slide 12
PART 3 — TENANT AND ADMIN SETUP
Charters for This Program
Charter | Accountable | Review Cadence
CHTR-01 Sponsorship / Leadership Charter | Yassine Berrada (ES) | Per Phase Gate
CHTR-04 Organizational Impact Charter | Salma Idrissi (CM) | On scope change
CHTR-08 Pulse / Interview Charter | Salma Idrissi (CM) | Per phase gate + ad hoc
journi — Operating Model Redesign (Regional Operating Model Redesign)
11

## Slide 13
PART 3 — TENANT AND ADMIN SETUP
Setup Checklist
Base tenant confirmed (Bouregreg Group, existing Organization)
Operating Model program team accounts created across all three sites
CM Project created, Lewin opened at Unfreeze
TPL-OM-7 phase template loaded on M17
Applicable Charters reviewed and accountable owners confirmed
journi — Operating Model Redesign (Regional Operating Model Redesign)
12

## Slide 14
PART 4 — WEEK-BY-WEEK TIMELINE
7 Phases, In Order
1. Current Operating Model Assessment
2. TOM Design
3. Detailed Org Design
4. Pilot Transition
5. Full Transition
6. Governance Adoption Tracking
7. Standing Rhythm Handover
Total program length: 34 weeks (guide numbering). Every phase below is walked in detail across the next slides — normal flow first, then six exceptions in full operational detail.
journi — Operating Model Redesign (Regional Operating Model Redesign)
13

## Slide 15
PHASE 1 OF 7
Current Operating Model Assessment
Weeks 1–8
NARRATIVE
Assesses exactly how much duplicated decision-making the site-based structure causes, once the ERP program's Build phase makes it visible.
journi — Operating Model Redesign (Regional Operating Model Redesign)
14

## Slide 16
PHASE 1 · CURRENT OPERATING MODEL ASSESSMENT
Key Moments in This Phase
Week | What Happens
Week 1 | Kickoff; Lewin opens at Unfreeze.
Week 5 | Decision-duplication mapped across all three sites.
Week 8 | Assessment gate closes.
journi — Operating Model Redesign (Regional Operating Model Redesign)
15

## Slide 17
PHASE 1 · CURRENT OPERATING MODEL ASSESSMENT
Framework Snapshot
LEWIN
Unfreeze
ADKAR
Awareness
BRIDGES
Ending
KÜBLER-ROSS
Denial
KEY TECHNIQUE THIS PHASE
Decision-duplication mapping: Make the site-based structure's duplicated decision-making visible and countable.
journi — Operating Model Redesign (Regional Operating Model Redesign)
16

## Slide 18
PHASE 2 OF 7
TOM Design
Weeks 6–14
NARRATIVE
Designs the target function-based operating model — Finance, Operations, and Quality reporting centrally.
journi — Operating Model Redesign (Regional Operating Model Redesign)
17

## Slide 19
PHASE 2 · TOM DESIGN
Key Moments in This Phase
Week | What Happens
Week 10 | Target operating model drafted against the assessment findings.
Week 14 | TOM design signed off.
journi — Operating Model Redesign (Regional Operating Model Redesign)
18

## Slide 20
PHASE 2 · TOM DESIGN
Framework Snapshot
LEWIN
Unfreeze
ADKAR
Awareness → Knowledge
BRIDGES
Ending
KÜBLER-ROSS
Denial
KEY TECHNIQUE THIS PHASE
Target operating model drafting: Design a function-based reporting structure against the assessment's own findings.
journi — Operating Model Redesign (Regional Operating Model Redesign)
19

## Slide 21
PHASE 3 OF 7
Detailed Org Design
Weeks 12–18
NARRATIVE
Details the specific reporting lines, decision rights, and role changes the redesign requires.
journi — Operating Model Redesign (Regional Operating Model Redesign)
20

## Slide 22
PHASE 3 · DETAILED ORG DESIGN
Key Moments in This Phase
Week | What Happens
Week 15 | Decision-rights matrix drafted per function.
Week 18 | Detailed org design gate closes.
journi — Operating Model Redesign (Regional Operating Model Redesign)
21

## Slide 23
PHASE 3 · DETAILED ORG DESIGN
Framework Snapshot
LEWIN
Unfreeze → Change
ADKAR
Knowledge
BRIDGES
Ending → Neutral Zone
KÜBLER-ROSS
Resistance/Anger
KEY TECHNIQUE THIS PHASE
Decision-rights matrix design: Specify exactly which decisions route where under the new structure.
journi — Operating Model Redesign (Regional Operating Model Redesign)
22

## Slide 24
PHASE 4 OF 7
Pilot Transition
Weeks 17–22
NARRATIVE
Pilots the new reporting structure at Casablanca Finance first — Exception E2's pilot-success-masks-risk pattern originates here.
journi — Operating Model Redesign (Regional Operating Model Redesign)
23

## Slide 25
PHASE 4 · PILOT TRANSITION
Key Moments in This Phase
Week | What Happens
Week 18 | Casablanca Finance transitions first.
Week 22 | Pilot succeeds cleanly — but on a pressure profile unlike Kenitra or Settat's.
journi — Operating Model Redesign (Regional Operating Model Redesign)
24

## Slide 26
PHASE 4 · PILOT TRANSITION
Framework Snapshot
LEWIN
Change
ADKAR
Knowledge → Ability
BRIDGES
Neutral Zone
KÜBLER-ROSS
Resistance/Anger → Exploration
KEY TECHNIQUE THIS PHASE
Single-site piloting: De-risk the full transition by testing on one site before all three.
journi — Operating Model Redesign (Regional Operating Model Redesign)
25

## Slide 27
PHASE 5 OF 7
Full Transition
Weeks 21–27
NARRATIVE
Extends the new reporting structure to Kenitra and Settat — where the pilot's clean success starts to look different.
journi — Operating Model Redesign (Regional Operating Model Redesign)
26

## Slide 28
PHASE 5 · FULL TRANSITION
Key Moments in This Phase
Week | What Happens
Week 23 | Amina Sqalli, now receiving escalations from all three sites, shows early capacity strain — Exception E3 opens.
Week 24 | A site director continues deciding unofficially — Exception E4 opens.
Week 27 | Full transition gate closes.
journi — Operating Model Redesign (Regional Operating Model Redesign)
27

## Slide 29
PHASE 5 · FULL TRANSITION
Framework Snapshot
LEWIN
Change
ADKAR
Ability
BRIDGES
Neutral Zone
KÜBLER-ROSS
Exploration
KEY TECHNIQUE THIS PHASE
Staged multi-site rollout: Extend the piloted structure to the remaining two sites.
journi — Operating Model Redesign (Regional Operating Model Redesign)
28

## Slide 30
PHASE 6 OF 7
Governance Adoption Tracking
Weeks 26–32
NARRATIVE
Tracks the new governance rhythm's real adoption — where the program's defining regression actually lands.
journi — Operating Model Redesign (Regional Operating Model Redesign)
29

## Slide 31
PHASE 6 · GOVERNANCE ADOPTION TRACKING
Key Moments in This Phase
Week | What Happens
Week 26 | The first 30-day sustainment checkpoint lands High regression risk — Exception E1 opens, firing ALT-002/ALT-015.
Week 29 | Root cause traced to Kenitra and Settat's unpredictable operational-pressure profile.
Week 32 | A clean checkpoint follows; sign-off unblocks.
journi — Operating Model Redesign (Regional Operating Model Redesign)
30

## Slide 32
PHASE 6 · GOVERNANCE ADOPTION TRACKING
Framework Snapshot
LEWIN
Change
ADKAR
Ability → Reinforcement (regression)
BRIDGES
Neutral Zone
KÜBLER-ROSS
Exploration
KEY TECHNIQUE THIS PHASE
30-day sustainment checkpoint: Catch a real reversion under operational pressure before it becomes permanent.
journi — Operating Model Redesign (Regional Operating Model Redesign)
31

## Slide 33
PHASE 7 OF 7
Standing Rhythm Handover
Weeks 30–34
NARRATIVE
Hands the new reporting structure off to a standing monthly governance rhythm — tested by a second, smaller regression signal.
journi — Operating Model Redesign (Regional Operating Model Redesign)
32

## Slide 34
PHASE 7 · STANDING RHYTHM HANDOVER
Key Moments in This Phase
Week | What Happens
Week 31 | Standing monthly rhythm confirmed and documented.
Week 34+ | A follow-up check three months later finds a partial slip at one site — Exception E6 opens.
journi — Operating Model Redesign (Regional Operating Model Redesign)
33

## Slide 35
PHASE 7 · STANDING RHYTHM HANDOVER
Framework Snapshot
LEWIN
Refreeze
ADKAR
Reinforcement
BRIDGES
New Beginning
KÜBLER-ROSS
Commitment
KEY TECHNIQUE THIS PHASE
Standing monthly governance rhythm: Replace a dedicated program team's oversight with a durable, ongoing rhythm.
journi — Operating Model Redesign (Regional Operating Model Redesign)
34

## Slide 36
PART 4 — MASTER WBS & GANTT
Every Phase, Across the Four Frameworks
Phase | Week(s) | Lewin | ADKAR | Bridges | Kübler-Ross
Current Operating Model Assessment | Weeks 1–8 | Unfreeze | Awareness | Ending | Denial
TOM Design | Weeks 6–14 | Unfreeze | Awareness → Knowledge | Ending | Denial
Detailed Org Design | Weeks 12–18 | Unfreeze → Change | Knowledge | Ending → Neutral Zone | Resistance/Anger
Pilot Transition | Weeks 17–22 | Change | Knowledge → Ability | Neutral Zone | Resistance/Anger → Exploration
Full Transition | Weeks 21–27 | Change | Ability | Neutral Zone | Exploration
Governance Adoption Tracking | Weeks 26–32 | Change | Ability → Reinforcement (regression) | Neutral Zone | Exploration
Standing Rhythm Handover | Weeks 30–34 | Refreeze | Reinforcement | New Beginning | Commitment
journi — Operating Model Redesign (Regional Operating Model Redesign)
35

## Slide 37
PART 4 — MASTER WBS & GANTT
Every Phase, Techniques and Tools
Phase | Week(s) | Technique | Goal | Tool
Current Operating Model Assessment | Weeks 1–8 | Decision-duplication mapping | Make the site-based structure's duplicated decision-making visible and countable. | M4 (Stakeholder Mapping)
TOM Design | Weeks 6–14 | Target operating model drafting | Design a function-based reporting structure against the assessment's own findings. | M17 (WBS & Gantt)
Detailed Org Design | Weeks 12–18 | Decision-rights matrix design | Specify exactly which decisions route where under the new structure. | M21 (Field Notes)
Pilot Transition | Weeks 17–22 | Single-site piloting | De-risk the full transition by testing on one site before all three. | M5 (ADKAR Engine)
Full Transition | Weeks 21–27 | Staged multi-site rollout | Extend the piloted structure to the remaining two sites. | M17 (WBS & Gantt)
Governance Adoption Tracking | Weeks 26–32 | 30-day sustainment checkpoint | Catch a real reversion under operational pressure before it becomes permanent. | M12 (Sustainment)
Standing Rhythm Handover | Weeks 30–34 | Standing monthly governance rhythm | Replace a dedicated program team's oversight with a durable, ongoing rhythm. | M12 (Sustainment)
journi — Operating Model Redesign (Regional Operating Model Redesign)
36

## Slide 38
PART 4 — SIX EXCEPTIONS, IN DETAIL
Six Realistic Ways This Program Could Have Gone Differently
journi — Operating Model Redesign (Regional Operating Model Redesign)
37

## Slide 39
E1 · GOVERNANCE ADOPTION TRACKING, WEEKS 26–32
Regression Risk Score Critical / Sustainment Sign-Off Blocked
DESCRIPTION
The program's first 30-day sustainment checkpoint found decisions at several sites quietly reverting to the old site-director escalation path under real operational pressure — ALT-002's exact condition, with ALT-015 following automatically.
TRIGGER
A sustainment checkpoint on M12 is marked complete with regression risk logged as High.
TIMELINE IMPACT
Blocks sign-off until a clean checkpoint follows — roughly one further monitoring cycle.
RECOVERY TASKS
Root-cause the reversion to Kenitra/Settat's unpredictable operational-pressure profile; reinforce the new decision-rights matrix directly with the reverting sites.
OUTPUTS: A clean follow-up checkpoint; an unblocked sustainment sign-off. RACSI: R = CM, SUP · A = CM · C = FPO · S = PM · I = ES, EU
journi — Operating Model Redesign (Regional Operating Model Redesign)
38

## Slide 40
E2 · PILOT–FULL TRANSITION, WEEKS 22–25
Pilot Success Masks a Site-Specific Risk
DESCRIPTION
Casablanca Finance's pilot succeeds cleanly, but Casablanca's steady, predictable finance-cycle pressure profile doesn't resemble Kenitra or Settat's plant-floor pressure profile — the exact difference that later drives Exception E1's regression at those sites specifically.
TRIGGER
A pilot site's clean success is used to assume readiness at sites with a materially different pressure profile.
TIMELINE IMPACT
No delay if caught before Full Transition — a planning correction, not a schedule change.
RECOVERY TASKS
Explicitly assess each remaining site's own pressure profile rather than assume the pilot's success generalizes.
OUTPUTS: A site-specific readiness assessment ahead of Full Transition. RACSI: R = CM, PM · A = CM · C = SUP · S = FPO · I = ES, EU
journi — Operating Model Redesign (Regional Operating Model Redesign)
39

## Slide 41
E3 · FULL TRANSITION, WEEKS 23–26
A Function Head Overwhelmed by Centralized Decision Volume
DESCRIPTION
Amina Sqalli, now receiving escalations from all three sites rather than one, cannot process the real decision volume alone — a capacity problem distinct from E1's habit-reversion problem, though both can look similar from outside.
TRIGGER
A Function Head's escalation backlog grows visibly following multi-site centralization.
TIMELINE IMPACT
Adds roughly one to two weeks while additional decision-support capacity is arranged.
RECOVERY TASKS
Add delegated decision authority for lower-stakes items; confirm the distinction between a capacity problem and a habit-reversion problem before prescribing a fix.
OUTPUTS: A revised decision-delegation threshold; a sustainable Function Head workload. RACSI: R = FPO, PM · A = CM · C = ES · S = SUP · I = ITL, EU
journi — Operating Model Redesign (Regional Operating Model Redesign)
40

## Slide 42
E4 · FULL TRANSITION–GOVERNANCE TRACKING, WEEKS 24–30
A Site Director Continues Deciding Unofficially
DESCRIPTION
A site director who lost formal decision authority continues making the same decisions informally — staff still bring them the question out of habit, and the director, not wanting to seem unhelpful, answers rather than redirecting.
TRIGGER
Decisions observed flowing through the old informal path despite the formal structure change.
TIMELINE IMPACT
No formal delay, but requires a direct conversation before it hardens into a permanent workaround.
RECOVERY TASKS
A direct conversation with the site director about redirecting rather than answering; reinforce the new path with staff directly.
OUTPUTS: A corrected decision-routing pattern. RACSI: R = CM, ES · A = ES · C = FPO · S = PM · I = SUP, EU
journi — Operating Model Redesign (Regional Operating Model Redesign)
41

## Slide 43
E5 · FULL TRANSITION, WEEKS 23–26
Reporting-Line Systems Lag Behind the Organizational Change
DESCRIPTION
HR and IT systems still show the old site-based reporting lines for several weeks after the organizational change takes effect, creating confusion about who formally approves what.
TRIGGER
A systems audit finds the org chart in HR/IT systems doesn't match the new reporting lines.
TIMELINE IMPACT
Adds roughly one week while systems are updated to match the organizational change.
RECOVERY TASKS
Update HR and IT systems promptly; communicate the interim gap directly so staff aren't confused by the mismatch.
OUTPUTS: Systems-of-record matching the real organizational structure. RACSI: R = ITL · A = PM · C = CM · S = FPO · I = ES, SUP, EU
journi — Operating Model Redesign (Regional Operating Model Redesign)
42

## Slide 44
E6 · STANDING RHYTHM HANDOVER, WEEKS 34+
A Second, Smaller Regression Signal After Handover
DESCRIPTION
A follow-up check three months after handover finds a partial slip at one site — not the full reversion E1 caught, but a specific decision type quietly drifting back, testing whether the standing monthly rhythm actually catches what the dedicated program team used to.
TRIGGER
A standing-rhythm governance check finds a partial, decision-type-specific drift.
TIMELINE IMPACT
No formal delay — resolved within the standing rhythm's own next cycle.
RECOVERY TASKS
Address the specific decision type directly; confirm the standing rhythm itself is catching what it's designed to catch.
OUTPUTS: A corrected drift; confirmed standing-rhythm effectiveness. RACSI: R = SUP, FPO · A = ES · C = CM · S = PM · I = ITL, EU
journi — Operating Model Redesign (Regional Operating Model Redesign)
43

## Slide 45
PART 5 — TRAINING PROGRAM
What This Training Covers
Per the E2E-OM chain, MP-05 is present — this training focuses on the new reporting-line mechanics and decision rights, not on convincing anyone the structure is correct.
journi — Operating Model Redesign (Regional Operating Model Redesign)
44

## Slide 46
PART 5 · TIER 1 OF 3
Strategic Management
Cohort: Yassine Berrada (Sponsor) · Weeks 1–14
Curriculum Entry | Content Focus
Sponsoring a Reporting-Line Change | Why an operating model redesign needs sustained reinforcement, not a one-time announcement, to hold.
Reading M12's Regression-Risk Flag | How to read a sustainment checkpoint as real evidence — a blocked sign-off is the system working, not failing.
journi — Operating Model Redesign (Regional Operating Model Redesign)
45

## Slide 47
PART 5 · TIER 2 OF 3
Operational Management
Cohort: Amina Sqalli (FPO), Loubna Tazi (SUP), other site directors' successors · Weeks 8–22
Curriculum Entry | Content Focus
Operating the New Decision-Rights Matrix | Exactly which decisions route where under the new structure — the direct prerequisite to avoiding Exception E1's reversion.
Redirecting Under Pressure | Specific coaching for the exact moment E1's regression happens — practicing the new routing rather than defaulting to habit.
journi — Operating Model Redesign (Regional Operating Model Redesign)
46

## Slide 48
PART 5 · TIER 3 OF 3
Operations (Frontline)
Cohort: All 95 people-manager-level staff · Weeks 15–25
Curriculum Entry | Content Focus
Using the New Reporting Structure | Who to escalate to under the new model, reinforced with the same decision-rights reference card later redeployed in E1's recovery.
journi — Operating Model Redesign (Regional Operating Model Redesign)
47

## Slide 49
PART 5 — TRAINING PROGRAM
Why This Curriculum Is Shaped This Way
Training completion reaches 100% by Week 25 — before the Week 26 checkpoint reveals the regression. A fully trained population can still regress under real operational pressure, because Knowledge and Ability were never this case's binding constraint — Reinforcement was.
journi — Operating Model Redesign (Regional Operating Model Redesign)
48

## Slide 50
CROSS-REFERENCE
Which journi Modules Dominate This Archetype
M12 (Sustainment)
The 30-day post-transition checkpoint — where a High regression risk fires ALT-002.
M5 (ADKAR Engine)
Reinforcement tracked separately from Ability, since this archetype is where the two diverge.
M17 (WBS & Gantt)
The TPL-OM-7 template — Pilot Transition de-risks Full Transition, one site at a time.
M6 (Emotional & Transition Layer)
A premature "New Beginning" reading is exactly what a regression later contradicts.
M21 (Field Notes)
The decision-rights matrix and site-specific readiness findings, documented directly.
M14 (Analytics)
The Composite Readiness Index drop at the 30-day checkpoint — a real, not gradual, signal.
journi — Operating Model Redesign (Regional Operating Model Redesign)
49

## Slide 51
ALERTS & PROOF
What This Case Fires
ALERTS THIS CASE EXERCISES
ALT-002 (Regression Risk Score Critical)
ALT-015 (Sustainment Sign-Off Blocked)
WHY
Built to run past its first sustainment checkpoint with High regression risk — the clearest real-data proof in the library that training completion alone does not guarantee reinforcement.
journi — Operating Model Redesign (Regional Operating Model Redesign)
50

## Slide 52
KEY TAKEAWAYS
What to Remember About This Archetype
› A real 30-day sustainment checkpoint landing High regression risk, and a training-completion record (100% by Week 25) that proves Reinforcement, not Knowledge, was the actual gap — not glossed over as a clean success.
› ADKAR Reinforcement dominates. Function Heads can pass every earlier checkpoint and still revert to old decision-making under real operational pressure — this archetype is built specifically to show that failure mode, not initial adoption, is the real test.
› Built to run past its first sustainment checkpoint with High regression risk — the clearest real-data proof in the library that training completion alone does not guarantee reinforcement.
journi — Operating Model Redesign (Regional Operating Model Redesign)
51

## Slide 53
Operating Model Redesign
Regional Operating Model Redesign
Manufacturing Sector · Bouregreg Group Scenario Library · Confidential