## Slide 1
Training & Skills Development
Plant Digital Skills Upskilling Program
A standalone digital-skills program with no go-live of its own — the only archetype where training is the entire content of every phase, not a supporting track.
7
PHASES
43
WEEKS
6
EXCEPTIONS
3
TRAINING TIERS
Manufacturing Sector · Bouregreg Group Scenario Library · Confidential

## Slide 2
PART 0 — PURPOSE
What This Guide Is, and How to Use It
WHAT THIS GUIDE IS
This deck follows the Plant Digital Skills Upskilling Program — journi's Training & Skills Development archetype case — from tenant setup through skills sustainment, a standalone digital-literacy program with no system rollout of its own to anchor to.
HOW TO USE IT
This program runs inside the same Bouregreg Group tenant as every other archetype in this series. A reader with the tenant already set up skips straight to CM Project creation.
journi — Training & Skills Development (Plant Digital Skills Upskilling Program)
01

## Slide 3
PART 0 — A NOTE ON FIDELITY
Verified Against journi's Real Source
Every journi module, field, and role named here is verified against journi's real source. This is journi's own stated case with no alerts in its real record — not because the program is trivial, but because none of journi's 9 live alert conditions are built around a standalone skills program with no go-live of its own.
RACSI CODES USED THROUGHOUT
ES = Executive Sponsor · CM = Change Manager · PM = Program/Project Manager · FPO = Functional Process Owner · ITL = IT/Technical Lead · SUP = Supervisor · EU = End User
journi — Training & Skills Development (Plant Digital Skills Upskilling Program)
02

## Slide 4
PART 1 — EXECUTIVE SUMMARY
Why This Case Matters
Every other guide in this series treats training as a track running alongside some other program's own milestones. This case has no surrounding program — the schedule is the curriculum's own, built around what it actually takes for 620 plant-floor staff to acquire, apply, and retain a durable digital skill.
journi — Training & Skills Development (Plant Digital Skills Upskilling Program)
03

## Slide 5
PART 1 — EXECUTIVE SUMMARY
The Case, in Brief
620 staff, plant floor, Kenitra and Settat
43 weeks (guide numbering, org-calendar W16–58)
Bouregreg Group builds a standalone digital-literacy and systems-skills program for 620 plant-floor staff without prior systems training, split across Kenitra and Settat, over 43 weeks — deliberately staggered a month behind the ERP program's own Train phase.
journi — Training & Skills Development (Plant Digital Skills Upskilling Program)
04

## Slide 6
PART 1 — EXECUTIVE SUMMARY
What This Guide Proves, Concretely
An AI-assisted curriculum drafted and refined through M16, a pilot cohort's validation before full two-plant deployment, a competency-verification record distinct from mere attendance, and a sustainment record showing skill retention measured, not assumed, months after delivery closed.
journi — Training & Skills Development (Plant Digital Skills Upskilling Program)
05

## Slide 7
PART 2 — THE FOUR FRAMEWORKS
Weighting for This Archetype
All five ADKAR blocks dominate equally, in sequence. Reinforcement is engineered by two dedicated phases — Practical Application and On-the-Job Coaching — the only archetype in the series to build reinforcement deliberately rather than leave it to chance.
journi — Training & Skills Development (Plant Digital Skills Upskilling Program)
06

## Slide 8
PART 2 — THE FOUR FRAMEWORKS
The Composite Readiness Index, Read for This Case
The Composite Readiness Index climbs steadily and predictably: Awareness and Knowledge move first, Ability climbs sharply once hands-on delivery begins, and Reinforcement is the slowest-moving block by design, closing only after Practical Application and On-the-Job Coaching have both run their full course.
journi — Training & Skills Development (Plant Digital Skills Upskilling Program)
07

## Slide 9
PART 3 — TENANT AND ADMIN SETUP
The Existing Tenant, and Reading Paths by Role
THE EXISTING TENANT
This program runs inside the same tenant journi's Master User Guide builds, under the existing Bouregreg Manufacturing Maroc Organization — no new Organization needed.
READING PATHS, BY ROLE
› A Change Manager running this program day to day: Part 2 once, then Part 4 in full.
› A Program/Project Manager: Part 4's PM Track column and the Master WBS & Gantt.
› An Executive Sponsor: Part 1, then Part 4's phase-opening narratives.
› A Super Admin or Org Admin: Part 3.
journi — Training & Skills Development (Plant Digital Skills Upskilling Program)
08

## Slide 10
PART 3 — TENANT AND ADMIN SETUP
The RACSI Team for This Program
Name | RACSI Code | Role
Fouad Belghazi | ES | Sponsor — VP Manufacturing Operations
Houda Amrani | CM | Change Manager
Tarik Benjelloun | PM | Skills Program Lead
Leila Ouahbi | FPO | Learning & Development Lead
Younes Berrada | ITL | Learning-systems and AI-drafting-tool lead
Karima Semlali | SUP | Kenitra Plant Floor Supervisor
Mustapha Idrissi | SUP | Settat Plant Floor Supervisor
journi — Training & Skills Development (Plant Digital Skills Upskilling Program)
09

## Slide 11
PART 3 — TENANT AND ADMIN SETUP
Creating the CM Project
1
On Module 1 — Hierarchy, create the Plant Digital Skills Upskilling Program CM Project under the existing Bouregreg Manufacturing Maroc Organization.
2
Set Change type: Training & Skills Development. Target population: "Plant-floor staff without prior systems training, Kenitra and Settat (620)." Business driver: "A skills gap identified independently of the ERP program, accelerated once the ERP program made it visible."
3
Save. Lewin opens at Unfreeze — a standalone skills program with no go-live of its own to align to.
4
On Module 17 — WBS & Gantt, load the TPL-TSD-7 phase template: Skills Gap Diagnosis, Curriculum Design, Training Delivery, Competency Verification, Practical Application, On-the-Job Coaching, Skills Sustainment.
journi — Training & Skills Development (Plant Digital Skills Upskilling Program)
10

## Slide 12
PART 3 — TENANT AND ADMIN SETUP
Charters for This Program
Charter | Accountable | Review Cadence
CHTR-01 Sponsorship / Leadership Charter | Fouad Belghazi (ES) | Per Phase Gate
CHTR-03 Communication Charter | Houda Amrani (CM) | Per communication wave
CHTR-08 Pulse / Interview Charter | Houda Amrani (CM) | Per phase gate + ad hoc
journi — Training & Skills Development (Plant Digital Skills Upskilling Program)
11

## Slide 13
PART 3 — TENANT AND ADMIN SETUP
Setup Checklist
Base tenant confirmed (Bouregreg Group, existing Organization)
Skills program team accounts created
CM Project created, Lewin opened at Unfreeze
TPL-TSD-7 phase template loaded on M17
Applicable Charters reviewed and accountable owners confirmed
journi — Training & Skills Development (Plant Digital Skills Upskilling Program)
12

## Slide 14
PART 4 — WEEK-BY-WEEK TIMELINE
7 Phases, In Order
1. Skills Gap Diagnosis
2. Curriculum Design
3. Training Delivery
4. Competency Verification
5. Practical Application
6. On-the-Job Coaching
7. Skills Sustainment
Total program length: 43 weeks (guide numbering, org-calendar W16–58). Every phase below is walked in detail across the next slides — normal flow first, then six exceptions in full operational detail.
journi — Training & Skills Development (Plant Digital Skills Upskilling Program)
13

## Slide 15
PHASE 1 OF 7
Skills Gap Diagnosis
Weeks 1–7
NARRATIVE
Establishes exactly what digital and systems skills gap exists across plant-floor staff at Kenitra and Settat, independent of any specific system rollout.
journi — Training & Skills Development (Plant Digital Skills Upskilling Program)
14

## Slide 16
PHASE 1 · SKILLS GAP DIAGNOSIS
Key Moments in This Phase
Week | What Happens
Week 1 | Kickoff; Lewin opens at Unfreeze.
Week 3 | Skills assessment begins at Kenitra.
Week 7 | Phase Gate: Go.
journi — Training & Skills Development (Plant Digital Skills Upskilling Program)
15

## Slide 17
PHASE 1 · SKILLS GAP DIAGNOSIS
Framework Snapshot
LEWIN
Unfreeze
ADKAR
Awareness
BRIDGES
Ending
KÜBLER-ROSS
Denial
KEY TECHNIQUE THIS PHASE
Plant-floor skills survey: Establish exactly which digital and systems skills 620 staff currently lack.
journi — Training & Skills Development (Plant Digital Skills Upskilling Program)
16

## Slide 18
PHASE 2 OF 7
Curriculum Design
Weeks 6–15
NARRATIVE
Designs the curriculum with AI-assisted drafting via M16 — the archetype that most exercises this module.
journi — Training & Skills Development (Plant Digital Skills Upskilling Program)
17

## Slide 19
PHASE 2 · CURRICULUM DESIGN
Key Moments in This Phase
Week | What Happens
Week 9 | AI-assisted curriculum drafting begins for Module 1.
Week 14 | Train-the-trainer session for the delivery team.
Week 15 | Phase Gate: Go.
journi — Training & Skills Development (Plant Digital Skills Upskilling Program)
18

## Slide 20
PHASE 2 · CURRICULUM DESIGN
Framework Snapshot
LEWIN
Unfreeze
ADKAR
Awareness → Knowledge
BRIDGES
Ending → Neutral Zone
KÜBLER-ROSS
Denial → Resistance/Anger
KEY TECHNIQUE THIS PHASE
AI-assisted curriculum drafting: Draft usable module content quickly without a dedicated instructional-design team.
journi — Training & Skills Development (Plant Digital Skills Upskilling Program)
19

## Slide 21
PHASE 3 OF 7
Training Delivery
Weeks 13–29
NARRATIVE
Delivers the curriculum, first to a pilot cohort, then in full across both plants — staggered a month behind the ERP program's own Train phase.
journi — Training & Skills Development (Plant Digital Skills Upskilling Program)
20

## Slide 22
PHASE 3 · TRAINING DELIVERY
Key Moments in This Phase
Week | What Happens
Week 15 | Pilot cohort delivery begins, Kenitra.
Week 23 | Pilot cohort validation complete.
Week 29 | Full deployment complete; Phase Gate: Go.
journi — Training & Skills Development (Plant Digital Skills Upskilling Program)
21

## Slide 23
PHASE 3 · TRAINING DELIVERY
Framework Snapshot
LEWIN
Change
ADKAR
Knowledge → Ability
BRIDGES
Neutral Zone
KÜBLER-ROSS
Resistance/Anger → Exploration
KEY TECHNIQUE THIS PHASE
Pilot-then-refine, staggered wave deployment: Validate the curriculum before committing both plants' full population to it.
journi — Training & Skills Development (Plant Digital Skills Upskilling Program)
22

## Slide 24
PHASE 4 OF 7
Competency Verification
Weeks 23–31
NARRATIVE
Verifies delivered training actually produced usable skill — a hands-on test, not attendance.
journi — Training & Skills Development (Plant Digital Skills Upskilling Program)
23

## Slide 25
PHASE 4 · COMPETENCY VERIFICATION
Key Moments in This Phase
Week | What Happens
Week 25 | Competency verification begins, Kenitra wave 1.
Week 30 | Targeted refresher sessions for identified gaps.
Week 31 | Phase Gate: Go — 100% certification confirmed.
journi — Training & Skills Development (Plant Digital Skills Upskilling Program)
24

## Slide 26
PHASE 4 · COMPETENCY VERIFICATION
Framework Snapshot
LEWIN
Change
ADKAR
Ability
BRIDGES
Neutral Zone
KÜBLER-ROSS
Exploration
KEY TECHNIQUE THIS PHASE
Hands-on competency test: Verify actual usable skill, not just attendance.
journi — Training & Skills Development (Plant Digital Skills Upskilling Program)
25

## Slide 27
PHASE 5 OF 7
Practical Application
Weeks 29–35
NARRATIVE
Moves verified skill into real day-to-day use — the first of two dedicated reinforcement phases built deliberately, not left to chance.
journi — Training & Skills Development (Plant Digital Skills Upskilling Program)
26

## Slide 28
PHASE 5 · PRACTICAL APPLICATION
Key Moments in This Phase
Week | What Happens
Week 30 | Real-world system-use monitoring, Kenitra.
Week 32 | Friction points identified from floor observation.
Week 35 | Phase Gate: Go.
journi — Training & Skills Development (Plant Digital Skills Upskilling Program)
27

## Slide 29
PHASE 5 · PRACTICAL APPLICATION
Framework Snapshot
LEWIN
Change
ADKAR
Ability → Reinforcement
BRIDGES
Neutral Zone
KÜBLER-ROSS
Exploration → Commitment
KEY TECHNIQUE THIS PHASE
Real-world use monitoring: Confirm the verified skill is actually used daily on the floor.
journi — Training & Skills Development (Plant Digital Skills Upskilling Program)
28

## Slide 30
PHASE 6 OF 7
On-the-Job Coaching
Weeks 31–39
NARRATIVE
Locks in the skill through supervisor-led coaching — the second dedicated reinforcement phase.
journi — Training & Skills Development (Plant Digital Skills Upskilling Program)
29

## Slide 31
PHASE 6 · ON-THE-JOB COACHING
Key Moments in This Phase
Week | What Happens
Week 31 | Supervisors trained as on-the-job coaches.
Week 36 | Coaching observations consolidated across both plants.
Week 39 | Phase Gate: Go.
journi — Training & Skills Development (Plant Digital Skills Upskilling Program)
30

## Slide 32
PHASE 6 · ON-THE-JOB COACHING
Framework Snapshot
LEWIN
Change
ADKAR
Reinforcement
BRIDGES
New Beginning
KÜBLER-ROSS
Commitment
KEY TECHNIQUE THIS PHASE
Supervisor-led coaching rounds: Lock in the skill through direct floor supervision, not just self-practice.
journi — Training & Skills Development (Plant Digital Skills Upskilling Program)
31

## Slide 33
PHASE 7 OF 7
Skills Sustainment
Weeks 35–43
NARRATIVE
Confirms the skill holds without active coaching — the program's actual close, and the milestone Lewin's Refreeze anchors to.
journi — Training & Skills Development (Plant Digital Skills Upskilling Program)
32

## Slide 34
PHASE 7 · SKILLS SUSTAINMENT
Key Moments in This Phase
Week | What Happens
Week 37 | First sustainment check, Kenitra — regression risk Low.
Week 41 | Second sustainment check, both plants — regression risk Low.
Week 43 | Refreeze confirmed; program closes.
journi — Training & Skills Development (Plant Digital Skills Upskilling Program)
33

## Slide 35
PHASE 7 · SKILLS SUSTAINMENT
Framework Snapshot
LEWIN
Change → Refreeze
ADKAR
Reinforcement
BRIDGES
New Beginning
KÜBLER-ROSS
Commitment
KEY TECHNIQUE THIS PHASE
Two-checkpoint sustainment tracking: Confirm the skill holds without active coaching, not just immediately after it ends.
journi — Training & Skills Development (Plant Digital Skills Upskilling Program)
34

## Slide 36
PART 4 — MASTER WBS & GANTT
Every Phase, Across the Four Frameworks
Phase | Week(s) | Lewin | ADKAR | Bridges | Kübler-Ross
Skills Gap Diagnosis | Weeks 1–7 | Unfreeze | Awareness | Ending | Denial
Curriculum Design | Weeks 6–15 | Unfreeze | Awareness → Knowledge | Ending → Neutral Zone | Denial → Resistance/Anger
Training Delivery | Weeks 13–29 | Change | Knowledge → Ability | Neutral Zone | Resistance/Anger → Exploration
Competency Verification | Weeks 23–31 | Change | Ability | Neutral Zone | Exploration
Practical Application | Weeks 29–35 | Change | Ability → Reinforcement | Neutral Zone | Exploration → Commitment
On-the-Job Coaching | Weeks 31–39 | Change | Reinforcement | New Beginning | Commitment
Skills Sustainment | Weeks 35–43 | Change → Refreeze | Reinforcement | New Beginning | Commitment
journi — Training & Skills Development (Plant Digital Skills Upskilling Program)
35

## Slide 37
PART 4 — MASTER WBS & GANTT
Every Phase, Techniques and Tools
Phase | Week(s) | Technique | Goal | Tool
Skills Gap Diagnosis | Weeks 1–7 | Plant-floor skills survey | Establish exactly which digital and systems skills 620 staff currently lack. | On-site observation checklist
Curriculum Design | Weeks 6–15 | AI-assisted curriculum drafting | Draft usable module content quickly without a dedicated instructional-design team. | M16 (AI Use Case Library)
Training Delivery | Weeks 13–29 | Pilot-then-refine, staggered wave deployment | Validate the curriculum before committing both plants' full population to it. | M9 (Training)
Competency Verification | Weeks 23–31 | Hands-on competency test | Verify actual usable skill, not just attendance. | M9 (Training) — competency record
Practical Application | Weeks 29–35 | Real-world use monitoring | Confirm the verified skill is actually used daily on the floor. | M21 (Field Notes)
On-the-Job Coaching | Weeks 31–39 | Supervisor-led coaching rounds | Lock in the skill through direct floor supervision, not just self-practice. | M9 (Training)
Skills Sustainment | Weeks 35–43 | Two-checkpoint sustainment tracking | Confirm the skill holds without active coaching, not just immediately after it ends. | M12 (Sustainment)
journi — Training & Skills Development (Plant Digital Skills Upskilling Program)
36

## Slide 38
PART 4 — SIX EXCEPTIONS, IN DETAIL
Six Realistic Contingencies — None of Which Actually Occurred
journi — Training & Skills Development (Plant Digital Skills Upskilling Program)
37

## Slide 39
C1 · SKILLS GAP DIAGNOSIS, WEEKS 1–7
Skills-Gap Assessment Misses a Real Gap
DESCRIPTION
The plant-floor assessment undercounts a specific skill gap because observation and interview don't surface a gap that only appears under real operating pressure. This did not occur.
TRIGGER
The gap surfaces later, during Training Delivery, as unexpectedly slow module completion.
TIMELINE IMPACT
Would require reopening Phase 1's findings and adding a module segment mid-curriculum.
RECOVERY TASKS
Re-assess with a more targeted method (hands-on task simulation); add a bridging module; re-verify the affected skill.
OUTPUTS: A corrected skills-gap record; an added curriculum module. RACSI: R = PM, FPO · A = CM · C = ITL · S = SUP · I = ES, EU
journi — Training & Skills Development (Plant Digital Skills Upskilling Program)
38

## Slide 40
C2 · CURRICULUM DESIGN, WEEKS 9–12
AI-Drafted Curriculum Content Is Technically Inaccurate
DESCRIPTION
M16's AI-assisted drafting produces module content that is fluent but technically wrong for Bouregreg Group's specific systems configuration. This did not occur.
TRIGGER
Human review during Phase 2 catches a factual error in drafted content.
TIMELINE IMPACT
Minor if caught during review; more disruptive if it reaches pilot delivery.
RECOVERY TASKS
Strengthen the human-review step validating systems-configuration accuracy; issue a correction session if needed.
OUTPUTS: A corrected module; a strengthened review step. RACSI: R = ITL, FPO · A = CM · C = PM · S = SUP · I = ES, EU
journi — Training & Skills Development (Plant Digital Skills Upskilling Program)
39

## Slide 41
C3 · TRAINING DELIVERY, WEEKS 15–23
Pilot Cohort Reveals the Curriculum Doesn't Work As Designed
DESCRIPTION
The pilot cohort's feedback shows the curriculum's pacing or sequencing doesn't work for plant-floor learners — not a content error, a design one. This did not occur.
TRIGGER
Pilot feedback or competency results showing a design-traceable difficulty pattern.
TIMELINE IMPACT
Would delay full deployment by however long a redesign takes — the cost the pilot exists to absorb.
RECOVERY TASKS
Redesign the affected portion; re-pilot with a small group before full deployment.
OUTPUTS: A redesigned, re-piloted curriculum portion. RACSI: R = FPO, PM · A = CM · C = ITL · S = SUP · I = ES, EU
journi — Training & Skills Development (Plant Digital Skills Upskilling Program)
40

## Slide 42
C4 · COMPETENCY VERIFICATION, WEEKS 25–29
Competency Verification Reveals Widespread Certification Failure
DESCRIPTION
A large share of one wave's staff fail the hands-on competency test — a systemic, not individual, problem. This did not occur.
TRIGGER
A verification pass rate well below the near-100% target.
TIMELINE IMPACT
Would pause the affected wave's gate while delivery or test-design is diagnosed.
RECOVERY TASKS
Diagnose delivery vs. test-validity failure; re-deliver or redesign accordingly; re-verify only the affected wave.
OUTPUTS: A diagnosis record; a corrected delivery or test; a re-verified wave. RACSI: R = PM, FPO · A = CM · C = ITL · S = SUP · I = ES, EU
journi — Training & Skills Development (Plant Digital Skills Upskilling Program)
41

## Slide 43
C5 · PRACTICAL APPLICATION, WEEKS 29–35
Practical Application Reveals the Skill Doesn't Transfer to Real Conditions
DESCRIPTION
Staff pass competency verification in a controlled setting but struggle under real plant-floor conditions — a transfer gap distinct from a competency gap. This did not occur.
TRIGGER
Floor observation showing verified-competent staff defaulting to old methods under pressure.
TIMELINE IMPACT
Would extend Practical Application's monitoring period and pull forward coaching content.
RECOVERY TASKS
Identify the specific real-condition factors; adjust job aids; begin targeted coaching earlier for the affected group.
OUTPUTS: A transfer-gap diagnosis; condition-specific job aids. RACSI: R = CM, SUP · A = CM · C = FPO · S = PM · I = ES, ITL, EU
journi — Training & Skills Development (Plant Digital Skills Upskilling Program)
42

## Slide 44
C6 · SKILLS SUSTAINMENT, WEEKS 37–41
Sustainment Check Reveals Skill Decay Months Later
DESCRIPTION
A sustainment checkpoint finds skill use has genuinely decayed — staff quietly reverted to old methods once active coaching stopped. This did not occur; both checkpoints logged regression risk as Low.
TRIGGER
A sustainment checkpoint logging regression risk as Medium or High.
TIMELINE IMPACT
Would delay program closure while a refresher-coaching cycle runs and a second check confirms it held.
RECOVERY TASKS
Run a targeted refresher cycle; identify and address the specific root cause of decay; re-run the sustainment check.
OUTPUTS: A refresher-coaching record; a confirmed clean sustainment check before closure. RACSI: R = CM, SUP · A = ES · C = FPO, PM · S = ITL · I = EU
journi — Training & Skills Development (Plant Digital Skills Upskilling Program)
43

## Slide 45
PART 5 — TRAINING PROGRAM
What This Training Covers
Training IS this archetype's entire content, not a supporting track — every phase in this program exists to move the population through the ADKAR arc itself, using specific, checkable compliance-adjacent behaviors verified through hands-on testing.
journi — Training & Skills Development (Plant Digital Skills Upskilling Program)
44

## Slide 46
PART 5 · TIER 1 OF 3
Strategic Management
Cohort: Fouad Belghazi (Sponsor), plant leadership · Weeks 1–16
Curriculum Entry | Content Focus
Sponsoring a Standalone Skills Program | Why a program with no go-live of its own still needs sustained sponsorship to hold through 43 weeks.
Reading a Sustainment Checkpoint as Real Evidence | How to read the two sustainment checks as accountable evidence, not a closeout formality.
journi — Training & Skills Development (Plant Digital Skills Upskilling Program)
45

## Slide 47
PART 5 · TIER 2 OF 3
Operational Management
Cohort: Karima Semlali, Mustapha Idrissi (Supervisors), delivery team · Weeks 14–39
Curriculum Entry | Content Focus
Train-the-Trainer, Digital Skills Program | Preparing the delivery team to teach the finalized curriculum consistently across both plants.
Coaching the New Skill On the Floor | Observation-based coaching rounds rather than informal check-ins.
journi — Training & Skills Development (Plant Digital Skills Upskilling Program)
46

## Slide 48
PART 5 · TIER 3 OF 3
Operations (Frontline)
Cohort: All 620 plant-floor staff · Weeks 15–29
Curriculum Entry | Content Focus
Module 1: Systems Navigation Basics | Core digital-systems navigation for staff without prior systems training.
Module 2: Digital Data Entry | Practical, checkable data-entry steps on the systems staff use daily.
Module 3: Digital Work Instructions | Reading and following digital work instructions in place of paper-based ones.
journi — Training & Skills Development (Plant Digital Skills Upskilling Program)
47

## Slide 49
PART 5 — TRAINING PROGRAM
Why This Curriculum Is Shaped This Way
Part 5 in this archetype is not a separate curriculum but a full course catalog by tier — the one deliverable in this series meant to outlive the program, since training itself already carried the full narrative in every phase above.
journi — Training & Skills Development (Plant Digital Skills Upskilling Program)
48

## Slide 50
CROSS-REFERENCE
Which journi Modules Dominate This Archetype
M9 (Training)
The heaviest use of any archetype — the entire program's content runs through this module.
M16 (AI Use Case Library)
AI-assisted curriculum drafting — the archetype that most exercises this module.
M5 (ADKAR Engine)
All five blocks tracked in sequence, from Awareness through Reinforcement.
M12 (Sustainment)
Two consecutive clean checkpoints, spaced apart, before the program closes Refreeze.
M17 (WBS & Gantt)
The TPL-TSD-7 template — the only archetype where every phase is itself training content.
M21 (Field Notes)
Floor-observation friction points and coaching outcomes, logged directly.
journi — Training & Skills Development (Plant Digital Skills Upskilling Program)
49

## Slide 51
ALERTS & PROOF
What This Case Proves By Not Firing
NO LIVE ALERT FIRES IN THIS PROGRAM'S REAL RECORD
Stated plainly, not manufactured — a clean record reported as a clean record.
WHY
None — none of journi's 9 live alerts are built around a standalone skills program with no go-live and no resistance log of its own.
journi — Training & Skills Development (Plant Digital Skills Upskilling Program)
50

## Slide 52
KEY TAKEAWAYS
What to Remember About This Archetype
› An AI-assisted curriculum drafted and refined through M16, a pilot cohort's validation before full two-plant deployment, a competency-verification record distinct from mere attendance, and a sustainment record showing skill retention measured, not assumed, months after delivery closed.
› All five ADKAR blocks dominate equally, in sequence. Reinforcement is engineered by two dedicated phases — Practical Application and On-the-Job Coaching — the only archetype in the series to build reinforcement deliberately rather than leave it to chance.
› None — none of journi's 9 live alerts are built around a standalone skills program with no go-live and no resistance log of its own.
journi — Training & Skills Development (Plant Digital Skills Upskilling Program)
51

## Slide 53
Training & Skills Development
Plant Digital Skills Upskilling Program
Manufacturing Sector · Bouregreg Group Scenario Library · Confidential