## Slide 1
Business Process Redesign
Order-to-Cash Process Redesign
Redesigning a process independent of any system change — where staff who privately own today's workarounds resist a redesign that makes those workarounds obsolete.
7
PHASES
50
WEEKS
6
EXCEPTIONS
3
TRAINING TIERS
Manufacturing Sector · Bouregreg Group Scenario Library · Confidential

## Slide 2
PART 0 — PURPOSE
What This Guide Is, and How to Use It
WHAT THIS GUIDE IS
This deck follows the Order-to-Cash Process Redesign — journi's BPR archetype case — from tenant setup through sustainment handoff, showing exactly how a process-only redesign (no system change) is run inside journi, week by week.
HOW TO USE IT
This program runs inside the same Bouregreg Group tenant as every other archetype in this series. A reader with the tenant already set up skips straight to CM Project creation.
journi — Business Process Redesign (Order-to-Cash Process Redesign)
01

## Slide 3
PART 0 — A NOTE ON FIDELITY
Verified Against journi's Real Source
Every journi module, field, and role named here is verified against journi's real source. Order-to-Cash is journi's own stated case for ALT-004 (Resistance Escalation Threshold Breached) — this deck shows exactly how that alert fires and is resolved through co-design, not suppression.
RACSI CODES USED THROUGHOUT
ES = Executive Sponsor · CM = Change Manager · PM = Program/Project Manager · FPO = Functional Process Owner · ITL = IT/Technical Lead · SUP = Supervisor · EU = End User
journi — Business Process Redesign (Order-to-Cash Process Redesign)
02

## Slide 4
PART 1 — EXECUTIVE SUMMARY
Why This Case Matters
Finance staff who built and privately own today's manual workarounds resist a redesign that makes those workarounds obsolete — by design, more than any specific skill gap, resistance (Kübler-Ross) is this archetype's central and defining risk.
journi — Business Process Redesign (Order-to-Cash Process Redesign)
03

## Slide 5
PART 1 — EXECUTIVE SUMMARY
The Case, in Brief
140 staff, Casablanca finance (AR and AP)
50 weeks (guide numbering)
Casablanca HQ's finance function has run order-to-cash manually since before the ERP program began; this 50-week project redesigns the process itself, independent of any system change, targeting a three-week month-end reconciliation problem self-inflicted by process design, not tooling.
journi — Business Process Redesign (Order-to-Cash Process Redesign)
04

## Slide 6
PART 1 — EXECUTIVE SUMMARY
What This Guide Proves, Concretely
A real ALT-004 firing at Week 20–24, resolved through a co-designed accuracy safeguard the resisting staff themselves helped define — and five further exceptions showing exactly how a redesign can go sideways even after the headline resistance risk is handled.
journi — Business Process Redesign (Order-to-Cash Process Redesign)
05

## Slide 7
PART 2 — THE FOUR FRAMEWORKS
Weighting for This Archetype
Kübler-Ross dominates. Staff who privately own today's workarounds resist a redesign that makes those workarounds obsolete — the Resistance/Anger stage, and the Resistance Log (M10) that feeds it, is this archetype's central risk, more than any specific skill gap ADKAR would otherwise catch first.
journi — Business Process Redesign (Order-to-Cash Process Redesign)
06

## Slide 8
PART 2 — THE FOUR FRAMEWORKS
The Composite Readiness Index, Read for This Case
The Composite Readiness Index dips visibly during the Pilot phase as the three resistance entries accumulate, then recovers once the co-designed safeguard lands — a real, not cosmetic, trough-and-recovery pattern worth reading as designed evidence, not noise.
journi — Business Process Redesign (Order-to-Cash Process Redesign)
07

## Slide 9
PART 3 — TENANT AND ADMIN SETUP
The Existing Tenant, and Reading Paths by Role
THE EXISTING TENANT
This program runs inside the same tenant journi's Master User Guide builds, under the existing Bouregreg Manufacturing Maroc Organization — no new Organization needed.
READING PATHS, BY ROLE
› A Change Manager running this program day to day: Part 2 once, then Part 4 in full.
› A Program/Project Manager: Part 4's PM Track column and the Master WBS & Gantt.
› An Executive Sponsor: Part 1, then Part 4's phase-opening narratives.
› A Super Admin or Org Admin: Part 3.
journi — Business Process Redesign (Order-to-Cash Process Redesign)
08

## Slide 10
PART 3 — TENANT AND ADMIN SETUP
The RACSI Team for This Program
Name | RACSI Code | Role
Karim Zniber | ES | Sponsor — VP Finance
Imane Berrada | CM | Change Manager
Othmane Rifai | PM | Program Manager
Salwa Tazi | FPO | Casablanca Finance Process Owner
Karim Alami | ITL | IT/Technical Lead
Amina Sebti | SUP | Supervisor
journi — Business Process Redesign (Order-to-Cash Process Redesign)
09

## Slide 11
PART 3 — TENANT AND ADMIN SETUP
Creating the CM Project
1
On Module 1 — Hierarchy, create the Order-to-Cash Process Redesign CM Project under the existing Bouregreg Manufacturing Maroc Organization — no new tenant needed.
2
Set Change type: Business Process Redesign. Target population: "Casablanca finance (AR and AP), 140 staff." Business driver: "Three weeks of month-end reconciliation work, self-inflicted by process design."
3
Save. Lewin opens at Unfreeze, run alongside the ERP program's own Discovery.
4
On Module 17 — WBS & Gantt, load the TPL-BPR-7 phase template: Intake & Diagnosis, Clean-Slate Design, Build, Pilot, Rollout, Stabilization, Sustainment.
journi — Business Process Redesign (Order-to-Cash Process Redesign)
10

## Slide 12
PART 3 — TENANT AND ADMIN SETUP
Charters for This Program
Charter | Accountable | Review Cadence
CHTR-01 Sponsorship / Leadership Charter | Karim Zniber (ES) | Per Phase Gate
CHTR-04 Organizational Impact Charter | Imane Berrada (CM) | On scope change
CHTR-08 Pulse / Interview Charter | Imane Berrada (CM) | Per phase gate + ad hoc
journi — Business Process Redesign (Order-to-Cash Process Redesign)
11

## Slide 13
PART 3 — TENANT AND ADMIN SETUP
Setup Checklist
Base tenant confirmed (Bouregreg Group, existing Organization)
BPR program team accounts created
CM Project created, Lewin opened at Unfreeze
TPL-BPR-7 phase template loaded on M17
Applicable Charters reviewed and accountable owners confirmed
journi — Business Process Redesign (Order-to-Cash Process Redesign)
12

## Slide 14
PART 4 — WEEK-BY-WEEK TIMELINE
7 Phases, In Order
1. Intake & Diagnosis
2. Clean-Slate Design
3. Build
4. Pilot
5. Rollout
6. Stabilization
7. Sustainment
Total program length: 50 weeks (guide numbering). Every phase below is walked in detail across the next slides — normal flow first, then six exceptions in full operational detail.
journi — Business Process Redesign (Order-to-Cash Process Redesign)
13

## Slide 15
PHASE 1 OF 7
Intake & Diagnosis
Weeks 1–7
NARRATIVE
Characterizes exactly where the three-week reconciliation problem comes from, process step by process step — before any redesign is proposed.
journi — Business Process Redesign (Order-to-Cash Process Redesign)
14

## Slide 16
PHASE 1 · INTAKE & DIAGNOSIS
Key Moments in This Phase
Week | What Happens
Week 1 | Kickoff; Lewin opens at Unfreeze, run alongside the ERP program's own Discovery.
Week 5 | Process-step diagnosis identifies the specific manual workarounds driving the delay.
Week 7 | Diagnosis gate closes.
journi — Business Process Redesign (Order-to-Cash Process Redesign)
15

## Slide 17
PHASE 1 · INTAKE & DIAGNOSIS
Framework Snapshot
LEWIN
Unfreeze
ADKAR
Awareness
BRIDGES
Ending
KÜBLER-ROSS
Denial
KEY TECHNIQUE THIS PHASE
Process-step root-cause mapping: Trace the three-week delay to specific manual workarounds, by step.
journi — Business Process Redesign (Order-to-Cash Process Redesign)
16

## Slide 18
PHASE 2 OF 7
Clean-Slate Design
Weeks 5–8
NARRATIVE
Designs the redesigned process without being anchored to today's workaround-shaped version of it.
journi — Business Process Redesign (Order-to-Cash Process Redesign)
17

## Slide 19
PHASE 2 · CLEAN-SLATE DESIGN
Key Moments in This Phase
Week | What Happens
Week 6 | Clean-slate design workshop, deliberately excluding today's workaround logic.
Week 8 | Clean-slate design signed off by the Steering Committee.
journi — Business Process Redesign (Order-to-Cash Process Redesign)
18

## Slide 20
PHASE 2 · CLEAN-SLATE DESIGN
Framework Snapshot
LEWIN
Unfreeze
ADKAR
Awareness
BRIDGES
Ending
KÜBLER-ROSS
Denial
KEY TECHNIQUE THIS PHASE
Clean-slate workshop: Design the new process without anchoring to today's workaround-shaped version.
journi — Business Process Redesign (Order-to-Cash Process Redesign)
19

## Slide 21
PHASE 3 OF 7
Build
Weeks 8–16
NARRATIVE
Builds the redesigned process's specific steps, forms, and approval chain — this is where Exception E4's legacy-system constraint surfaces.
journi — Business Process Redesign (Order-to-Cash Process Redesign)
20

## Slide 22
PHASE 3 · BUILD
Key Moments in This Phase
Week | What Happens
Week 10 | A legacy system constraint blocks a required data field — Exception E4 opens.
Week 13 | A bounded workaround validated and configured.
Week 16 | Build gate closes.
journi — Business Process Redesign (Order-to-Cash Process Redesign)
21

## Slide 23
PHASE 3 · BUILD
Framework Snapshot
LEWIN
Unfreeze → Change
ADKAR
Knowledge
BRIDGES
Ending → Neutral Zone
KÜBLER-ROSS
Denial → Resistance/Anger
KEY TECHNIQUE THIS PHASE
Bounded technical workaround design: Solve a legacy-system constraint without touching the legacy system directly.
journi — Business Process Redesign (Order-to-Cash Process Redesign)
22

## Slide 24
PHASE 4 OF 7
Pilot
Weeks 14–24
NARRATIVE
Pilots the redesigned process on a single process step — the phase this archetype is built to cross the resistance-escalation threshold in.
journi — Business Process Redesign (Order-to-Cash Process Redesign)
23

## Slide 25
PHASE 4 · PILOT
Key Moments in This Phase
Week | What Happens
Week 20 | First resistance entry logged by an AR staff member defending removed manual-control expertise.
Week 24 | Third resistance entry lands, firing ALT-004 — Exception E1 opens and resolves within the same week.
journi — Business Process Redesign (Order-to-Cash Process Redesign)
24

## Slide 26
PHASE 4 · PILOT
Framework Snapshot
LEWIN
Change
ADKAR
Knowledge → Ability
BRIDGES
Neutral Zone
KÜBLER-ROSS
Resistance/Anger
KEY TECHNIQUE THIS PHASE
Co-designed accuracy safeguard: Resolve resistance by building the mitigation with the resisting staff, not around them.
journi — Business Process Redesign (Order-to-Cash Process Redesign)
25

## Slide 27
PHASE 5 OF 7
Rollout
Weeks 22–32
NARRATIVE
Rolls the redesigned process out organization-wide across AR and AP — where an informal, untracked resistance pattern (Exception E2) can hide.
journi — Business Process Redesign (Order-to-Cash Process Redesign)
26

## Slide 28
PHASE 5 · ROLLOUT
Key Moments in This Phase
Week | What Happens
Week 26 | Adoption metrics lag in a sub-team with no open resistance entries — Exception E2 opens.
Week 28 | The co-designed safeguard, tested only against AR's volume, reaches AP — Exception E3 opens.
Week 32 | Rollout gate closes.
journi — Business Process Redesign (Order-to-Cash Process Redesign)
27

## Slide 29
PHASE 5 · ROLLOUT
Framework Snapshot
LEWIN
Change
ADKAR
Ability
BRIDGES
Neutral Zone
KÜBLER-ROSS
Resistance/Anger → Exploration
KEY TECHNIQUE THIS PHASE
Adoption-vs-resistance-log cross-check: Catch an informal resistance pattern that never becomes a formal log entry.
journi — Business Process Redesign (Order-to-Cash Process Redesign)
28

## Slide 30
PHASE 6 OF 7
Stabilization
Weeks 30–42
NARRATIVE
Confirms the redesigned process holds under real monthly volume — and whether the reconciliation-time target is actually being met.
journi — Business Process Redesign (Order-to-Cash Process Redesign)
29

## Slide 31
PHASE 6 · STABILIZATION
Key Moments in This Phase
Week | What Happens
Week 34 | Reconciliation time reads two weeks, not the targeted one week — Exception E5 opens.
Week 38 | Root-cause disaggregation traces the shortfall to E3's AP-specific safeguard cost.
Week 42 | Stabilization gate closes.
journi — Business Process Redesign (Order-to-Cash Process Redesign)
30

## Slide 32
PHASE 6 · STABILIZATION
Framework Snapshot
LEWIN
Change
ADKAR
Ability
BRIDGES
Neutral Zone
KÜBLER-ROSS
Exploration
KEY TECHNIQUE THIS PHASE
Reconciliation-time root-cause disaggregation: Separate a real partial shortfall from a hidden, addressable cause.
journi — Business Process Redesign (Order-to-Cash Process Redesign)
31

## Slide 33
PHASE 7 OF 7
Sustainment
Weeks 40–50
NARRATIVE
Hands the redesigned process off to standing operations — complicated by the Process Owner's own mid-rollout departure.
journi — Business Process Redesign (Order-to-Cash Process Redesign)
32

## Slide 34
PHASE 7 · SUSTAINMENT
Key Moments in This Phase
Week | What Happens
Week 26 | Salwa Tazi's departure notice triggers Exception E6's structured handover.
Week 44 | A successor Process Owner fully onboarded and RACSI-updated.
Week 50 | Sustainment handoff complete; program closes.
journi — Business Process Redesign (Order-to-Cash Process Redesign)
33

## Slide 35
PHASE 7 · SUSTAINMENT
Framework Snapshot
LEWIN
Refreeze
ADKAR
Reinforcement
BRIDGES
New Beginning
KÜBLER-ROSS
Commitment
KEY TECHNIQUE THIS PHASE
Decision-rationale handover: Preserve the *why* behind key design decisions, not just the *what*, through a leadership transition.
journi — Business Process Redesign (Order-to-Cash Process Redesign)
34

## Slide 36
PART 4 — MASTER WBS & GANTT
Every Phase, Across the Four Frameworks
Phase | Week(s) | Lewin | ADKAR | Bridges | Kübler-Ross
Intake & Diagnosis | Weeks 1–7 | Unfreeze | Awareness | Ending | Denial
Clean-Slate Design | Weeks 5–8 | Unfreeze | Awareness | Ending | Denial
Build | Weeks 8–16 | Unfreeze → Change | Knowledge | Ending → Neutral Zone | Denial → Resistance/Anger
Pilot | Weeks 14–24 | Change | Knowledge → Ability | Neutral Zone | Resistance/Anger
Rollout | Weeks 22–32 | Change | Ability | Neutral Zone | Resistance/Anger → Exploration
Stabilization | Weeks 30–42 | Change | Ability | Neutral Zone | Exploration
Sustainment | Weeks 40–50 | Refreeze | Reinforcement | New Beginning | Commitment
journi — Business Process Redesign (Order-to-Cash Process Redesign)
35

## Slide 37
PART 4 — MASTER WBS & GANTT
Every Phase, Techniques and Tools
Phase | Week(s) | Technique | Goal | Tool
Intake & Diagnosis | Weeks 1–7 | Process-step root-cause mapping | Trace the three-week delay to specific manual workarounds, by step. | M4 (Stakeholder Mapping)
Clean-Slate Design | Weeks 5–8 | Clean-slate workshop | Design the new process without anchoring to today's workaround-shaped version. | M17 (WBS & Gantt)
Build | Weeks 8–16 | Bounded technical workaround design | Solve a legacy-system constraint without touching the legacy system directly. | M21 (Field Notes)
Pilot | Weeks 14–24 | Co-designed accuracy safeguard | Resolve resistance by building the mitigation with the resisting staff, not around them. | M10 (Resistance Log)
Rollout | Weeks 22–32 | Adoption-vs-resistance-log cross-check | Catch an informal resistance pattern that never becomes a formal log entry. | M5 (ADKAR Engine)
Stabilization | Weeks 30–42 | Reconciliation-time root-cause disaggregation | Separate a real partial shortfall from a hidden, addressable cause. | M14 (Analytics)
Sustainment | Weeks 40–50 | Decision-rationale handover | Preserve the *why* behind key design decisions, not just the *what*, through a leadership transition. | M21 (Field Notes)
journi — Business Process Redesign (Order-to-Cash Process Redesign)
36

## Slide 38
PART 4 — SIX EXCEPTIONS, IN DETAIL
Six Realistic Ways This Program Could Have Gone Differently
journi — Business Process Redesign (Order-to-Cash Process Redesign)
37

## Slide 39
E1 · PILOT, WEEKS 20–24
Resistance Escalation Threshold Breached
DESCRIPTION
Three AR staff, each defending the manual-control expertise the redesigned process removes, logged individually-coded resistance entries within a three-week window — ALT-004's exact condition.
TRIGGER
Three or more open resistance entries accumulated within journi's rolling window.
TIMELINE IMPACT
No Phase 4 gate delay — resolved within the same phase by Week 24.
RECOVERY TASKS
Direct, individual conversations with each of the three staff; a secondary accuracy-review safeguard co-designed with them, not imposed on them.
OUTPUTS: Three closed resistance entries; a co-designed accuracy safeguard folded into the standing rollout design. RACSI: R = CM · A = CM · C = FPO, SUP · S = PM · I = ES, EU
journi — Business Process Redesign (Order-to-Cash Process Redesign)
38

## Slide 40
E2 · ROLLOUT, WEEKS 26–28
A Workaround Champion Undermines the Process Informally
DESCRIPTION
A senior AR staff member who never logged a formal resistance entry quietly tells colleagues to keep a personal shadow spreadsheet "just in case," undermining adoption without ever surfacing as a trackable entry.
TRIGGER
Adoption metrics (M5 Ability) lag in a sub-team despite no open resistance entries there.
TIMELINE IMPACT
Roughly one week added to that sub-team's rollout confirmation.
RECOVERY TASKS
Investigate the adoption lag directly; identify the informal influence through conversation; convert the informal pattern into a formal, resolvable one.
OUTPUTS: A newly logged, then closed, resistance entry; a standing practice of cross-checking adoption metrics against the resistance log. RACSI: R = CM, SUP · A = CM · C = FPO · S = PM · I = ES, EU
journi — Business Process Redesign (Order-to-Cash Process Redesign)
39

## Slide 41
E3 · ROLLOUT–STABILIZATION, WEEKS 28–36
The Co-Designed Safeguard Slows AP More Than Expected
DESCRIPTION
The safeguard co-designed with AR's resisting staff was tested only against AR's volume; rolled out to AP's significantly higher volume, it adds more processing time than the redesign was meant to save.
TRIGGER
Reconciliation-time monitoring (M14) trends against the business case's own target, not toward it.
TIMELINE IMPACT
Extends Stabilization by two to three weeks while the safeguard is re-tuned for AP.
RECOVERY TASKS
Confirm the cost specifically in AP; redesign the trigger threshold for AP's volume rather than removing the safeguard; re-test before declaring Stabilization complete.
OUTPUTS: An AP-specific safeguard threshold; a documented reason the AR-tested design didn't generalize. RACSI: R = PM, FPO · A = CM · C = SUP · S = ITL · I = ES, EU
journi — Business Process Redesign (Order-to-Cash Process Redesign)
40

## Slide 42
E4 · BUILD, WEEKS 8–13
A Legacy System Constraint Blocks a Required Data Field
DESCRIPTION
The redesigned process requires a new data field (a credit-note reason code) the legacy finance system, still in use pending the separate ERP program's own migration, does not natively support.
TRIGGER
A build-phase technical constraint discovered when the new field's configuration is attempted.
TIMELINE IMPACT
Adds one to two weeks to Build while a bounded workaround is designed and validated.
RECOVERY TASKS
Confirm the constraint is real; design a bounded workaround that doesn't require touching the legacy system; validate it doesn't reintroduce a manual step.
OUTPUTS: A documented constraint and its bounded workaround. RACSI: R = ITL, PM · A = PM · C = CM · S = FPO · I = ES, SUP, EU
journi — Business Process Redesign (Order-to-Cash Process Redesign)
41

## Slide 43
E5 · STABILIZATION, WEEKS 34–42
Reconciliation-Time Reduction Stalls Below Target
DESCRIPTION
The business case targeted a reduction from three weeks to one; Stabilization's readings hold at two weeks — real progress, but short of target.
TRIGGER
Two consecutive monthly readings below the business-case target, without further improving trend.
TIMELINE IMPACT
Extends Stabilization by one monitoring cycle rather than close the gate on a partial result presented as full success.
RECOVERY TASKS
Disaggregate the remaining gap by root cause (largely E3's AP safeguard cost); decide explicitly whether to invest further or revise the target, documented either way.
OUTPUTS: A disaggregated root-cause finding; either a closed gap or an explicitly revised target. RACSI: R = CM, FPO · A = ES · C = PM · S = ITL · I = SUP, EU
journi — Business Process Redesign (Order-to-Cash Process Redesign)
42

## Slide 44
E6 · ROLLOUT, WEEKS 26–30
The Process Owner Departs Mid-Rollout
DESCRIPTION
Salwa Tazi, the Casablanca Finance Process Owner and the person who did the most direct co-design work with the pilot's resisting staff, accepts a role elsewhere mid-rollout.
TRIGGER
A confirmed departure notice from the named Functional Process Owner during an active phase.
TIMELINE IMPACT
Adds roughly two weeks to Rollout for a structured handover before departure.
RECOVERY TASKS
A structured handover capturing the *why* behind key design decisions; identify and onboard a successor before the departure, not after.
OUTPUTS: A documented decision-rationale handover; a successor Process Owner onboarded and RACSI-updated. RACSI: R = CM, FPO · A = ES · C = PM · S = SUP · I = ITL, EU
journi — Business Process Redesign (Order-to-Cash Process Redesign)
43

## Slide 45
PART 5 — TRAINING PROGRAM
What This Training Covers
Per the E2E-BPR chain, MP-05 is present — training here focuses on the redesigned process's specific new steps, not persuasion about why the redesign is needed (Kübler-Ross's Resistance/Anger stage, not Awareness, is this archetype's real barrier).
journi — Business Process Redesign (Order-to-Cash Process Redesign)
44

## Slide 46
PART 5 · TIER 1 OF 3
Strategic Management
Cohort: Karim Zniber (Sponsor), finance leadership · Weeks 1–4
Curriculum Entry | Content Focus
Sponsoring a Process Redesign Against Owned Workarounds | Why visible sponsorship matters most exactly when staff privately own what's being removed.
Reading a Resistance Log as Real Evidence | How to read three open entries as the system working, not failing.
journi — Business Process Redesign (Order-to-Cash Process Redesign)
45

## Slide 47
PART 5 · TIER 2 OF 3
Operational Management
Cohort: Salwa Tazi (FPO), Amina Sebti (SUP) · Weeks 4–14
Curriculum Entry | Content Focus
Operating the Redesigned Order-to-Cash Process | The specific new steps, forms, and approval chain, replacing the old workaround-shaped version.
Co-Designing a Recovery With Resisting Staff | The specific technique behind Exception E1's resolution.
journi — Business Process Redesign (Order-to-Cash Process Redesign)
46

## Slide 48
PART 5 · TIER 3 OF 3
Operations (Frontline)
Cohort: All 140 AR and AP staff · Weeks 12–28
Curriculum Entry | Content Focus
Using the New Process, Step by Step | Practical training on the redesigned process, delivered ahead of each rollout wave.
The New Accuracy Safeguard, By Volume | AR-specific and later AP-specific versions of the same safeguard.
journi — Business Process Redesign (Order-to-Cash Process Redesign)
47

## Slide 49
PART 5 — TRAINING PROGRAM
Why This Curriculum Is Shaped This Way
Training completion here is necessary but not sufficient — Exception E2 shows a fully trained cohort can still undermine adoption informally, which is why the resistance log, not the training-completion rate, is this archetype's real leading indicator.
journi — Business Process Redesign (Order-to-Cash Process Redesign)
48

## Slide 50
CROSS-REFERENCE
Which journi Modules Dominate This Archetype
M10 (Resistance Log)
The archetype's most-watched module — 3+ open entries fires ALT-004.
M4 (Stakeholder Mapping)
Identifies exactly whose workaround is being redesigned away, by name.
M17 (WBS & Gantt)
The TPL-BPR-7 template — Clean-Slate Design is this archetype's defining phase.
M21 (Field Notes)
Captures the specific, named fear or rationale behind a resistance entry or handover.
M14 (Analytics)
Reconciliation-time trend monitoring against the business case's own target.
M5 (ADKAR Engine)
Cross-checked against the resistance log to catch informal, untracked resistance.
journi — Business Process Redesign (Order-to-Cash Process Redesign)
49

## Slide 51
ALERTS & PROOF
What This Case Fires
ALERTS THIS CASE EXERCISES
ALT-004 (Resistance Escalation Threshold Breached)
WHY
Built deliberately to cross the resistance-escalation threshold — the defining alert of this archetype.
journi — Business Process Redesign (Order-to-Cash Process Redesign)
50

## Slide 52
KEY TAKEAWAYS
What to Remember About This Archetype
› A real ALT-004 firing at Week 20–24, resolved through a co-designed accuracy safeguard the resisting staff themselves helped define — and five further exceptions showing exactly how a redesign can go sideways even after the headline resistance risk is handled.
› Kübler-Ross dominates. Staff who privately own today's workarounds resist a redesign that makes those workarounds obsolete — the Resistance/Anger stage, and the Resistance Log (M10) that feeds it, is this archetype's central risk, more than any specific skill gap ADKAR would otherwise catch first.
› Built deliberately to cross the resistance-escalation threshold — the defining alert of this archetype.
journi — Business Process Redesign (Order-to-Cash Process Redesign)
51

## Slide 53
Business Process Redesign
Order-to-Cash Process Redesign
Manufacturing Sector · Bouregreg Group Scenario Library · Confidential