## Slide 1
Compliance-Driven Change
Loi 09-08 Data Protection Compliance Program
Bringing data handling into compliance with a fixed external deadline — the case where a Phase Gate closing as anything but Go has zero schedule slack to absorb it.
7
PHASES
64
WEEKS
6
EXCEPTIONS
3
TRAINING TIERS
Manufacturing Sector · Bouregreg Group Scenario Library · Confidential

## Slide 2
PART 0 — PURPOSE
What This Guide Is, and How to Use It
WHAT THIS GUIDE IS
This deck follows the Loi 09-08 Data Protection Compliance Program — journi's Compliance-Driven Change archetype case — from tenant setup through ongoing compliance handover, bringing Bouregreg Group's data handling into compliance with a fixed CNDP audit deadline.
HOW TO USE IT
This program runs inside the same Bouregreg Group tenant as every other archetype in this series, from the very start of the tenant's life given the fixed external deadline. A reader with the tenant already set up skips straight to CM Project creation.
journi — Compliance-Driven Change (Loi 09-08 Data Protection Compliance Program)
01

## Slide 3
PART 0 — A NOTE ON FIDELITY
Verified Against journi's Real Source
Every journi module, field, and role named here is verified against journi's real source. This is journi's own stated case where ALT-009 (Phase Gate No-Go/Conditional) matters most precisely because it does not fire — every Phase Gate in this program's real record closes Go, on schedule.
RACSI CODES USED THROUGHOUT
ES = Executive Sponsor · CM = Change Manager · PM = Program/Project Manager · FPO = Functional Process Owner · ITL = IT/Technical Lead · SUP = Supervisor · EU = End User
journi — Compliance-Driven Change (Loi 09-08 Data Protection Compliance Program)
02

## Slide 4
PART 1 — EXECUTIVE SUMMARY
Why This Case Matters
Every other program in this series can, in principle, slip a phase gate by a few weeks without an external consequence. This one cannot — the CNDP's own audit schedule is fixed and external, and there is no schedule buffer to absorb a Conditional or No-Go decision without missing a regulatory deadline.
journi — Compliance-Driven Change (Loi 09-08 Data Protection Compliance Program)
03

## Slide 5
PART 1 — EXECUTIVE SUMMARY
The Case, in Brief
310 staff, HR, Sales, Customer Service
64 weeks (guide numbering, org-calendar aligned)
Bouregreg Group brings customer and employee personal-data handling into compliance with Loi 09-08, under CNDP oversight, for HR, Sales, and Customer Service (310 staff), closing every phase gate on schedule with controls live weeks ahead of the ERP program's own Deploy week.
journi — Compliance-Driven Change (Loi 09-08 Data Protection Compliance Program)
04

## Slide 6
PART 1 — EXECUTIVE SUMMARY
What This Guide Proves, Concretely
Seven consecutive clean Phase Gate decisions, a controls-go-live date sequenced deliberately ahead of a sibling program's own critical week, and a first monitoring cycle confirming the controls hold under real operating conditions, not just at go-live.
journi — Compliance-Driven Change (Loi 09-08 Data Protection Compliance Program)
05

## Slide 7
PART 2 — THE FOUR FRAMEWORKS
Weighting for This Archetype
Awareness and Ability dominate; Desire matters least of any archetype. Staff do not need to want to comply — they need to know the rule and be able to follow it correctly. The Phase Gate itself is the framework that matters most, since the real risk here is schedule risk, not adoption risk.
journi — Compliance-Driven Change (Loi 09-08 Data Protection Compliance Program)
06

## Slide 8
PART 2 — THE FOUR FRAMEWORKS
The Composite Readiness Index, Read for This Case
The Composite Readiness Index reads high and stable throughout — Knowledge and Ability both clear quickly against specific, checkable rules, and there is no real emotional undercurrent for Bridges or Kübler-Ross to track. Benchmarking reads "In Line" or "Ahead" for the program's whole life.
journi — Compliance-Driven Change (Loi 09-08 Data Protection Compliance Program)
07

## Slide 9
PART 3 — TENANT AND ADMIN SETUP
The Existing Tenant, and Reading Paths by Role
THE EXISTING TENANT
This program runs inside the same tenant journi's Master User Guide builds, under the existing Bouregreg Manufacturing Maroc Organization — no new Organization needed.
READING PATHS, BY ROLE
› A Change Manager running this program day to day: Part 2 once, then Part 4 in full.
› A Program/Project Manager: Part 4's PM Track column and the Master WBS & Gantt.
› An Executive Sponsor: Part 1, then Part 4's phase-opening narratives.
› A Super Admin or Org Admin: Part 3.
journi — Compliance-Driven Change (Loi 09-08 Data Protection Compliance Program)
08

## Slide 10
PART 3 — TENANT AND ADMIN SETUP
The RACSI Team for This Program
Name | RACSI Code | Role
Karim Idrissi | ES | Sponsor — General Counsel/Chief Compliance Officer
Sanaa Bouzoubaa | CM | Change Manager
Hamza Alaoui | PM | Compliance Program Lead
Nadia Squalli | FPO | HR Data Privacy Lead
Reda Fassi | ITL | Data systems and access-control lead
Amine Tazi | SUP | Sales Operations Manager
journi — Compliance-Driven Change (Loi 09-08 Data Protection Compliance Program)
09

## Slide 11
PART 3 — TENANT AND ADMIN SETUP
Creating the CM Project
1
On Module 1 — Hierarchy, create the Loi 09-08 Data Protection Compliance Program CM Project under the existing Bouregreg Manufacturing Maroc Organization.
2
Set Change type: Compliance. Target population: "Any function touching personal data — HR, Sales, Customer Service (310)." Business driver: "A scheduled CNDP audit against Loi 09-08 carries a fixed external deadline, not a discretionary program timeline."
3
Save. Lewin opens at Unfreeze, justified: "Opening Unfreeze at program start, Week 1, run from the very start of the tenant's life given the fixed external deadline."
4
On Module 17 — WBS & Gantt, load the TPL-COMP-7 phase template: Regulatory Requirement & Gap Analysis, Control Design, Control Implementation, Internal Audit/Independent Testing, Controls Go Live, First Monitoring Cycle, Ongoing Compliance Handover.
journi — Compliance-Driven Change (Loi 09-08 Data Protection Compliance Program)
10

## Slide 12
PART 3 — TENANT AND ADMIN SETUP
Charters for This Program
Charter | Accountable | Review Cadence
CHTR-01 Sponsorship / Leadership Charter | Karim Idrissi (ES) | Per Phase Gate
CHTR-03 Communication Charter | Sanaa Bouzoubaa (CM) | Per communication wave
CHTR-04 Organizational Impact Charter | Sanaa Bouzoubaa (CM) | On scope change
CHTR-08 Pulse / Interview Charter | Sanaa Bouzoubaa (CM) | Per phase gate + ad hoc
journi — Compliance-Driven Change (Loi 09-08 Data Protection Compliance Program)
11

## Slide 13
PART 3 — TENANT AND ADMIN SETUP
Setup Checklist
Base tenant confirmed (Bouregreg Group, existing Organization)
Compliance team accounts created
CM Project created, Lewin opened at Unfreeze
TPL-COMP-7 phase template loaded on M17
Applicable Charters reviewed and accountable owners confirmed
journi — Compliance-Driven Change (Loi 09-08 Data Protection Compliance Program)
12

## Slide 14
PART 4 — WEEK-BY-WEEK TIMELINE
7 Phases, In Order
1. Regulatory Requirement & Gap Analysis
2. Control Design
3. Control Implementation
4. Internal Audit / Independent Testing
5. Controls Go Live
6. First Monitoring Cycle
7. Ongoing Compliance Handover
Total program length: 64 weeks (guide numbering, org-calendar aligned). Every phase below is walked in detail across the next slides — normal flow first, then six exceptions in full operational detail.
journi — Compliance-Driven Change (Loi 09-08 Data Protection Compliance Program)
13

## Slide 15
PHASE 1 OF 7
Regulatory Requirement & Gap Analysis
Weeks 1–14
NARRATIVE
Establishes exactly what Loi 09-08 requires and where current data-handling practice falls short, across HR, Sales, and Customer Service.
journi — Compliance-Driven Change (Loi 09-08 Data Protection Compliance Program)
14

## Slide 16
PHASE 1 · REGULATORY REQUIREMENT & GAP ANALYSIS
Key Moments in This Phase
Week | What Happens
Week 1 | Kickoff; Lewin opens at Unfreeze.
Week 5 | Gap analysis begins across all three functions.
Week 14 | Phase Gate: clean Go.
journi — Compliance-Driven Change (Loi 09-08 Data Protection Compliance Program)
15

## Slide 17
PHASE 1 · REGULATORY REQUIREMENT & GAP ANALYSIS
Framework Snapshot
LEWIN
Unfreeze
ADKAR
Awareness
BRIDGES
Neutral Zone
KÜBLER-ROSS
Exploration
KEY TECHNIQUE THIS PHASE
Statutory clause mapping: Map every Loi 09-08 article to a specific business process it governs.
journi — Compliance-Driven Change (Loi 09-08 Data Protection Compliance Program)
16

## Slide 18
PHASE 2 OF 7
Control Design
Weeks 12–28
NARRATIVE
Designs the specific controls — retention rules, access restrictions, subject-access-request processes — that close the gaps found.
journi — Compliance-Driven Change (Loi 09-08 Data Protection Compliance Program)
17

## Slide 19
PHASE 2 · CONTROL DESIGN
Key Moments in This Phase
Week | What Happens
Week 15 | Retention controls designed for HR personnel records.
Week 19 | Subject-access-request process designed.
Week 28 | Phase Gate: clean Go.
journi — Compliance-Driven Change (Loi 09-08 Data Protection Compliance Program)
18

## Slide 20
PHASE 2 · CONTROL DESIGN
Framework Snapshot
LEWIN
Unfreeze
ADKAR
Awareness → Knowledge
BRIDGES
Neutral Zone
KÜBLER-ROSS
Exploration
KEY TECHNIQUE THIS PHASE
Control catalogue design: Design specific, checkable controls closing each identified gap.
journi — Compliance-Driven Change (Loi 09-08 Data Protection Compliance Program)
19

## Slide 21
PHASE 3 OF 7
Control Implementation
Weeks 26–40
NARRATIVE
Implements the designed controls plant-wide across all three functions.
journi — Compliance-Driven Change (Loi 09-08 Data Protection Compliance Program)
20

## Slide 22
PHASE 3 · CONTROL IMPLEMENTATION
Key Moments in This Phase
Week | What Happens
Week 30 | Access-restriction controls implemented across HR, Sales, CS.
Week 36 | Retention schedules operational.
Week 40 | Phase Gate: clean Go.
journi — Compliance-Driven Change (Loi 09-08 Data Protection Compliance Program)
21

## Slide 23
PHASE 3 · CONTROL IMPLEMENTATION
Framework Snapshot
LEWIN
Change
ADKAR
Knowledge → Ability
BRIDGES
Neutral Zone
KÜBLER-ROSS
Exploration
KEY TECHNIQUE THIS PHASE
Function-by-function rollout: Implement controls across HR, Sales, and Customer Service without disrupting daily operations.
journi — Compliance-Driven Change (Loi 09-08 Data Protection Compliance Program)
22

## Slide 24
PHASE 4 OF 7
Internal Audit / Independent Testing
Weeks 38–48
NARRATIVE
Independently tests the implemented controls before go-live — journi's own independence discipline is the point.
journi — Compliance-Driven Change (Loi 09-08 Data Protection Compliance Program)
23

## Slide 25
PHASE 4 · INTERNAL AUDIT / INDEPENDENT TESTING
Key Moments in This Phase
Week | What Happens
Week 42 | Independent testing team confirmed genuinely independent of implementation.
Week 46 | Testing findings closed.
Week 48 | Phase Gate: clean Go.
journi — Compliance-Driven Change (Loi 09-08 Data Protection Compliance Program)
24

## Slide 26
PHASE 4 · INTERNAL AUDIT / INDEPENDENT TESTING
Framework Snapshot
LEWIN
Change
ADKAR
Ability
BRIDGES
Neutral Zone
KÜBLER-ROSS
Exploration
KEY TECHNIQUE THIS PHASE
Independence-verified testing: Confirm controls work, tested by a team genuinely independent of implementation.
journi — Compliance-Driven Change (Loi 09-08 Data Protection Compliance Program)
25

## Slide 27
PHASE 5 OF 7
Controls Go Live
Weeks 46–52
NARRATIVE
Goes live with the tested controls, timed deliberately ahead of the ERP program's own Deploy week so the two never compete for the same Legal/Compliance attention.
journi — Compliance-Driven Change (Loi 09-08 Data Protection Compliance Program)
26

## Slide 28
PHASE 5 · CONTROLS GO LIVE
Key Moments in This Phase
Week | What Happens
Week 48 | Controls go live across all three functions.
Week 52 | Phase Gate: clean Go.
journi — Compliance-Driven Change (Loi 09-08 Data Protection Compliance Program)
27

## Slide 29
PHASE 5 · CONTROLS GO LIVE
Framework Snapshot
LEWIN
Change
ADKAR
Ability
BRIDGES
Neutral Zone → New Beginning
KÜBLER-ROSS
Exploration → Commitment
KEY TECHNIQUE THIS PHASE
Deliberately sequenced go-live: Time go-live ahead of the ERP program's own Deploy week to avoid competing for Legal/Compliance attention.
journi — Compliance-Driven Change (Loi 09-08 Data Protection Compliance Program)
28

## Slide 30
PHASE 6 OF 7
First Monitoring Cycle
Weeks 50–58
NARRATIVE
Confirms the controls hold under real operating conditions, not just at the moment of go-live.
journi — Compliance-Driven Change (Loi 09-08 Data Protection Compliance Program)
29

## Slide 31
PHASE 6 · FIRST MONITORING CYCLE
Key Moments in This Phase
Week | What Happens
Week 52 | First monitoring cycle begins.
Week 58 | Phase Gate: clean Go — seventh consecutive clean gate.
journi — Compliance-Driven Change (Loi 09-08 Data Protection Compliance Program)
30

## Slide 32
PHASE 6 · FIRST MONITORING CYCLE
Framework Snapshot
LEWIN
Change → Refreeze
ADKAR
Ability → Reinforcement
BRIDGES
New Beginning
KÜBLER-ROSS
Commitment
KEY TECHNIQUE THIS PHASE
Real-condition control monitoring: Confirm controls hold under real operating conditions, not just at go-live.
journi — Compliance-Driven Change (Loi 09-08 Data Protection Compliance Program)
31

## Slide 33
PHASE 7 OF 7
Ongoing Compliance Handover
Weeks 56–64, open-ended beyond
NARRATIVE
Hands ongoing compliance monitoring to standing operations — continuing beyond Week 64 since a regulatory obligation has no project end date.
journi — Compliance-Driven Change (Loi 09-08 Data Protection Compliance Program)
32

## Slide 34
PHASE 7 · ONGOING COMPLIANCE HANDOVER
Key Moments in This Phase
Week | What Happens
Week 60 | Ongoing handover package delivered.
Week 64 | Program formally closes; compliance monitoring continues beyond, by design.
journi — Compliance-Driven Change (Loi 09-08 Data Protection Compliance Program)
33

## Slide 35
PHASE 7 · ONGOING COMPLIANCE HANDOVER
Framework Snapshot
LEWIN
Refreeze (standing)
ADKAR
Reinforcement
BRIDGES
New Beginning
KÜBLER-ROSS
Commitment
KEY TECHNIQUE THIS PHASE
Standing compliance monitoring handoff: Transfer ongoing monitoring to standing operations, since the obligation has no end date.
journi — Compliance-Driven Change (Loi 09-08 Data Protection Compliance Program)
34

## Slide 36
PART 4 — MASTER WBS & GANTT
Every Phase, Across the Four Frameworks
Phase | Week(s) | Lewin | ADKAR | Bridges | Kübler-Ross
Regulatory Requirement & Gap Analysis | Weeks 1–14 | Unfreeze | Awareness | Neutral Zone | Exploration
Control Design | Weeks 12–28 | Unfreeze | Awareness → Knowledge | Neutral Zone | Exploration
Control Implementation | Weeks 26–40 | Change | Knowledge → Ability | Neutral Zone | Exploration
Internal Audit / Independent Testing | Weeks 38–48 | Change | Ability | Neutral Zone | Exploration
Controls Go Live | Weeks 46–52 | Change | Ability | Neutral Zone → New Beginning | Exploration → Commitment
First Monitoring Cycle | Weeks 50–58 | Change → Refreeze | Ability → Reinforcement | New Beginning | Commitment
Ongoing Compliance Handover | Weeks 56–64+ | Refreeze (standing) | Reinforcement | New Beginning | Commitment
journi — Compliance-Driven Change (Loi 09-08 Data Protection Compliance Program)
35

## Slide 37
PART 4 — MASTER WBS & GANTT
Every Phase, Techniques and Tools
Phase | Week(s) | Technique | Goal | Tool
Regulatory Requirement & Gap Analysis | Weeks 1–14 | Statutory clause mapping | Map every Loi 09-08 article to a specific business process it governs. | LibreOffice Calc
Control Design | Weeks 12–28 | Control catalogue design | Design specific, checkable controls closing each identified gap. | M21 (Field Notes)
Control Implementation | Weeks 26–40 | Function-by-function rollout | Implement controls across HR, Sales, and Customer Service without disrupting daily operations. | M17 (WBS & Gantt)
Internal Audit / Independent Testing | Weeks 38–48 | Independence-verified testing | Confirm controls work, tested by a team genuinely independent of implementation. | M19 (Charter Registry)
Controls Go Live | Weeks 46–52 | Deliberately sequenced go-live | Time go-live ahead of the ERP program's own Deploy week to avoid competing for Legal/Compliance attention. | M3 (Initiative Registry)
First Monitoring Cycle | Weeks 50–58 | Real-condition control monitoring | Confirm controls hold under real operating conditions, not just at go-live. | M12 (Sustainment)
Ongoing Compliance Handover | Weeks 56–64+ | Standing compliance monitoring handoff | Transfer ongoing monitoring to standing operations, since the obligation has no end date. | M12 (Sustainment)
journi — Compliance-Driven Change (Loi 09-08 Data Protection Compliance Program)
36

## Slide 38
PART 4 — SIX EXCEPTIONS, IN DETAIL
Six Realistic Contingencies — None of Which Actually Occurred
journi — Compliance-Driven Change (Loi 09-08 Data Protection Compliance Program)
37

## Slide 39
C1 · REGULATORY REQUIREMENT & GAP ANALYSIS, WEEKS 5–14
A Regulatory Clause Misread During Gap Analysis
DESCRIPTION
The gap analysis initially reads a Loi 09-08 retention-period clause more leniently than the CNDP's own published guidance actually requires — a misreading that would only surface when Legal's own independent review catches it late in Phase 1. This did not occur.
TRIGGER
Legal's independent review of the gap analysis catching a clause misreading.
TIMELINE IMPACT
Would extend Phase 1 by one to two weeks while the retention-period control is redesigned against the correct reading.
RECOVERY TASKS
Legal independently re-verifies every retention-period clause reading before Phase 1 closes.
OUTPUTS: A corrected, Legal-verified gap analysis. RACSI: R = CM, ES · A = ES · C = FPO · S = PM · I = ITL, SUP, EU
journi — Compliance-Driven Change (Loi 09-08 Data Protection Compliance Program)
38

## Slide 40
C2 · CONTROL DESIGN, WEEKS 15–23
Control Design Insufficient for a Specific Data Type
DESCRIPTION
The general control catalogue, designed for standard HR and customer data, turns out insufficient for health-related data HR holds for occupational-medicine purposes — which Loi 09-08 treats more strictly. This did not occur.
TRIGGER
A specific data category found to need stricter controls than the general catalogue provides.
TIMELINE IMPACT
Would add a targeted control-design cycle for the specific data type, roughly one to two weeks.
RECOVERY TASKS
Design a stricter, data-type-specific control layer on top of the general catalogue.
OUTPUTS: A data-type-specific control addendum. RACSI: R = FPO, ITL · A = CM · C = ES · S = PM · I = SUP, EU
journi — Compliance-Driven Change (Loi 09-08 Data Protection Compliance Program)
39

## Slide 41
C3 · REQUIREMENT ANALYSIS–CONTROL DESIGN, WEEKS 5–20
A Third-Party Data Processor Missed From Scope
DESCRIPTION
A payroll vendor processing HR personal data on Bouregreg's behalf is missed from the original scope, discovered only when the control catalogue's access-restriction design realizes it has no way to govern a third party's own systems. This did not occur.
TRIGGER
A scope review discovering a third-party processor with no governing control.
TIMELINE IMPACT
Would require a vendor-compliance addendum, adding two to three weeks.
RECOVERY TASKS
Extend the control catalogue to cover third-party processor governance via contractual and technical controls.
OUTPUTS: A vendor-compliance control addendum. RACSI: R = ES, ITL · A = ES · C = CM · S = PM · I = FPO, SUP, EU
journi — Compliance-Driven Change (Loi 09-08 Data Protection Compliance Program)
40

## Slide 42
C4 · INTERNAL AUDIT / INDEPENDENT TESTING, WEEKS 40–45
The Independent Testing Team Isn't Genuinely Independent
DESCRIPTION
A staff member assigned to the "independent" testing team turns out to have also done configuration work on one of the controls being tested — a genuine independence failure. This did not occur.
TRIGGER
A conflict-of-interest review finding testing-team overlap with implementation.
TIMELINE IMPACT
Would require reassigning the affected control's testing, adding roughly one week.
RECOVERY TASKS
Reassign the specific control's testing to a genuinely independent reviewer.
OUTPUTS: A verified, genuinely independent test result. RACSI: R = CM · A = CM · C = ES · S = PM · I = FPO, ITL, SUP, EU
journi — Compliance-Driven Change (Loi 09-08 Data Protection Compliance Program)
41

## Slide 43
C5 · CONTROL IMPLEMENTATION, WEEKS 26–37
A Data Incident During Implementation, Before Controls Are Live
DESCRIPTION
A data-handling incident occurs while implementation is still in progress and the new controls aren't live yet, forcing an unplanned test of whether the incident-response process works before it was scheduled to be tested. This did not occur.
TRIGGER
A reportable data-handling incident during Control Implementation.
TIMELINE IMPACT
Would not delay the schedule directly, but would force an immediate, out-of-cycle incident response.
RECOVERY TASKS
Run the incident response using whatever process exists at that point; accelerate the specific control that would have prevented the incident.
OUTPUTS: A documented incident response; an accelerated control fix. RACSI: R = ITL, FPO · A = ES · C = CM · S = PM · I = SUP, EU
journi — Compliance-Driven Change (Loi 09-08 Data Protection Compliance Program)
42

## Slide 44
C6 · ANY PHASE, WEEKS 1–64
CNDP Shifts the Audit Date or Scope Mid-Program
DESCRIPTION
The CNDP itself moves the audit date earlier, or expands its stated scope, partway through the program — an external schedule shock this program's own design has no control over. This did not occur.
TRIGGER
A formal CNDP notice changing the audit date or scope.
TIMELINE IMPACT
Would force compressing every remaining phase proportionally — the single hardest scenario in the contingency list.
RECOVERY TASKS
Immediately re-baseline the WBS against the new date; escalate to the Sponsor and Steering Committee for an explicit prioritization decision.
OUTPUTS: A re-baselined schedule; a documented prioritization decision if full scope cannot be met. RACSI: R = PM, CM · A = ES · C = FPO, ITL · S = SUP · I = EU
journi — Compliance-Driven Change (Loi 09-08 Data Protection Compliance Program)
43

## Slide 45
PART 5 — TRAINING PROGRAM
What This Training Covers
Per the E2E-COMP chain, MP-05 is present — but unlike the Cultural archetype's persuasion-heavy curriculum, this training is built entirely around specific, checkable compliance behaviors, verifiable against the same control checklist independent testers use.
journi — Compliance-Driven Change (Loi 09-08 Data Protection Compliance Program)
44

## Slide 46
PART 5 · TIER 1 OF 3
Strategic Management
Cohort: Karim Idrissi (Sponsor), function heads · Weeks 1–16
Curriculum Entry | Content Focus
Sponsoring a Fixed-Deadline Compliance Program | Why a CNDP-facing program cannot treat its own schedule as negotiable.
Reading a Phase Gate Decision Record | How to read Go/Conditional/No-Go as accountable evidence.
journi — Compliance-Driven Change (Loi 09-08 Data Protection Compliance Program)
45

## Slide 47
PART 5 · TIER 2 OF 3
Operational Management
Cohort: Nadia Squalli (FPO), Amine Tazi (SUP), CS data-privacy coordinator · Weeks 14–52
Curriculum Entry | Content Focus
Operating the Control Design Checklist | Consent capture, data minimization, and retention limits as specific, checkable steps.
Preparing a Function for Independent Testing | What testers actually check, and how to have evidence ready.
Running the First Monitoring Cycle | Keeping the checklist live after go-live, not just at the moment of testing.
journi — Compliance-Driven Change (Loi 09-08 Data Protection Compliance Program)
46

## Slide 48
PART 5 · TIER 3 OF 3
Operations (Frontline)
Cohort: All 310 HR, Sales, and Customer Service staff · Weeks 40–52
Curriculum Entry | Content Focus
Handling a Data Subject Access Request | The specific, checkable steps for responding within the legally required window.
Data Minimization in Daily Sales and CRM Entry | Exactly what personal-data fields are and are not to be captured.
Recognizing and Reporting a Suspected Data Incident | A specific action sequence, rehearsed, not a general "be careful" message.
Retention Schedule Compliance | Specific retention periods and deletion triggers per data category.
journi — Compliance-Driven Change (Loi 09-08 Data Protection Compliance Program)
47

## Slide 49
PART 5 — TRAINING PROGRAM
Why This Curriculum Is Shaped This Way
Training completion here is a direct, auditable input to the same evidence package CNDP itself may review — unlike every other guide in this series, this program carries no coaching or reinforcement track of its own, because a compliance behavior either happened correctly or it did not.
journi — Compliance-Driven Change (Loi 09-08 Data Protection Compliance Program)
48

## Slide 50
CROSS-REFERENCE
Which journi Modules Dominate This Archetype
M17 (WBS & Gantt)
The TPL-COMP-7 template — every phase gate dated against a fixed external deadline.
M5 (ADKAR Engine)
Awareness and Ability scored against specific, checkable rules — not general sentiment.
M19 (Charter Registry)
Formal charters matter more here given the external regulator relationship.
M9 (Training)
Checkable-behavior training — data handling, retention, access requests — not persuasion.
M12 (Sustainment)
The First Monitoring Cycle — the direct mechanism behind seven consecutive clean gates.
M3 (Initiative Registry)
A deliberately sequenced go-live date, timed against a sibling program's own critical week.
journi — Compliance-Driven Change (Loi 09-08 Data Protection Compliance Program)
49

## Slide 51
ALERTS & PROOF
What This Case Proves By Not Firing
NO LIVE ALERT FIRES IN THIS PROGRAM'S REAL RECORD
Stated plainly, not manufactured — a clean record reported as a clean record.
WHY
None fire in this program's real record — every Phase Gate closes Go, on schedule, which is the entire point: ALT-009 (Phase Gate No-Go/Conditional) matters most here precisely because it does not fire.
journi — Compliance-Driven Change (Loi 09-08 Data Protection Compliance Program)
50

## Slide 52
KEY TAKEAWAYS
What to Remember About This Archetype
› Seven consecutive clean Phase Gate decisions, a controls-go-live date sequenced deliberately ahead of a sibling program's own critical week, and a first monitoring cycle confirming the controls hold under real operating conditions, not just at go-live.
› Awareness and Ability dominate; Desire matters least of any archetype. Staff do not need to want to comply — they need to know the rule and be able to follow it correctly. The Phase Gate itself is the framework that matters most, since the real risk here is schedule risk, not adoption risk.
› None fire in this program's real record — every Phase Gate closes Go, on schedule, which is the entire point: ALT-009 (Phase Gate No-Go/Conditional) matters most here precisely because it does not fire.
journi — Compliance-Driven Change (Loi 09-08 Data Protection Compliance Program)
51

## Slide 53
Compliance-Driven Change
Loi 09-08 Data Protection Compliance Program
Manufacturing Sector · Bouregreg Group Scenario Library · Confidential