## Slide 1
Cultural / Values Transformation
One Bouregreg: Post-Acquisition Culture Integration
Aligning two distinct ways of working under one set of values after an acquisition — not a system or process change at all.
7
PHASES
78
WEEKS
6
EXCEPTIONS
3
TRAINING TIERS
Manufacturing Sector · Bouregreg Group Scenario Library · Confidential

## Slide 2
PART 0 — PURPOSE
What This Guide Is, and How to Use It
WHAT THIS GUIDE IS
This deck follows One Bouregreg: Post-Acquisition Culture Integration — journi's Cultural/Values Transformation archetype case — from tenant setup through institutionalization, aligning two distinct ways of working under one set of values after an acquisition.
HOW TO USE IT
This program runs inside the same Bouregreg Group tenant as every other archetype in this series, six months into the ERP program's own life. A reader with the tenant already set up skips straight to CM Project creation.
journi — Cultural / Values Transformation (One Bouregreg: Post-Acquisition Culture Integration)
01

## Slide 3
PART 0 — A NOTE ON FIDELITY
Verified Against journi's Real Source
Every journi module, field, and role named here is verified against journi's real source. This is journi's own stated case for ALT-003 (Sponsor Coverage Gap) — this deck shows exactly how a newly appointed Sponsor's slow start fires the alert and is corrected.
RACSI CODES USED THROUGHOUT
ES = Executive Sponsor · CM = Change Manager · PM = Program/Project Manager · FPO = Functional Process Owner · ITL = IT/Technical Lead · SUP = Supervisor · EU = End User
journi — Cultural / Values Transformation (One Bouregreg: Post-Acquisition Culture Integration)
02

## Slide 4
PART 1 — EXECUTIVE SUMMARY
Why This Case Matters
A newly appointed Sponsor with zero logged actions damages Bridges and Kübler-Ross — this archetype's dominant frameworks — faster than any other, because a cultural program's central evidence is leadership visibility, not a training-completion metric.
journi — Cultural / Values Transformation (One Bouregreg: Post-Acquisition Culture Integration)
03

## Slide 5
PART 1 — EXECUTIVE SUMMARY
The Case, in Brief
260 staff (acquired Tangier team) + Bouregreg counterparts
78 weeks (guide numbering, 18-month horizon)
Six months into the ERP program, Bouregreg Group acquires a smaller regional competitor's Tangier distribution operation; this project aligns two distinct ways of working under one set of values within an 18-month horizon, targeting the acquired Tangier team plus their new Bouregreg counterparts.
journi — Cultural / Values Transformation (One Bouregreg: Post-Acquisition Culture Integration)
04

## Slide 6
PART 1 — EXECUTIVE SUMMARY
What This Guide Proves, Concretely
A real Sponsor Coverage Gap that fires and is corrected, a real Desire stall traced to a named, acquisition-specific fear, and a Refreeze signed only once the evidence — not the acquisition's own press-release timeline — supports it.
journi — Cultural / Values Transformation (One Bouregreg: Post-Acquisition Culture Integration)
05

## Slide 7
PART 2 — THE FOUR FRAMEWORKS
Weighting for This Archetype
Bridges and Kübler-Ross dominate. Identity and emotional integration matter more than any specific skill here — a newly appointed Sponsor with zero logged actions damages exactly these two frameworks fastest, which is why this archetype is built to fire ALT-003 early rather than later.
journi — Cultural / Values Transformation (One Bouregreg: Post-Acquisition Culture Integration)
06

## Slide 8
PART 2 — THE FOUR FRAMEWORKS
The Composite Readiness Index, Read for This Case
The Composite Readiness Index's training-completion term rises well ahead of its Bridges/Kübler-Ross-driven cultural terms from Week 35 onward — a deliberate, predicted gap: a high training-completion reading confirms staff can use shared systems, not that the four target values have taken hold.
journi — Cultural / Values Transformation (One Bouregreg: Post-Acquisition Culture Integration)
07

## Slide 9
PART 3 — TENANT AND ADMIN SETUP
The Existing Tenant, and Reading Paths by Role
THE EXISTING TENANT
This program runs inside the same tenant journi's Master User Guide builds, under the existing Bouregreg Manufacturing Maroc Organization — no new Organization needed.
READING PATHS, BY ROLE
› A Change Manager running this program day to day: Part 2 once, then Part 4 in full.
› A Program/Project Manager: Part 4's PM Track column and the Master WBS & Gantt.
› An Executive Sponsor: Part 1, then Part 4's phase-opening narratives.
› A Super Admin or Org Admin: Part 3.
journi — Cultural / Values Transformation (One Bouregreg: Post-Acquisition Culture Integration)
08

## Slide 10
PART 3 — TENANT AND ADMIN SETUP
The RACSI Team for This Program
Name | RACSI Code | Role
Karim Fassi | ES | Sponsor — newly appointed integration Sponsor
Nadia Chraibi | CM | Change Manager
Youssef Idrissi | PM | Integration Program Manager
Amal Ziani | FPO | HR Business Partner for the integration
Hicham Bennani | ITL | Systems/tooling lead
Fatima-Zahra Idrissi | SUP | Tangier Distribution Center site lead
Rachid Amrani | SUP | Casablanca supply chain/logistics lead
journi — Cultural / Values Transformation (One Bouregreg: Post-Acquisition Culture Integration)
09

## Slide 11
PART 3 — TENANT AND ADMIN SETUP
Creating the CM Project
1
On Module 1 — Hierarchy, create the One Bouregreg: Culture Integration CM Project under the existing Bouregreg Manufacturing Maroc Organization — no new tenant needed, despite the acquisition.
2
Set Change type: Cultural / Values Transformation. Target population: "Acquired Tangier team (260) plus Bouregreg counterparts." Business driver: "The acquisition's stated synergies depend on the two workforces actually operating as one company within 18 months."
3
Save. Lewin opens at Unfreeze, justified against the acquisition's own closing date, six months into the ERP program's own life.
4
On Module 17 — WBS & Gantt, load the TPL-CULT-7 phase template: Diagnosis, Target Values Design, Leadership Modeling & Reinforcement Build, Pilot Cohort, Organization-Wide Rollout, Reinforcement Through Skepticism, Institutionalization.
journi — Cultural / Values Transformation (One Bouregreg: Post-Acquisition Culture Integration)
10

## Slide 12
PART 3 — TENANT AND ADMIN SETUP
Charters for This Program
Charter | Accountable | Review Cadence
CHTR-01 Sponsorship / Leadership Charter | Karim Fassi (ES) | Per Phase Gate
CHTR-03 Communication Charter | Nadia Chraibi (CM) | Per communication wave
CHTR-04 Organizational Impact Charter | Nadia Chraibi (CM) | On scope change
CHTR-08 Pulse / Interview Charter | Nadia Chraibi (CM) | Per phase gate + ad hoc
journi — Cultural / Values Transformation (One Bouregreg: Post-Acquisition Culture Integration)
11

## Slide 13
PART 3 — TENANT AND ADMIN SETUP
Setup Checklist
Base tenant confirmed (Bouregreg Group, existing Organization)
Integration program team accounts created across both legacy workforces
CM Project created, Lewin opened at Unfreeze
TPL-CULT-7 phase template loaded on M17
Applicable Charters reviewed and accountable owners confirmed
journi — Cultural / Values Transformation (One Bouregreg: Post-Acquisition Culture Integration)
12

## Slide 14
PART 4 — WEEK-BY-WEEK TIMELINE
7 Phases, In Order
1. Diagnosis
2. Target Values Design
3. Leadership Modeling & Reinforcement Build
4. Pilot Cohort
5. Organization-Wide Rollout
6. Reinforcement Through Skepticism
7. Institutionalization
Total program length: 78 weeks (guide numbering, 18-month horizon). Every phase below is walked in detail across the next slides — normal flow first, then six exceptions in full operational detail.
journi — Cultural / Values Transformation (One Bouregreg: Post-Acquisition Culture Integration)
13

## Slide 15
PHASE 1 OF 7
Diagnosis
Weeks 1–10
NARRATIVE
Characterizes two starting cultures, not one — Bouregreg's plant-floor culture and Tangier's distribution-operation culture — before any values are proposed.
journi — Cultural / Values Transformation (One Bouregreg: Post-Acquisition Culture Integration)
14

## Slide 16
PHASE 1 · DIAGNOSIS
Key Moments in This Phase
Week | What Happens
Week 1 | Kickoff; Lewin opens at Unfreeze.
Week 1–6 | Karim Fassi logs zero visible actions on M7 — Exception E1 opens.
Week 10 | Diagnosis gate closes; dual-culture baseline complete.
journi — Cultural / Values Transformation (One Bouregreg: Post-Acquisition Culture Integration)
15

## Slide 17
PHASE 1 · DIAGNOSIS
Framework Snapshot
LEWIN
Unfreeze
ADKAR
Awareness
BRIDGES
Ending
KÜBLER-ROSS
Denial
KEY TECHNIQUE THIS PHASE
Dual-culture baseline mapping: Characterize two starting cultures side by side before proposing any values.
journi — Cultural / Values Transformation (One Bouregreg: Post-Acquisition Culture Integration)
16

## Slide 18
PHASE 2 OF 7
Target Values Design
Weeks 4–16
NARRATIVE
Designs the four target values with locked, bilingual-tested behavior anchors — not aspirational language alone.
journi — Cultural / Values Transformation (One Bouregreg: Post-Acquisition Culture Integration)
17

## Slide 19
PHASE 2 · TARGET VALUES DESIGN
Key Moments in This Phase
Week | What Happens
Week 6 | Sponsor Coverage Gap resolved via a direct, visible town hall.
Week 10 | Steering Committee formally seated.
Week 16 | All four values carry locked, bilingual-tested behavior anchors.
journi — Cultural / Values Transformation (One Bouregreg: Post-Acquisition Culture Integration)
18

## Slide 20
PHASE 2 · TARGET VALUES DESIGN
Framework Snapshot
LEWIN
Unfreeze
ADKAR
Awareness
BRIDGES
Ending
KÜBLER-ROSS
Denial
KEY TECHNIQUE THIS PHASE
Bilingual behavior-anchor design: Lock each value to a specific, testable behavior in both languages, not aspirational text.
journi — Cultural / Values Transformation (One Bouregreg: Post-Acquisition Culture Integration)
19

## Slide 21
PHASE 3 OF 7
Leadership Modeling & Reinforcement Build
Weeks 12–26
NARRATIVE
Builds the recognition and escalation reinforcement system while leaders model the target values directly.
journi — Cultural / Values Transformation (One Bouregreg: Post-Acquisition Culture Integration)
20

## Slide 22
PHASE 3 · LEADERSHIP MODELING & REINFORCEMENT BUILD
Key Moments in This Phase
Week | What Happens
Week 19 | Recognition system pilot-tested with a small mixed Tangier/Casablanca group.
Week 22 | Manager coaching circles begin.
Week 26 | All 8 leaders (4 per side) have logged specific commitments.
journi — Cultural / Values Transformation (One Bouregreg: Post-Acquisition Culture Integration)
21

## Slide 23
PHASE 3 · LEADERSHIP MODELING & REINFORCEMENT BUILD
Framework Snapshot
LEWIN
Unfreeze → Change
ADKAR
Knowledge
BRIDGES
Ending → Neutral Zone
KÜBLER-ROSS
Denial → Resistance/Anger
KEY TECHNIQUE THIS PHASE
Paired-leader modeling: Have leaders from both legacy organizations model values jointly, not separately.
journi — Cultural / Values Transformation (One Bouregreg: Post-Acquisition Culture Integration)
22

## Slide 24
PHASE 4 OF 7
Pilot Cohort
Weeks 20–34
NARRATIVE
Pairs one Tangier team with one legacy Bouregreg team as a genuine working pair, not two isolated pilots.
journi — Cultural / Values Transformation (One Bouregreg: Post-Acquisition Culture Integration)
23

## Slide 25
PHASE 4 · PILOT COHORT
Key Moments in This Phase
Week | What Happens
Week 20 | Pilot pair selected: Tangier Dispatch and Casablanca Supply Chain Liaison.
Week 25 | Tangier Dispatch's Desire drops to 2 over an unconfirmed consolidation rumor — Exception E2 opens.
Week 34 | Pilot cohort gate closes.
journi — Cultural / Values Transformation (One Bouregreg: Post-Acquisition Culture Integration)
24

## Slide 26
PHASE 4 · PILOT COHORT
Framework Snapshot
LEWIN
Change
ADKAR
Knowledge → Desire
BRIDGES
Neutral Zone
KÜBLER-ROSS
Resistance/Anger
KEY TECHNIQUE THIS PHASE
Genuine cross-site pairing: Pair one Tangier team with one Bouregreg team as a real working relationship, not two isolated pilots.
journi — Cultural / Values Transformation (One Bouregreg: Post-Acquisition Culture Integration)
25

## Slide 27
PHASE 5 OF 7
Organization-Wide Rollout
Weeks 32–50
NARRATIVE
Rolls the values program out in two waves — where a Divergence Pattern can surface in a cohort with less direct Tangier contact.
journi — Cultural / Values Transformation (One Bouregreg: Post-Acquisition Culture Integration)
26

## Slide 28
PHASE 5 · ORGANIZATION-WIDE ROLLOUT
Key Moments in This Phase
Week | What Happens
Week 42 | A Wave 2 Casablanca cohort fires ALT-001 (Divergence Pattern Detected) — Exception E3 opens.
Week 47 | Divergence resolved through a real cross-site paired exposure.
Week 50 | Rollout gate closes.
journi — Cultural / Values Transformation (One Bouregreg: Post-Acquisition Culture Integration)
27

## Slide 29
PHASE 5 · ORGANIZATION-WIDE ROLLOUT
Framework Snapshot
LEWIN
Change
ADKAR
Knowledge → Ability
BRIDGES
Neutral Zone
KÜBLER-ROSS
Resistance/Anger → Exploration
KEY TECHNIQUE THIS PHASE
Two-wave staged rollout: Roll out in waves so later cohorts benefit from earlier lessons.
journi — Cultural / Values Transformation (One Bouregreg: Post-Acquisition Culture Integration)
28

## Slide 30
PHASE 6 OF 7
Reinforcement Through Skepticism
Weeks 45–68
NARRATIVE
Holds the values program's reinforcement work steady against real skepticism — including a Board announcement racing ahead of the program's own evidence.
journi — Cultural / Values Transformation (One Bouregreg: Post-Acquisition Culture Integration)
29

## Slide 31
PHASE 6 · REINFORCEMENT THROUGH SKEPTICISM
Key Moments in This Phase
Week | What Happens
Week 56 | A public "Integration Complete" statement outpaces journi's own Lewin reading — Exception E4 opens.
Week 65 | A promotion decision regresses Tangier sentiment sharply — Exception E5 opens.
Week 68 | Reinforcement phase gate closes.
journi — Cultural / Values Transformation (One Bouregreg: Post-Acquisition Culture Integration)
30

## Slide 32
PHASE 6 · REINFORCEMENT THROUGH SKEPTICISM
Framework Snapshot
LEWIN
Change
ADKAR
Ability → Reinforcement
BRIDGES
Neutral Zone
KÜBLER-ROSS
Exploration
KEY TECHNIQUE THIS PHASE
Two-clock discipline against a public announcement: Separate a corporate/brand milestone from journi's own evidence-based Refreeze call.
journi — Cultural / Values Transformation (One Bouregreg: Post-Acquisition Culture Integration)
31

## Slide 33
PHASE 7 OF 7
Institutionalization
Weeks 62–78, open-ended beyond
NARRATIVE
Confirms the four values are genuinely the new normal — closing Refreeze from evidence, not the acquisition's own press-release timeline.
journi — Cultural / Values Transformation (One Bouregreg: Post-Acquisition Culture Integration)
32

## Slide 34
PHASE 7 · INSTITUTIONALIZATION
Key Moments in This Phase
Week | What Happens
Week 70 | Cross-site cohort divergence (Exception E6) still being tracked as this phase closes.
Week 78 | Refreeze called from evidence; reinforcement continues well past the ERP program's own close.
journi — Cultural / Values Transformation (One Bouregreg: Post-Acquisition Culture Integration)
33

## Slide 35
PHASE 7 · INSTITUTIONALIZATION
Framework Snapshot
LEWIN
Refreeze
ADKAR
Reinforcement
BRIDGES
New Beginning
KÜBLER-ROSS
Commitment
KEY TECHNIQUE THIS PHASE
Cross-site CRI divergence tracking: Track a structural, slow-moving cohort gap rather than treat it as a single-week trigger.
journi — Cultural / Values Transformation (One Bouregreg: Post-Acquisition Culture Integration)
34

## Slide 36
PART 4 — MASTER WBS & GANTT
Every Phase, Across the Four Frameworks
Phase | Week(s) | Lewin | ADKAR | Bridges | Kübler-Ross
Diagnosis | Weeks 1–10 | Unfreeze | Awareness | Ending | Denial
Target Values Design | Weeks 4–16 | Unfreeze | Awareness | Ending | Denial
Leadership Modeling & Reinforcement Build | Weeks 12–26 | Unfreeze → Change | Knowledge | Ending → Neutral Zone | Denial → Resistance/Anger
Pilot Cohort | Weeks 20–34 | Change | Knowledge → Desire | Neutral Zone | Resistance/Anger
Organization-Wide Rollout | Weeks 32–50 | Change | Knowledge → Ability | Neutral Zone | Resistance/Anger → Exploration
Reinforcement Through Skepticism | Weeks 45–68 | Change | Ability → Reinforcement | Neutral Zone | Exploration
Institutionalization | Weeks 62–78+ | Refreeze | Reinforcement | New Beginning | Commitment
journi — Cultural / Values Transformation (One Bouregreg: Post-Acquisition Culture Integration)
35

## Slide 37
PART 4 — MASTER WBS & GANTT
Every Phase, Techniques and Tools
Phase | Week(s) | Technique | Goal | Tool
Diagnosis | Weeks 1–10 | Dual-culture baseline mapping | Characterize two starting cultures side by side before proposing any values. | M4 (Stakeholder Mapping)
Target Values Design | Weeks 4–16 | Bilingual behavior-anchor design | Lock each value to a specific, testable behavior in both languages, not aspirational text. | M21 (Field Notes)
Leadership Modeling & Reinforcement Build | Weeks 12–26 | Paired-leader modeling | Have leaders from both legacy organizations model values jointly, not separately. | M8 (Communications)
Pilot Cohort | Weeks 20–34 | Genuine cross-site pairing | Pair one Tangier team with one Bouregreg team as a real working relationship, not two isolated pilots. | M6 (Emotional & Transition Layer)
Organization-Wide Rollout | Weeks 32–50 | Two-wave staged rollout | Roll out in waves so later cohorts benefit from earlier lessons. | M5 (ADKAR Engine)
Reinforcement Through Skepticism | Weeks 45–68 | Two-clock discipline against a public announcement | Separate a corporate/brand milestone from journi's own evidence-based Refreeze call. | M3 (Initiative Registry)
Institutionalization | Weeks 62–78+ | Cross-site CRI divergence tracking | Track a structural, slow-moving cohort gap rather than treat it as a single-week trigger. | M14 (Analytics)
journi — Cultural / Values Transformation (One Bouregreg: Post-Acquisition Culture Integration)
36

## Slide 38
PART 4 — SIX EXCEPTIONS, IN DETAIL
Six Realistic Ways This Program Could Have Gone Differently
journi — Cultural / Values Transformation (One Bouregreg: Post-Acquisition Culture Integration)
37

## Slide 39
E1 · DIAGNOSIS, WEEKS 1–6
Sponsor Coverage Gap
DESCRIPTION
Karim Fassi, newly appointed as this program's integration Sponsor, logged zero visible actions on M7 through the program's first four weeks — exactly ALT-003's condition.
TRIGGER
Sponsor visibility on M7 logged as "weak."
TIMELINE IMPACT
No formal gate delay, but risks damaging Bridges/Kübler-Ross evidence if left unaddressed.
RECOVERY TASKS
A direct, visible town hall and a documented sponsorship action plan.
OUTPUTS: A corrected Sponsor visibility reading; a rebuilt trust baseline. RACSI: R = CM, PM · A = ES · C = FPO · S = SUP · I = EU
journi — Cultural / Values Transformation (One Bouregreg: Post-Acquisition Culture Integration)
38

## Slide 40
E2 · PILOT COHORT, WEEKS 25–30
Desire Stall at Tangier Pilot
DESCRIPTION
Tangier Dispatch's ADKAR Desire score dropped to 2, triggering a mandatory barrier-reason note. The root cause was an unconfirmed rumor that Tangier's dispatch function would be consolidated into Casablanca within a year.
TRIGGER
Desire logged at 2 or below, auto-escalating.
TIMELINE IMPACT
No gate delay — resolved through direct, honest communication within the pilot phase.
RECOVERY TASKS
Confirm or deny the rumor directly and honestly; address the underlying fear rather than the surface symptom.
OUTPUTS: A resolved rumor; a recovered Desire score. RACSI: R = CM · A = CM · C = ES, SUP · S = PM · I = FPO, EU
journi — Cultural / Values Transformation (One Bouregreg: Post-Acquisition Culture Integration)
39

## Slide 41
E3 · ORGANIZATION-WIDE ROLLOUT, WEEKS 42–47
Divergence Pattern at Rollout
DESCRIPTION
A Wave 2 Casablanca cohort with markedly less direct Tangier contact showed Knowledge and Ability both at 4 or above while Bridges still read "Ending" — ALT-001's exact condition. The cohort understood the values intellectually but had never had them tested against a real cross-site relationship.
TRIGGER
ALT-001 (Divergence Pattern Detected) fires on M6.
TIMELINE IMPACT
No gate delay — resolved through a targeted cross-site exposure within the rollout window.
RECOVERY TASKS
Create a real, not simulated, cross-site working relationship for the affected cohort.
OUTPUTS: A resolved divergence; a genuine cross-site relationship in place of an intellectual-only understanding. RACSI: R = CM · A = CM · C = SUP, FPO · S = ITL · I = ES, EU
journi — Cultural / Values Transformation (One Bouregreg: Post-Acquisition Culture Integration)
40

## Slide 42
E4 · REINFORCEMENT THROUGH SKEPTICISM, WEEKS 56–60
Premature "Integration Complete" Declaration
DESCRIPTION
Bouregreg Group's Board issued a public "One Bouregreg — Integration Complete" statement timed to fiscal year-end, while journi's own Lewin reading remained "Change," not Refreeze — this program's own two-clock problem.
TRIGGER
A corporate/brand milestone announced ahead of journi's own evidence-based Refreeze call.
TIMELINE IMPACT
No gate delay, but risks staff reading the announcement as premature spin or license to stop reinforcement work.
RECOVERY TASKS
Communicate the distinction between the corporate milestone and the ongoing reinforcement work directly, not silently.
OUTPUTS: A clarified internal message; continued reinforcement work despite the public announcement. RACSI: R = CM · A = ES · C = PM · S = FPO · I = SUP, EU
journi — Cultural / Values Transformation (One Bouregreg: Post-Acquisition Culture Integration)
41

## Slide 43
E5 · REINFORCEMENT THROUGH SKEPTICISM, WEEKS 65–68
Sentiment Regression
DESCRIPTION
A newly created "combined regional" role passed over a tenured Tangier candidate for a less-tenured Bouregreg-side candidate; Tangier's Kübler-Ross sentiment regressed sharply toward Resistance/Anger — read as evidence that "Equal Standing" was not real in practice.
TRIGGER
A cohort's Kübler-Ross reading moves backward following a specific triggering event.
TIMELINE IMPACT
No gate delay — resolved through a transparent review within the same phase.
RECOVERY TASKS
A transparent review of the decision; correction of the genuine procedural gap found (the role was never posted at Tangier).
OUTPUTS: A documented procedural fix; a rebuilt trust baseline at Tangier. RACSI: R = FPO, ES · A = ES · C = CM · S = SUP · I = EU
journi — Cultural / Values Transformation (One Bouregreg: Post-Acquisition Culture Integration)
42

## Slide 44
E6 · CROSS-CUTTING, PHASES 4–7
Cross-Site Cohort Divergence
DESCRIPTION
Across three consecutive Composite Readiness Index readings, Tangier's cohort score consistently trailed the Casablanca-counterpart cohort by a real margin — a slower-moving, structural pattern tracing to Tangier's later program-relative start and deeper trust deficit.
TRIGGER
A persistent, non-noise CRI gap between cohorts across multiple readings.
TIMELINE IMPACT
No single gate delay — tracked continuously from Pilot through Institutionalization.
RECOVERY TASKS
Track the gap explicitly rather than average it away; direct additional reinforcement resources toward the lagging cohort.
OUTPUTS: A standing, disaggregated cross-site tracking practice, still active as Institutionalization closes. RACSI: R = CM, SUP · A = CM · C = FPO, PM · S = ITL · I = ES, EU
journi — Cultural / Values Transformation (One Bouregreg: Post-Acquisition Culture Integration)
43

## Slide 45
PART 5 — TRAINING PROGRAM
What This Training Covers
MP-05 does not appear in journi's E2E-CULT chain — nothing here trains anyone into believing the four values. What this program trains is real, values-independent capability: Tangier staff don't yet know Bouregreg's shared systems, and Bouregreg's own People Managers have never supervised a newly-merged team.
journi — Cultural / Values Transformation (One Bouregreg: Post-Acquisition Culture Integration)
44

## Slide 46
PART 5 · TIER 1 OF 3
Strategic Management
Cohort: The Steering Committee: Karim Fassi, Nadia Chraibi, Youssef Idrissi, Meryem Sabri, Laila Mernissi · Weeks 10–14
Curriculum Entry | Content Focus
Leading a Two-Culture Organization | Governing an integration where neither culture is the default — reading Bridges/Kübler-Ross as leadership signals.
journi Governance for Multi-Organization Programs | Reading a Stakeholder Map and CRI that span two Organizations under one Group.
Communicating Through an Acquisition | Media, investor, and internal-communication discipline, delivered ahead of the Week 56 Two-Clock Problem.
journi — Cultural / Values Transformation (One Bouregreg: Post-Acquisition Culture Integration)
45

## Slide 47
PART 5 · TIER 2 OF 3
Operational Management
Cohort: People Managers across both Organizations (12 total) · Weeks 18–24
Curriculum Entry | Content Focus
Managing a Newly-Merged Team | Supervisory skills specific to managing staff from the other company's original workforce.
Unified Operating Procedures — Distribution & Logistics | Harmonized SOPs so managers supervise a mixed team on one shared procedure.
Coaching Fundamentals for People Managers | Feeds directly into M11 (Manager as Coach)'s team-scoped heatmap.
journi — Cultural / Values Transformation (One Bouregreg: Post-Acquisition Culture Integration)
46

## Slide 48
PART 5 · TIER 3 OF 3
Operations (Frontline)
Cohort: All 400 target staff, split by rollout wave · Weeks 35–47
Curriculum Entry | Content Focus
Bouregreg Shared Systems & Tools Orientation | Practical onboarding to shared order-tracking and dispatch tooling.
Unified Safety & Quality Procedures | Harmonized standards across both sites' operations.
Customer Commitment Standards — One Bouregreg | Unified customer-facing service standards.
journi — Cultural / Values Transformation (One Bouregreg: Post-Acquisition Culture Integration)
47

## Slide 49
PART 5 — TRAINING PROGRAM
Why This Curriculum Is Shaped This Way
A high training-completion reading confirms Tangier and Casablanca staff can use the shared systems — it does not, on its own, confirm the four values have taken hold. That evidence still comes from Bridges, Kübler-Ross, and Part 4's own mechanisms, and this program's training term is expected to rise well ahead of its cultural terms, by design.
journi — Cultural / Values Transformation (One Bouregreg: Post-Acquisition Culture Integration)
48

## Slide 50
CROSS-REFERENCE
Which journi Modules Dominate This Archetype
M6 (Emotional & Transition Layer)
The heaviest use of Bridges and Kübler-Ross of any archetype — two starting cultures tracked side by side.
M7 (Sponsor & Coalition)
A newly appointed Sponsor starts with zero logged actions — the direct ALT-003 trigger.
M5 (ADKAR Engine)
Desire is the block most exposed here — a named, specific fear (job security) stalls it.
M8 (Communications)
Joint briefings for paired cohorts, not separate messaging for each legacy culture.
M9 (Training)
A parallel track for real capability gaps, deliberately kept separate from the values curriculum itself.
M14 (Analytics)
Tracks the training-completion term rising well ahead of the cultural CRI terms — a predicted, not alarming, gap.
journi — Cultural / Values Transformation (One Bouregreg: Post-Acquisition Culture Integration)
49

## Slide 51
ALERTS & PROOF
What This Case Fires
ALERTS THIS CASE EXERCISES
ALT-003 (Sponsor Coverage Gap)
WHY
Built deliberately around a newly appointed Sponsor's slow start — the archetype most exposed to sponsorship visibility risk.
journi — Cultural / Values Transformation (One Bouregreg: Post-Acquisition Culture Integration)
50

## Slide 52
KEY TAKEAWAYS
What to Remember About This Archetype
› A real Sponsor Coverage Gap that fires and is corrected, a real Desire stall traced to a named, acquisition-specific fear, and a Refreeze signed only once the evidence — not the acquisition's own press-release timeline — supports it.
› Bridges and Kübler-Ross dominate. Identity and emotional integration matter more than any specific skill here — a newly appointed Sponsor with zero logged actions damages exactly these two frameworks fastest, which is why this archetype is built to fire ALT-003 early rather than later.
› Built deliberately around a newly appointed Sponsor's slow start — the archetype most exposed to sponsorship visibility risk.
journi — Cultural / Values Transformation (One Bouregreg: Post-Acquisition Culture Integration)
51

## Slide 53
Cultural / Values Transformation
One Bouregreg: Post-Acquisition Culture Integration
Manufacturing Sector · Bouregreg Group Scenario Library · Confidential