## Slide 1
ERP Implementation
Bouregreg ERP Adoption Program
A full system cutover across every site at once — the throughline case where all four frameworks matter equally, all the time.
8
PHASES
64
WEEKS
6
EXCEPTIONS
3
TRAINING TIERS
Manufacturing Sector · Bouregreg Group Scenario Library · Confidential

## Slide 2
PART 0 — PURPOSE
What This Guide Is, and How to Use It
WHAT THIS GUIDE IS
This deck follows the Bouregreg ERP Adoption Program — journi's own throughline case — from tenant setup through Sustain, showing exactly how a full, vendor-agnostic ERP cutover is run inside journi, week by week, module by module.
HOW TO USE IT
The tenant this deck builds is the same one every other archetype guide in this series extends. A reader who already has the tenant set up can skip straight to the Setup section's CM Project creation step.
journi — ERP Implementation (Bouregreg ERP Adoption Program)
01

## Slide 3
PART 0 — A NOTE ON FIDELITY
Verified Against journi's Real Source
Every journi module, field, and role named here is verified against journi's real source and its own Master User Guide. This is the case most likely to exercise ALT-001 (Divergence Pattern Detected) at UAT and ALT-009 (Phase Gate No-Go/Conditional) at any gate — this deck states plainly which of the two actually fires in the real record, rather than imply both.
RACSI CODES USED THROUGHOUT
ES = Executive Sponsor · CM = Change Manager · PM = Program/Project Manager · FPO = Functional Process Owner · ITL = IT/Technical Lead · SUP = Supervisor · EU = End User
journi — ERP Implementation (Bouregreg ERP Adoption Program)
02

## Slide 4
PART 1 — EXECUTIVE SUMMARY
Why This Case Matters
Every other archetype in this series can treat one or two frameworks as dominant. ERP cannot: a full cutover needs organizational readiness (Lewin) and individual capability (ADKAR) at the same time, everywhere, for the program's entire 64-week life — the only archetype where that is true throughout, not just at one phase.
journi — ERP Implementation (Bouregreg ERP Adoption Program)
03

## Slide 5
PART 1 — EXECUTIVE SUMMARY
The Case, in Brief
3,400 staff, all sites (Casablanca, Kenitra, Settat)
64 weeks (org calendar W1–64)
Bouregreg Group replaces fragmented, manual, and legacy tooling with one integrated system of record across Order Management, Inventory, and Finance, across all three sites, over 64 weeks — the tenant's own founding program, opened at Unfreeze from Week 1.
journi — ERP Implementation (Bouregreg ERP Adoption Program)
04

## Slide 6
PART 1 — EXECUTIVE SUMMARY
What This Guide Proves, Concretely
A real Divergence Pattern catch before go-live (Casablanca, Week 28), a real cross-site Composite Readiness Index disaggregation (Exception E6), and a Refreeze called only once Sustain's own 90-day checkpoint evidence supports it — not the go-live date.
journi — ERP Implementation (Bouregreg ERP Adoption Program)
05

## Slide 7
PART 2 — THE FOUR FRAMEWORKS
Weighting for This Archetype
ADKAR and Lewin dominate equally, throughout. A system cutover needs organizational readiness (Lewin's Change → Refreeze) and individual capability (ADKAR's Knowledge/Ability) at the same time — neither alone is sufficient, and unlike every other archetype in this series, that is true across all 8 phases, not concentrated in one.
journi — ERP Implementation (Bouregreg ERP Adoption Program)
06

## Slide 8
PART 2 — THE FOUR FRAMEWORKS
The Composite Readiness Index, Read for This Case
The Composite Readiness Index reads a genuinely different story at each site by mid-Train — Casablanca ahead on Knowledge/Ability given proximity to the program team, Settat behind following a Desire stall, Kenitra solid until a later sentiment regression — exactly the blended-vs-disaggregated tension Exception E6 exists to resolve.
journi — ERP Implementation (Bouregreg ERP Adoption Program)
07

## Slide 9
PART 3 — TENANT AND ADMIN SETUP
The Existing Tenant, and Reading Paths by Role
THE EXISTING TENANT
This program runs inside the same tenant journi's Master User Guide builds, under the existing Bouregreg Manufacturing Maroc Organization — no new Organization needed.
READING PATHS, BY ROLE
› A Change Manager running this program day to day: Part 2 once, then Part 4 in full.
› A Program/Project Manager: Part 4's PM Track column and the Master WBS & Gantt.
› An Executive Sponsor: Part 1, then Part 4's phase-opening narratives.
› A Super Admin or Org Admin: Part 3.
journi — ERP Implementation (Bouregreg ERP Adoption Program)
08

## Slide 10
PART 3 — TENANT AND ADMIN SETUP
The RACSI Team for This Program
Name | RACSI Code | Role
CFO, Bouregreg Group | ES | Sponsor
Driss El Amrani | CM | Change Manager — owns day-to-day program execution
Ghita Bennis | PM | Practitioner / Contributor — PM-track coordination, WBS & Gantt (M17)
Houda Zerouali | FPO | People Manager
Meryem Sabri | Org Admin | Organization-level setup and cross-site CRI disaggregation
Reda Loukili | EU | Employee
journi — ERP Implementation (Bouregreg ERP Adoption Program)
09

## Slide 11
PART 3 — TENANT AND ADMIN SETUP
Creating the CM Project
1
On Module 2 — Users & Roles, seed Bouregreg Group's initial team: Super Admin, Group Admin, Org Admin, then the project-scoped Change Manager, People Manager, Sponsor, Employee, and Practitioner accounts.
2
On Module 1 — Hierarchy, create the Bouregreg ERP Adoption Program CM Project, owned by Driss El Amrani, with all 3,400 staff across three sites as target population.
3
Save. Lewin opens at Unfreeze — the tenant's founding framework reading, justified against the board-approved business case.
4
On Module 17 — WBS & Gantt, load the TPL-ERP-8 phase template: Discovery, Design, Build, Test, Train, Deploy, Hypercare, Sustain.
journi — ERP Implementation (Bouregreg ERP Adoption Program)
10

## Slide 12
PART 3 — TENANT AND ADMIN SETUP
Charters for This Program
Charter | Accountable | Review Cadence
CHTR-01 Sponsorship / Leadership Charter | CFO, Bouregreg Group (ES) | Per Phase Gate
CHTR-02 Participative Management Charter | Frontline Supervisor role | Per champion briefing
CHTR-05 Team Coaching Charter | People Manager role | At Hypercare sentiment recovery
CHTR-06 One-to-One Coaching Charter | Driss El Amrani (CM) | At Divergence Pattern resolution
CHTR-08 Pulse / Interview Charter | Driss El Amrani (CM) | Per phase gate + ad hoc
journi — ERP Implementation (Bouregreg ERP Adoption Program)
11

## Slide 13
PART 3 — TENANT AND ADMIN SETUP
Setup Checklist
Base tenant confirmed (Bouregreg Group, Bouregreg Manufacturing Maroc Organization)
ERP program team accounts created across all RBAC scopes
CM Project created, Lewin opened at Unfreeze
TPL-ERP-8 phase template loaded on M17
Applicable Charters reviewed and accountable owners confirmed
journi — ERP Implementation (Bouregreg ERP Adoption Program)
12

## Slide 14
PART 4 — WEEK-BY-WEEK TIMELINE
8 Phases, In Order
1. Discovery
2. Design
3. Build
4. Test
5. Train
6. Deploy
7. Hypercare
8. Sustain
Total program length: 64 weeks (org calendar W1–64). Every phase below is walked in detail across the next slides — normal flow first, then six exceptions in full operational detail.
journi — ERP Implementation (Bouregreg ERP Adoption Program)
13

## Slide 15
PHASE 1 OF 8
Discovery
Weeks 1–8
NARRATIVE
Establishes the current-state process map across Order Management, Inventory, and Finance, and confirms the business case driving the cutover.
journi — ERP Implementation (Bouregreg ERP Adoption Program)
14

## Slide 16
PHASE 1 · DISCOVERY
Key Moments in This Phase
Week | What Happens
Week 1 | Kickoff; Lewin opens at Unfreeze.
Week 5 | Current-state process mapping across all three sites.
Week 8 | Discovery gate closes; future-state scope confirmed.
journi — ERP Implementation (Bouregreg ERP Adoption Program)
15

## Slide 17
PHASE 1 · DISCOVERY
Framework Snapshot
LEWIN
Unfreeze
ADKAR
Awareness
BRIDGES
Ending
KÜBLER-ROSS
Denial
KEY TECHNIQUE THIS PHASE
Current-state process mapping: Establish exactly what today's manual/legacy process actually does, by site.
journi — ERP Implementation (Bouregreg ERP Adoption Program)
16

## Slide 18
PHASE 2 OF 8
Design
Weeks 6–17
NARRATIVE
Signs off the future-state design principles the whole build will configure against — starting before Discovery formally closes, since PM and CM tracks run in parallel.
journi — ERP Implementation (Bouregreg ERP Adoption Program)
17

## Slide 19
PHASE 2 · DESIGN
Key Moments in This Phase
Week | What Happens
Week 9 | First town hall; first real Awareness scores land, Settat lowest.
Week 13 | Design scope signed off by the Steering Committee.
Week 17 | Design gate closes.
journi — ERP Implementation (Bouregreg ERP Adoption Program)
18

## Slide 20
PHASE 2 · DESIGN
Framework Snapshot
LEWIN
Unfreeze
ADKAR
Awareness
BRIDGES
Ending
KÜBLER-ROSS
Denial
KEY TECHNIQUE THIS PHASE
Future-state design-principle sign-off: Lock the principles every later configuration sprint builds against.
journi — ERP Implementation (Bouregreg ERP Adoption Program)
19

## Slide 21
PHASE 3 OF 8
Build
Weeks 14–35
NARRATIVE
The longest phase — four configuration sprints against the signed-off design principles. This is where Exception E1 (Desire Stall at Settat) plays out in full.
journi — ERP Implementation (Bouregreg ERP Adoption Program)
20

## Slide 22
PHASE 3 · BUILD
Key Moments in This Phase
Week | What Happens
Week 18–22 | Mid-Build; Settat's Desire drops to 2, auto-escalating — Exception E1 opens.
Week 22 | CFO delivers a direct staffing commitment to the Settat cohort in person.
Week 35 | Build gate closes; Lewin call actually moves, backed by evidence.
journi — ERP Implementation (Bouregreg ERP Adoption Program)
21

## Slide 23
PHASE 3 · BUILD
Framework Snapshot
LEWIN
Unfreeze → Change
ADKAR
Awareness → Desire
BRIDGES
Ending → Neutral Zone
KÜBLER-ROSS
Denial → Resistance/Anger
KEY TECHNIQUE THIS PHASE
Configuration sprints + barrier-note clustering: Build the system while catching and clustering readiness barriers by root cause, not symptom.
journi — ERP Implementation (Bouregreg ERP Adoption Program)
22

## Slide 24
PHASE 4 OF 8
Test
Weeks 28–39
NARRATIVE
The first point a representative slice of end users gets real hands-on exposure — and the first honest opportunity to run the Divergence Pattern check.
journi — ERP Implementation (Bouregreg ERP Adoption Program)
23

## Slide 25
PHASE 4 · TEST
Key Moments in This Phase
Week | What Happens
Week 28 | SIT test script run: 40 scripted scenarios across all three modules.
Week 31 | A Casablanca finance UAT participant fires ALT-001 (Divergence Pattern Detected) — Exception E2 opens.
Week 35 | Loss-focused 1:1 held; underlying concern (a role that doesn't exist post-cutover) surfaced and closed.
journi — ERP Implementation (Bouregreg ERP Adoption Program)
24

## Slide 26
PHASE 4 · TEST
Framework Snapshot
LEWIN
Change
ADKAR
Knowledge → Ability
BRIDGES
Neutral Zone
KÜBLER-ROSS
Resistance/Anger → Exploration
KEY TECHNIQUE THIS PHASE
Scripted SIT + Divergence Pattern check: Confirm technical correctness and catch a trained-but-not-yet-accepted cohort before go-live.
journi — ERP Implementation (Bouregreg ERP Adoption Program)
25

## Slide 27
PHASE 5 OF 8
Train
Weeks 35–42
NARRATIVE
Runs alongside Test rather than strictly after it — Knowledge becomes Ability under increasingly realistic conditions.
journi — ERP Implementation (Bouregreg ERP Adoption Program)
26

## Slide 28
PHASE 5 · TRAIN
Key Moments in This Phase
Week | What Happens
Week 35 | Sandbox environment opens for supervised practice, all three sites.
Week 36 | Knowledge/Ability scored per cohort: Settat reads meaningfully behind — Exception E6 opens.
Week 37 | Composite Readiness Index disaggregated by site for the first time: Casablanca 78%, Kenitra 68%, Settat 54%.
journi — ERP Implementation (Bouregreg ERP Adoption Program)
27

## Slide 29
PHASE 5 · TRAIN
Framework Snapshot
LEWIN
Change
ADKAR
Knowledge → Ability
BRIDGES
Neutral Zone
KÜBLER-ROSS
Exploration
KEY TECHNIQUE THIS PHASE
Sandbox practice + per-cohort Knowledge/Ability scoring: Move Knowledge into Ability under realistic, supervised conditions.
journi — ERP Implementation (Bouregreg ERP Adoption Program)
28

## Slide 30
PHASE 6 OF 8
Deploy
Week 43
NARRATIVE
A single, sharp week — the clearest instance of the two-clock problem this series treats as a first-class risk, not an edge case.
journi — ERP Implementation (Bouregreg ERP Adoption Program)
29

## Slide 31
PHASE 6 · DEPLOY
Key Moments in This Phase
Week | What Happens
Week 43, Day 1–4 | Technical go-live clean across all three sites.
Week 43, Day 5 | Hypercare activates; Lewin marked "Change → Refreeze (provisional)," not confirmed — Exception E3 opens by design.
journi — ERP Implementation (Bouregreg ERP Adoption Program)
30

## Slide 32
PHASE 6 · DEPLOY
Framework Snapshot
LEWIN
Change → Refreeze (provisional)
ADKAR
Ability
BRIDGES
Neutral Zone
KÜBLER-ROSS
Exploration
KEY TECHNIQUE THIS PHASE
Two-clock discipline (provisional Refreeze): Separate the technical go-live milestone from the confirmed emotional/behavioral Refreeze call.
journi — ERP Implementation (Bouregreg ERP Adoption Program)
31

## Slide 33
PHASE 7 OF 8
Hypercare
Weeks 44–50
NARRATIVE
The last mile of adoption is won or lost here — Kübler-Ross regression during this window is normal, expected behavior, not a data error.
journi — ERP Implementation (Bouregreg ERP Adoption Program)
32

## Slide 34
PHASE 7 · HYPERCARE
Key Moments in This Phase
Week | What Happens
Week 45 | Bridges/Kübler-Ross re-pulse at 2-week mark; Kenitra dips — Exception E4 trigger.
Week 46 | Kenitra defect resolved; supervisor holds a team huddle acknowledging the setback directly.
Week 48 | Exception E6's disaggregated CRI gap narrows substantially: 82% / 76% / 74%.
journi — ERP Implementation (Bouregreg ERP Adoption Program)
33

## Slide 35
PHASE 7 · HYPERCARE
Framework Snapshot
LEWIN
Change → Refreeze (provisional)
ADKAR
Ability → Reinforcement
BRIDGES
Neutral Zone → New Beginning
KÜBLER-ROSS
Exploration → Commitment
KEY TECHNIQUE THIS PHASE
2- and 4-week Bridges/Kübler-Ross re-pulse: Catch and resolve a sentiment dip before it hardens into lasting resistance.
journi — ERP Implementation (Bouregreg ERP Adoption Program)
34

## Slide 36
PHASE 8 OF 8
Sustain
Weeks 51–64
NARRATIVE
Refreeze is called from checkpoint evidence, never the calendar — the discipline that protects against Exception E5 (Reinforcement Gap at Sustain).
journi — ERP Implementation (Bouregreg ERP Adoption Program)
35

## Slide 37
PHASE 8 · SUSTAIN
Key Moments in This Phase
Week | What Happens
Week 56 | Reinforcement stalls below 3 at the 90-day checkpoint — Exception E5 opens.
Week 60 | CFO re-authorizes a further checkpoint cadence; champion network re-chartered for reinforcement.
Week 64 | Two consecutive healthy checkpoints follow; Refreeze is called from that evidence and program closes.
journi — ERP Implementation (Bouregreg ERP Adoption Program)
36

## Slide 38
PHASE 8 · SUSTAIN
Framework Snapshot
LEWIN
Refreeze
ADKAR
Reinforcement
BRIDGES
New Beginning
KÜBLER-ROSS
Commitment
KEY TECHNIQUE THIS PHASE
30/60/90-day sustainment checkpoints: Call Refreeze from evidence, never the calendar.
journi — ERP Implementation (Bouregreg ERP Adoption Program)
37

## Slide 39
PART 4 — MASTER WBS & GANTT
Every Phase, Across the Four Frameworks
Phase | Week(s) | Lewin | ADKAR | Bridges | Kübler-Ross
Discovery | Weeks 1–8 | Unfreeze | Awareness | Ending | Denial
Design | Weeks 6–17 | Unfreeze | Awareness | Ending | Denial
Build | Weeks 14–35 | Unfreeze → Change | Awareness → Desire | Ending → Neutral Zone | Denial → Resistance/Anger
Test | Weeks 28–39 | Change | Knowledge → Ability | Neutral Zone | Resistance/Anger → Exploration
Train | Weeks 35–42 | Change | Knowledge → Ability | Neutral Zone | Exploration
Deploy | Week 43 | Change → Refreeze (provisional) | Ability | Neutral Zone | Exploration
Hypercare | Weeks 44–50 | Change → Refreeze (provisional) | Ability → Reinforcement | Neutral Zone → New Beginning | Exploration → Commitment
Sustain | Weeks 51–64 | Refreeze | Reinforcement | New Beginning | Commitment
journi — ERP Implementation (Bouregreg ERP Adoption Program)
38

## Slide 40
PART 4 — MASTER WBS & GANTT
Every Phase, Techniques and Tools
Phase | Week(s) | Technique | Goal | Tool
Discovery | Weeks 1–8 | Current-state process mapping | Establish exactly what today's manual/legacy process actually does, by site. | M4 (Stakeholder Mapping)
Design | Weeks 6–17 | Future-state design-principle sign-off | Lock the principles every later configuration sprint builds against. | M17 (WBS & Gantt)
Build | Weeks 14–35 | Configuration sprints + barrier-note clustering | Build the system while catching and clustering readiness barriers by root cause, not symptom. | M5 (ADKAR Engine)
Test | Weeks 28–39 | Scripted SIT + Divergence Pattern check | Confirm technical correctness and catch a trained-but-not-yet-accepted cohort before go-live. | M6 (Emotional & Transition Layer)
Train | Weeks 35–42 | Sandbox practice + per-cohort Knowledge/Ability scoring | Move Knowledge into Ability under realistic, supervised conditions. | M9 (Training)
Deploy | Week 43 | Two-clock discipline (provisional Refreeze) | Separate the technical go-live milestone from the confirmed emotional/behavioral Refreeze call. | M3 (Initiative Registry)
Hypercare | Weeks 44–50 | 2- and 4-week Bridges/Kübler-Ross re-pulse | Catch and resolve a sentiment dip before it hardens into lasting resistance. | M11 (Manager as Coach)
Sustain | Weeks 51–64 | 30/60/90-day sustainment checkpoints | Call Refreeze from evidence, never the calendar. | M12 (Sustainment)
journi — ERP Implementation (Bouregreg ERP Adoption Program)
39

## Slide 41
PART 4 — SIX EXCEPTIONS, IN DETAIL
Six Realistic Ways This Program Could Have Gone Differently
journi — ERP Implementation (Bouregreg ERP Adoption Program)
40

## Slide 42
E1 · BUILD, WEEKS 18–22
Desire Stall at Settat
DESCRIPTION
Settat's ADKAR Desire score drops to 2, auto-escalating a barrier-reason note citing low visibility into the new inventory workflow and unresolved staffing-level fears.
TRIGGER
Desire logged at 2 or below for the Settat plant-floor cohort on M5, auto-escalating.
TIMELINE IMPACT
No Build gate delay — resolved within the same phase via a direct sponsor intervention.
RECOVERY TASKS
Cluster barrier notes by root cause; run targeted listening sessions confirming position security, not workflow visibility, is the primary driver; CFO delivers a direct staffing commitment in person.
OUTPUTS: A closed barrier note; a documented sponsor intervention; a recovered Desire score. RACSI: R = CM · A = ES · C = FPO, SUP · S = PM · I = EU
journi — ERP Implementation (Bouregreg ERP Adoption Program)
41

## Slide 43
E2 · TEST, WEEKS 31–35
Divergence Pattern at UAT
DESCRIPTION
A Casablanca finance UAT participant logs Knowledge ≥ 4 and Ability ≥ 4 while Bridges still reads exactly "Ending" — ALT-001's exact condition.
TRIGGER
ALT-001 (Divergence Pattern Detected) fires on M6, cross-referenced against M5.
TIMELINE IMPACT
No gate delay — resolved through a confidential 1:1 within the same week window.
RECOVERY TASKS
Confirm the alert against supervisor observation; hold a loss-focused 1:1; the underlying concern (a role that doesn't exist post-cutover) is surfaced and given an explicit closure moment.
OUTPUTS: A confidential 1:1 outcome logged as a Bridges re-score; a closed divergence. RACSI: R = CM · A = CM · C = ES · S = PM · I = FPO, EU
journi — ERP Implementation (Bouregreg ERP Adoption Program)
42

## Slide 44
E3 · DEPLOY, WEEK 43
Two-Clock Problem at Deploy
DESCRIPTION
Lewin is technically eligible to call "Refreeze" on the Deploy week's calendar date, while Bridges and Kübler-Ross across most cohorts still read Neutral Zone or lower — the organizational clock and the emotional clock diverging exactly as designed to anticipate.
TRIGGER
Technical go-live succeeds while emotional-layer evidence remains pending re-pulse.
TIMELINE IMPACT
No delay to go-live itself — the discipline costs nothing when there is no lag, and catches the case when there is one.
RECOVERY TASKS
Mark Lewin "Change → Refreeze (provisional)," not confirmed; require the 2- and 4-week Bridges/Kübler-Ross re-pulse across all three sites before calling Refreeze.
OUTPUTS: A provisional Lewin state; confirming evidence at Weeks 45/47/50. RACSI: R = CM · A = ES · C = PM · S = FPO · I = SUP, EU
journi — ERP Implementation (Bouregreg ERP Adoption Program)
43

## Slide 45
E4 · HYPERCARE, WEEKS 45–46
Sentiment Regression During Hypercare
DESCRIPTION
Kenitra's Kübler-Ross reading moves backward from Exploration to Resistance/Anger following a visible, embarrassing stock-count error caused by a configuration defect.
TRIGGER
A cohort's Kübler-Ross reading moves backward on M6 following a specific triggering event.
TIMELINE IMPACT
Resolved within the same week — the defect is fixed and communicated inside Hypercare's own window.
RECOVERY TASKS
Resolve Defect #31; the Kenitra supervisor holds a team huddle acknowledging the incident directly; targeted coaching on the affected stock-count step.
OUTPUTS: A closed defect; a logged coaching action on M11; a confirmed sentiment recovery. RACSI: R = SUP · A = ES · C = ITL · S = CM · I = PM, EU
journi — ERP Implementation (Bouregreg ERP Adoption Program)
44

## Slide 46
E5 · SUSTAIN, WEEKS 53–56
Reinforcement Gap at Sustain
DESCRIPTION
ADKAR Reinforcement stalls below 3 as the program's formal end date approaches, with no forcing deadline prompting continued attention — the exact risk Sustain's evidence-based discipline exists to prevent.
TRIGGER
Reinforcement score stalls below 3 on M5 near the program's formal close.
TIMELINE IMPACT
Extends the Refreeze call past the original close date — accepted, since Refreeze is called from evidence, never the calendar.
RECOVERY TASKS
CFO re-authorizes a further checkpoint cadence at 105 and 120 days; the champion network is re-chartered specifically for reinforcement.
OUTPUTS: Two further consecutive healthy checkpoints; a Refreeze call backed by that evidence. RACSI: R = CM · A = ES · C = PM · S = FPO · I = SUP, EU
journi — ERP Implementation (Bouregreg ERP Adoption Program)
45

## Slide 47
E6 · TRAIN–HYPERCARE, WEEKS 36–48
Cohort Divergence Across Sites
DESCRIPTION
Casablanca, Kenitra, and Settat read genuinely differently across all four frameworks by mid-Train, making the project-level Composite Readiness Index a misleading blend of three very different real situations.
TRIGGER
Site-level ADKAR/Bridges readings diverge sharply enough that a single blended CRI would mislead the Steering Committee.
TIMELINE IMPACT
No gate delay — the fix is a reporting discipline, not a schedule change.
RECOVERY TASKS
Disaggregate the Composite Readiness Index by site using M4's site tags; flag the lagging site for a second training wave; track the three readings separately until they converge.
OUTPUTS: A disaggregated CRI reporting practice, carried forward as the standing reporting standard. RACSI: R = CM, PM · A = CM · C = ES · S = FPO · I = SUP, EU
journi — ERP Implementation (Bouregreg ERP Adoption Program)
46

## Slide 48
PART 5 — TRAINING PROGRAM
What This Training Covers
Per the E2E-ERP chain, MP-05 runs at full weight across the Train phase — role-based training by cohort, with sandbox practice hours tracked separately from classroom completion.
journi — ERP Implementation (Bouregreg ERP Adoption Program)
47

## Slide 49
PART 5 · TIER 1 OF 3
Strategic Management
Cohort: CFO, Executive Viewer, Site Directors · Weeks 8–17
Curriculum Entry | Content Focus
Sponsoring a Full System Cutover | Why visible, sustained sponsorship matters more here than in any narrower archetype.
Reading a Divergence Pattern Alert | How to read ALT-001 as real evidence, not a false alarm.
journi — ERP Implementation (Bouregreg ERP Adoption Program)
48

## Slide 50
PART 5 · TIER 2 OF 3
Operational Management
Cohort: Driss El Amrani, Houda Zerouali, site supervisors · Weeks 22–39
Curriculum Entry | Content Focus
Barrier-Note Clustering and Response | Turning individual barrier notes into a targeted, root-cause recovery.
Running a Loss-Focused 1:1 | The specific coaching technique behind Exception E2's resolution.
journi — ERP Implementation (Bouregreg ERP Adoption Program)
49

## Slide 51
PART 5 · TIER 3 OF 3
Operations (Frontline)
Cohort: All 3,400 end users, by site and cohort · Weeks 35–50
Curriculum Entry | Content Focus
New System Navigation, By Module | Order Management, Inventory, and Finance, each trained separately by cohort.
Sandbox Practice Under Supervision | Hands-on rehearsal before go-live, tracked separately from classroom attendance.
journi — ERP Implementation (Bouregreg ERP Adoption Program)
50

## Slide 52
PART 5 — TRAINING PROGRAM
Why This Curriculum Is Shaped This Way
Training completion alone does not close this program — Reinforcement, the slowest-moving ADKAR block, is what Sustain's checkpoints exist to verify, months after the last training session ends.
journi — ERP Implementation (Bouregreg ERP Adoption Program)
51

## Slide 53
CROSS-REFERENCE
Which journi Modules Dominate This Archetype
M17 (WBS & Gantt)
The 8-phase TPL-ERP-8 template — the longest, most detailed schedule of any archetype.
M5 (ADKAR Engine)
Scored per site/cohort — the direct input to catching site-level divergence.
M9 (Training)
The Train phase's entire content — job aids, sandbox environments, per-site delivery waves.
M12 (Sustainment)
The Hypercare-to-Sustain handoff — the checkpoint that justifies closing Lewin at Refreeze.
M14 (Analytics)
The Composite Readiness Index, disaggregated by site when a blended number would mislead.
M6 (Emotional & Transition Layer)
Bridges and Kübler-Ross, cross-referenced with ADKAR to compute ALT-001.
journi — ERP Implementation (Bouregreg ERP Adoption Program)
52

## Slide 54
ALERTS & PROOF
What This Case Fires
ALERTS THIS CASE EXERCISES
ALT-001 (Divergence Pattern Detected)
ALT-009 (Phase Gate No-Go/Conditional, if any gate closes non-Go)
WHY
The throughline case — the one most likely to exercise a Knowledge/Ability-vs-Bridges divergence, given its scale and duration.
journi — ERP Implementation (Bouregreg ERP Adoption Program)
53

## Slide 55
KEY TAKEAWAYS
What to Remember About This Archetype
› A real Divergence Pattern catch before go-live (Casablanca, Week 28), a real cross-site Composite Readiness Index disaggregation (Exception E6), and a Refreeze called only once Sustain's own 90-day checkpoint evidence supports it — not the go-live date.
› ADKAR and Lewin dominate equally, throughout. A system cutover needs organizational readiness (Lewin's Change → Refreeze) and individual capability (ADKAR's Knowledge/Ability) at the same time — neither alone is sufficient, and unlike every other archetype in this series, that is true across all 8 phases, not concentrated in one.
› The throughline case — the one most likely to exercise a Knowledge/Ability-vs-Bridges divergence, given its scale and duration.
journi — ERP Implementation (Bouregreg ERP Adoption Program)
54

## Slide 56
ERP Implementation
Bouregreg ERP Adoption Program
Manufacturing Sector · Bouregreg Group Scenario Library · Confidential